## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
December 18, 2008

## Slide 2: PMO Update - Agenda
  2008 Project Spending Update
  2009 Project Reforecast Update
    $250k budget adjustment to the CO list
  4Q Unfunded Projects Update
  Recent Project Implementations
    November 2008

## Slide 3: 2008 Project Spending Update – 12/15/2008
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 8,450,000 | $ 5,676,754 | $ 5,444,675
IO | $ 6,400,000 | $ 8,031,000 | $ 7,362,876
MO | $ 1,200,000 | $ 1,394,906 | $ 1,273,674
RO | $ 6,100,000 | $ 3,635,094 | $ 2,791,330
SO | $ 50,000 | $ 1,071,795 | $ 904,155
Nodal / Zonal Interdependent | $ 5,314,000 | $ 6,715,129 | $ 6,715,130
Released but Not Reallocated | $ 0 | $ 989,322 | $ 0
Total | $ 27,514,000 | $ 27,514,000 | $ 24,491,839
CO – Met Center * | $ 0 | $ 6,232,880 | $ 1,234,474
* Met Center project is not funded by initial project budget allocation
Arrows indicate trend since last report (October 2008)

## Slide 4: 2009 Project Reforecast –Schedule
2009 Project Prioritization Schedule - Overview
  Q1 2008
    2009 Initiative Lists drafted, revised and approved for inclusion in ERCOT budget request
  September 2008
    CARTs revise 2009 Initiative Lists to prepare for market review
  October 2008
    Initial review by market subcommittees
      MO list approved by COPS, RO list approved by RMS
  November 2008
    Review by TAC (November 6)
    Additional input from ROS, WMS (November 13 / November 19)
    PRS approval of all CART lists (November 20)
  December 2008
    Review by TAC (December 4)
      No action taken because ERCOT will not be submitting their 2009 budget until January

## Slide 5: 2009 Project Reforecast – Recent Activity
2009 Project Approval Status by Program Area
  CO (Corporate Operations)
    7 projects able to initiate due to approval of $1.2M “capability” funding
    $250k increase to Taylor Reconfiguration
  IO (IT Operations)
    No changes since Executive Team review on 10/13/2008
  MO (Market Operations)
    Modified and approved by COPS on 10/14/2008
  RO (Retail Operations)
    Modified and approved by RMS on 10/15/2008
  SO (System Operations)
    ROS and WMS reviews resulted in the following:
      Addition of an SO placeholder of $500k to fund efforts being considered as a result of the Nodal Go-Live delay
        Examples: PRR675, PRR601, PRR409, SCR720, SCR728
      Additional PPL line item for PRR776 discussed
        Pending the results of the Impact Analysis currently in progress
        Alternative language to PRR776 also being considered
  New budget estimate = $12.95M

## Slide 6: 2009 Project Reforecast – Summary by CART
** CO – Met Center | $ 20,400,000 | $ 20,400,000 | $ 0
* Revised 2009 project budget is $12.95M
** Met Center project is funded by a separate budget line item
CART | Initial 2009 Budget | Revised Draft 2009 Budget | Change
CO | $ 3,550,000 | $ 2,025,000 | ($ 1,525,000)
IO | $ 8,350,000 | $ 5,525,000 | ($ 2,825,000)
MO | $ 4,300,000 | $ 550,000 | ($ 3,750,000)
RO | $ 3,500,000 | $ 3,450,000 | ($ 50,000)
SO | $ 7,500,000 | $ 1,400,000 | ($ 6,100,000)
Total | $ 27,200,000 | * $ 12,950,000 | ($ 14,250,000)

## Slide 7: PMO Update - Unfunded Project List
Unfunded Project List – Quarterly Update
  There are not any unfunded projects at this time
    No change since last report
  Note: Reassessment of several previously approved (but not implemented) PRRs and SCRs is underway
    PRR601, PRR675, PRR409, SCR720, SCR728

## Slide 8: PMO Update - YTD 2008 Project Implementations
January 2008
  IO PR-70050_01 EIS ETL Tool Implementation
February 2008
  CO PR-70044_01 MET Center Facility Analysis
  RO PR-70005_01 MO SAS70 Procedures Optimization
  IO PR-70012_01 Cyber Security Project #14
  IO PR-70037_01 OC-3 Microwave Replacement
  SO PR-70035_01 2007 REC Program Modifications
March 2008
  IO PR-60055_01 Enterprise Service Management
  IO PR-60013_01 Enhanced Digital Certificate Program
  MO PR-70038_01 ERCOT.com Infrastructure Enhancement
        (Collage Infrastructure Redesign)
  CO PR-70013_01 Corporate Document Management
  CO PR-70041_01 Taylor Control Room Display System Replacement
April 2008
  None

## Slide 9: PMO Update - YTD 2008 Project Implementations (cont’d)
May 2008
  MO PR-70048_01 MV90xi System Upgrade
  CO PR-70053_01 Video Teleconferencing
  IO PR-70055_01 Additional Production SAN Capacity
June 2008
  MO PR-60077_01 ERCOT.com Registered Area
  IO PR-70030_01 Tellabs DCCS System Replacement
  IO PR-80022_01 Additional SAN Capacity for Projects
July 2008
  RO PR-60008_01 Terms and Conditions & Performance Measures
  CO PR-70023_01 CyberSecurity Project #2
  CO PR-70047_01 Corporate Application Environment True-Up
  CO PR-80010_01 Ruby Standardization
  CO PR-60073_01 eRecruiting

## Slide 10: PMO Update - YTD 2008 Project Implementations (cont’d)
August 2008
  RO PR-60015_01 Siebel Data Model Assessment
  CO PR-80035_01 Intranet Assessment HR & Communications
  IO PR-70054_01 Blade Refresh
September 2008
  MO PR-40066_04 Lodestar 4.7 Upgrade
  SO PR-50070_01 Unit Testing Automation and Electronic Submittal – Phase 1
October 2008
  IO PR-80023_01 Firewall Replacement
  CO PR-60094_01 Physical Access Control Upgrade
  CO PR-50015_03 Lawson Procurement Process Flow
  CO PR-60020_02 Lawson 9x Upgrade

## Slide 11: PMO Update - YTD 2008 Project Implementations (cont’d)
November 2008
  SO PR-80037_01 Starter Phasor Monitoring System (SPMS)
  RO PR-70006_02 Website Enhancements for ERCOT Outage Notification Phase 2
  MO PR-70057_01 AMIT Study for Long Term Settlement Solution