## Slide 1: Texas Nodal Program Implementation: Program Update
Ron Hinsley

## Slide 2: Agenda
Highlights
Scope Management
Staffing
Preliminary Schedule Reviews
Top Risks / Issues
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 3: Highlights – 1
No tasks on the program critical path are currently behind schedule
Core Project Highlights
  NMMS delivered a synchronized model (v1.21 schema and data set) on Dec. 10 – a major milestone delivered on time.
  EMS Outage Evaluation, Voltage Support, Interfaces, and Displays release completed FAT on Nov. 14. The team recently also completed FAT testing on the Habitat 5.6 Security Patch on Dec. 11
  MMS4 FAT for Patch5 completed on Nov. 21. MMS4 FAT testing for Patch6 is currently underway
  CRR FAT for Patch1.08 completed on Dec. 11. This completes FAT for the CRR4 release
  COMS completed FAT on their Registration/Disputes release (REG4/DISP2) on Dec. 10 and completed a migration to production on Dec. 14. They also completed FAT on the Settlement & Billing Data Aggregation release (Lodestar bundle for data aggregation re-write) on Dec. 19

## Slide 4: Highlights – 2
Utilicast released their report of the assessment of the new integrated schedule and budget on Dec. 19
  Report cites progress in program controls, accountability and transparency
  Also outlines remaining challenges and risks (see risk slide)
ERCOT looking into alternatives to renegotiating contracts with product vendors
Notes: Staffing – November numbers are preliminary.

## Slide 5: Program Scope is Locked Down
Scope for the December 2010 release of the Nodal Program schedule should be locked down with any proposed changes subject to a strict change control process – Utilicast
New change requests (NPRRs, SCRs, CIs) will be judged on impact to schedule and budget
ERCOT will comment on schedule and budget impact only, not on market need
Comments have been submitted for NPRR164
SCR752 discussion – impact to Outage Scheduler
Notes: Staffing – November numbers are preliminary.

## Slide 6: Staffing
Employees 163
Contractors 164

## Slide 7: Preliminary Schedule Reviews
Review Activity | Date
Present schedule to TPTF for initial review | Dec. 10, 2008 (completed)
Gather initial TPTF feedback | Dec. 16, 2008 (completed)
Present revised schedule to TPTF for additional reviews and incorporate feedback; finalize budget | January 2009
Present to TAC and incorporate feedback | February 2009
Present to Special Nodal Program Committee and incorporate feedback | February 2009
Present to Board of Directors and incorporate feedback | February 2009
Present to PUCT | TBD
Initial TPTF review and discussion conducted on Dec. 10 and Dec. 16
Additional detailed discussion and work session with TPTF scheduled for Jan. 7
Proposed high-level review timeline

## Slide 8: Top Risks / Issues – 1
Description | Status
(Risk: Dec. 12) Existing integration testing strategy (i.e., planning approach, team structure, methodology), as well as the tactical implementation (i.e., execution plan, resource plan, testing schedules) may not be adequate to successfully perform integration. | The Integration Team is working to provide more specific task-level scheduling details for the utilization of Functional SMEs from the projects to support Functional Integration Test (FIT) and Business Scenarios (E2E) test execution activities. Meetings with core product PMs are underway. A new Integration Lab (iLab) environment is underway to support more integration component testing in parallel with FAT. The objective is to identify and resolve integration adaptor issues prior to migrating the applications and associated integration adaptors to iTest.
(Risk: Dec 19) Stability and the ability to physically expand the current IT infrastructure (environments) is a risk to the nodal program schedule. | Plans are underway for new data centers that will be online in sufficient time to support go-live.
(Risk: Dec 19): Scope creep may adversely impact the schedule. The nodal project requirements have not been finalized and locked down. | Change control process has more executive oversight incorporated. All functionality has been locked as of Dec 19; changes after this date will likely impact schedule and/or budget.

## Slide 9: Top Risks / Issues – 2
Description | Status
(Risk: Oct 17) Information Lifecycle Management (ILM) strategy for ERCOT is behind schedule. Current processes do not adequately address archival and storage requirements for nodal; existing data center constraints limit new storage growth. Without ILM in place and executed, the nodal program go-live data could be delayed because of insufficient storage. | SAIC has been engaged to complete the Road Map for an ILM strategy at ERCOT. Estimated 6 week effort, then the ILM Project will proceed. Interviews for ILM PM conducted.
(Risk: Nov. 21) With the delayed go-live for Nodal, there are a number of Zonal projects, PRRs, and IMM suggestions for Zonal improvements that may result in resource constraints for Nodal. | Currently in process of identifying potential resource conflicts so that ERCOT can reprioritize scheduled Nodal activities and/or identify new resources to perform the additional work.
(Risk: Nov. 21) In order to keep the multiple database environments in synch (Dev, iTest, Prod), a refresh of the associated databases must be completed. This activity is estimated to take approximately one month based on prior refreshes. Actual downtime is estimated at one to two weeks and has not been incorporated into the schedule. | Tentatively scheduled for March 2009; working closely with Nodal project teams to minimize downtime impacts. Will also need to plan for another refresh in 2010.

## Slide 10
Questions?