## Slide 1: TPTF Update for TAC January 8, 2009 Joel Mickey jmickey@ercot.com
http://nodal.ercot.com <number>
Notes: <number>

## Slide 2: Agenda:
http://nodal.ercot.com <number>
Item | Description | Purpose
1. Meeting Summary | Summary of recent TPTF activities | For Review
2. Vote Summary | Summary of recent TPTF Votes | For Review
3. Next Meetings | Upcoming activities | For Review
4. Approval of Milestones | N/A | For Vote
Notes: <number>

## Slide 3
http://nodal.ercot.com <number>
Meeting Summary:
Since the previous TAC Meeting:
  TPTF participated in a Preliminary Nodal Schedule Review:
    December 10, 2008
  TPTF held one regularly scheduled TPTF Meeting:
    December 15 – 16, 2008
Notes: <number>

## Slide 4
http://nodal.ercot.com <number>
Meeting Summary – December 10, 2008:
On December 10, 2008, TPTF participated in a Preliminary Nodal Schedule Review:
  During the review, TPTF was provided with an overview of the Preliminary Nodal Integrated Program Schedule, including the following key documents (see postings at http://nodal.ercot.com/about/po/sch/index.html):
    Preliminary Nodal Integrated Program Timeline
    Preliminary Early Delivery Systems (EDS) Project Timeline
    Preliminary Program Milestones and Critical Path
Initial TPTF feedback from this preliminary review was discussed during the regularly scheduled TPTF meeting on December 16, 2008.
Notes: <number>

## Slide 5
http://nodal.ercot.com <number>
Meeting Summary – December 15 – 16, 2008:
On December 15, TPTF discussed:
  Change Process Discussion:
    In light of the new Preliminary Nodal Integrated Program Schedule, TPTF requested that ERCOT provide a January 2009 discussion at TPTF to clarify the current change process, the role of TPTF in reviewing NPRRs/SCRs/NOGRRs, and the possible need to update the document Managing Protocol Content During Texas Nodal Market Implementation
  NPRR Updates:
    NPRR135, Deletion of Unaccounted For Energy (UFE) Analysis Zone Language:
      TPTF took no action on NPRR135 but requested that a nodal impact analysis be posted prior to the assignment of an essentiality status
    NPRR146, Inter-Control Center Communication Protocol (ICCP) Telemetry Information Submittals:
      On December 15, 2008, TPTF reviewed NPRR146 as remanded by PRS and endorsed TPTF comments to be submitted to PRS. The endorsement carried by unanimous roll-call vote. The Consumer Market Segment was not represented for the vote.
    NPRR149, Change the name of Emergency Electric Curtailment Plan (EECP) to Energy Emergency Alert (EEA):
      TPTF took no action on NPRR149 but requested that a nodal impact analysis be posted prior to the assignment of an essentiality status
Notes: <number>

## Slide 6
http://nodal.ercot.com <number>
Meeting Summary – December 15 – 16, 2008:
On December 15, TPTF discussed (continued):
  NPRR Updates (continued):
    NPRR155, Clarification of Authorized Representative:
      TPTF took no action on this NPRR
    NPRR165, Synchronizing Section 1 with PRR697:
      TPTF deferred discussion of NPRR165 to January 2009
    Draft NPRR, Clarify the Calculation and Posting of Locational Marginal Prices (LMPs) for the Load Zone and LMPs for Each Hub:
      On December 15, 2008, TPTF endorsed this draft NPRR to be submitted to PRS on behalf of TPTF with a preliminary essentiality status of "Needed for Go-Live." TPTF requested that an Impact Analysis (IA) be performed by ERCOT and returned to TPTF as soon as possible. The endorsement carried by roll-call vote with 100% in favor and one abstention from the Independent Power Marketer (IPM) Market Segment. The Independent Generator and Consumer Market Segments were not represented for the vote.
      This draft NPRR was subsequently posted as NPRR169
Notes: <number>

## Slide 7
http://nodal.ercot.com <number>
Meeting Summary – December 15 – 16, 2008:
On December 15, TPTF discussed (continued):
  Reliability Unit Commitment (RUC) Implementation:
    TPTF received clarifications regarding how the current RUC implementation reflects Nodal Protocols. TPTF provided feedback to the clarifications for additional consideration during a future TPTF meeting.
  Business Requirements Update:
    TPTF discussed the proposed approach to reviewing Business Requirements and Conceptual System Designs (CSDs), which are currently being updated to reflect the incorporation of post-Baseline 2 NPRRs, NOGRRs, and SCRs. TPTF will begin reviewing/approving the updated documentation in early 2009.
Notes: <number>

## Slide 8
http://nodal.ercot.com <number>
Meeting Summary – December 15 – 16, 2008:
On December 16, TPTF discussed:
  Program Status Update
  Preliminary Nodal Integrated Program Schedule
    TPTF discussed initial feedback for the new schedule and requested that ERCOT coordinate an additional, ad hoc meeting to discuss the new schedule further on January 7, 2009
Notes: <number>

## Slide 9
Vote Summary – December 15 – 16, 2008:
Vote Item | Sector | For | Against | Abstention
On December 15, 2008, TPTF endorsed comments for NPRR146, ICCP Telemetry Information Submittals, to be submitted to PRS. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator | ■ |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | 
Note: the votes in this summary are available for pick-up from the December 15-16 TPTF Meeting Page.
http://nodal.ercot.com <number>
Vote Item | Sector | For | Against | Abstention
On December 15, 2008, TPTF endorsed the Draft NPRR, Clarify the Calculation and Posting of LMPs for the Load Zone and LMPs for each Hub, with a preliminary essentiality status of "Needed for Go-Live.” TPTF requested that the NPRR be submitted to PRS on behalf of TPTF and that the IA be performed by ERCOT and returned to TPTF as soon as possible. | Cooperative | ■ |  | 
 | Municipal | ■ |  | 
 | Investor Owned Utility | ■ |  | 
 | Independent Generator |  |  | 
 | Consumer |  |  | 
 | Independent REP | ■ |  | 
 | Independent Power Marketer | ■ |  | Westar Energy, Inc.

## Slide 10
http://nodal.ercot.com <number>
Next Meetings:
Next Meetings:
  January 7, 2009 – TPTF Preliminary Nodal Schedule Review
  January 12 – 13, 2009
  January 26 – 28, 2009
Visit the 2008 TPTF Calendar
Notes: <number>

## Slide 11
http://nodal.ercot.com <number>
Questions
?
Notes: <number>