## Slide 1: 2009 Project Reforecast
Troy Anderson
ERCOT Program Management Office
January 8, 2009

## Slide 2: 2009 Project Reforecast – Introductory Comments
2009 project budget has increased from $12.7M to $18.4M
Primary driver:
  ERCOT determined there is a critical need to expand the Taylor data center in order to properly maintain current operations
  This is in addition to the data center work planned as part of the Met Center Disposition project
  $6.75M project added to the CO list to expand the current Taylor data center into the remaining raised floor space of TCC1
ERCOT-wide effort to fund the data center expansion project and maintain the current 41.71 cent System Administration Fee
  ERCOT Strategic Review Team (SRT) recommended various reductions to the project budget to assist in the effort
  ERCOT executives elected to take two measures impacting projects
    Deferred the CO project to reconfigure the offices in TCC1
    Reduced the project contingency on all projects that are not yet started from 35% to 25%
    PUCT and market projects were exempt from the contingency reduction

## Slide 3: 2009 Project Reforecast – Schedule
2009 Project Prioritization Schedule
  Q1 2008
    2009 Initiative Lists drafted, revised and approved
  September 2008
    CARTs revise 2009 Initiative Lists to prepare for market review
  October 2008
    Initial review by market subcommittees
      Approved by COPS and RMS
  November 2008
    Additional updates by ROS, WMS (November 13 / November 19)
    PRS approved all project lists (November 20)
  January 2009
    Review by TAC (January 8)
    Available for F&A and Board (January 20)

## Slide 4: 2009 Project Reforecast – Activity Since PRS Approval
CO (Corporate Operations)
  Addition of Data Center Expansion to meet short term data center needs +$6.75M
  Deferral of Taylor TCC1 Office Reconfiguration -$0.45M
  Reduce contingency for projects not yet started -$0.02M
IO (IT Operations)
  Reduce contingency for projects not yet started -$0.41M
MO (Market Operations)
  Reduce contingency for projects not yet started (excludes market projects) -$0.03M
RO (Retail Operations)
  Reduce contingency for projects not yet started (excludes market projects) -$0.06M
SO (System Operations)
  Reduce contingency for projects not yet started (excludes market projects) -$0.05M
  Continuing effort to update Impact Analyses and CBAs for:
    PRR601, PRR675, PRR409, SCR720, SCR728
    Expect to have the updated IAs and CBAs available for PRS on 1/22
PRS reviewed and approved the combined project lists on 11/20/2008
  Project budget estimate at time of PRS approval = $12.7M
  New project budget estimate = $18.4M
    No impacts to PUCT and market projects

## Slide 5: 2009 Project Reforecast – Summary by CART
* Met Center | $ 20,400,000 | $ 20,400,000 | $ 0
* The Met Center project is funded by a separate line item in the ERCOT budget
Program Area | 2009 Budget Prior Revision | 2009 Budget Updated Revision | Change
CO | $ 1,775,000 | $ 8,060,000 | $ 6,285,000
IO | $ 5,525,000 | $ 5,115,000 | ($ 410,000)
MO | $ 550,000 | $ 520,000 | ($ 30,000)
RO | $ 3,450,000 | $ 3,390,000 | ($ 60,000)
SO | $ 1,400,000 | $ 1,350,000 | ($ 50,000)
Total | $ 12,700,000 | $ 18,435,000 | $ 5,735,000