## NPRRs
NPRR # | Source | Approval Status | Baseline | Needed for Go-Live? | Short Description | Submitter | Schedule Impact | Cost Impact | Legend | NPRR | NPRR Posting Date | TPTF Approval | PRS Approval #1 | IA Posting Date | PRS Approval #2 | TAC Approval | Board Approved Date
77 | NPRR | Approved | Post-Baseline2 | Yes | Incorporating the ERCOT Internal Audit Department and Other Clarifications (PRR735 companion) | ERCOT Staff | None | 0 | Light Green = Board approved | 77 | 2007-08-07 |  | 2007-08-23 | 2007-08-07 | 2007-10-18 | 2007-11-01 | 2007-12-11
78 | NPRR | Approved | Post-Baseline2 | Yes | Simplifying the Dispute Process | SDAWG | None | Minor to be absorbed | Yellow = Ready for TAC and/or Board approval | 78 | 2007-08-13 | 2007-09-11 | 2007-09-20 | 2007-11-14 | 2007-12-13 | 2008-01-11 | 2008-01-15
79 | NPRR | Rejected | Post-Baseline2 | N/A | Remove Shift Schedule Posting Requirement |  | N/A | N/A | Bright Green = Tabled at TAC waiting on Nodal Go-Live date | 79 | 2007-08-13: 2007-08-15; 2007-11-14: 2007-08-15; 2007-12-13: 2007-08-23
80 | NPRR | Approved | Post-Baseline2 | Yes | Revised Wording of Protocol Section 3.1.5.1 (Electrical buses as consequentially outaged transmission elements.) | Center Point | None | 0 | Tan = Tabled at PRS | 80 | 2007-08-16 | 2007-08-14 | 2007-08-23 | 2007-09-17 | 2007-09-20 | 2007-10-05 | 2007-10-16
81 | NPRR | Approved | Post-Baseline2 | Yes | Automatic Voltage Regulator (AVR) Status | ERCOT Staff | None | <$50k | Orange = Reduction in scope | 81 | 2007-08-31 | 2007-09-10 | 2007-09-20 | 2007-11-08 | 2007-11-15 | 2008-03-06 | 2008-03-18
82 | NPRR | Approved | Post-Baseline2 | Yes | Section 8, Performance Monitoring and Compliance, Revisions to Monitoring and Qualification Tests | TPTF | None | $50k-$100k | Gray = post-implementation cost savings for ERCOT | 82 | 2007-09-11 | 2007-09-25 | 2007-10-18 | 2007-10-29 | 2007-11-15 | 2007-11-29 | 2007-12-11
83 | NPRR | Approved | Post-Baseline2 | Yes | Remove Real-Time Energy Charge for a BLT from List of Real-Time Charge Types | ERCOT Staff | None | 0 | Withdrawn or rejected | 83 | 2007-10-11 | 2007-10-14 | 2007-10-18 | 2007-11-14 | 2007-11-15 | 2007-11-29 | 2007-12-11
84 | NPRR | Approved | Post-Baseline2 | Yes | Creating Amendment to Standard Form Market Participant Agreement | ERCOT Staff | None | 0 | No shading = Pending at TPTF, PRS, or other subcommittee | 84 | 2007-10-23 | 2007-12-05 | 2007-12-13 | 2008-01-17 | 2008-01-17 | 2008-02-07 | 2008-02-19
85 | NPRR | Approved | Post-Baseline2 | Yes | Revision of Digital Certificate Procedures | ERCOT Staff | None | 0 |  | 85 | 2007-10-24 | 2007-11-26 | 2007-12-13 | 2008-01-16 | 2008-01-17 | 2008-02-07 | 2008-02-19
86 | NPRR | Approved | Post-Baseline2 | Yes | Settlement Clarifications to RUC Capacity Shortfall Ratio Share Formula | TPTF | None | 0 |  | 86 | 2007-10-25 | 2007-10-08 | 2007-11-15 | 2007-12-12 | 2007-12-13 | 2008-01-03 | 2008-01-15
87 | NPRR | Approved | Post-Baseline2 | Yes | Market Monitor Terminology Change | ERCOT Staff | None | 0 |  | 87 | 2007-10-30 | 2007-11-11 | 2007-11-15 | 2007-12-12 | 2007-12-13 | 2008-01-03 | 2008-01-15
88 | NPRR | Approved | Post-Baseline2 | Yes | Revision to 16.11.5, Monitoring of a Counter-Party’s Creditworthiness and Credit Exposure by ERCOT | Reliant | None | 0 |  | 88 | 2007-10-31 | 2007-11-05 | 2007-12-13 | 2008-01-17 | 2008-01-17 | 2008-02-04 | 2008-02-19
89 | NPRR | Approved | Post-Baseline2 | Yes | Changing Posting Requirement of Certain Documents from MIS Secure to Public Area | ERCOT Staff | None | 0 |  | 89 | 2007-11-07 | 2007-12-20 | 2008-01-17 | 2008-02-21 | 2008-02-21 | 2008-03-06 | 2008-03-18
90 | NPRR | Approved | Post-Baseline2 | Yes | Corrections of FIP-FOP in Energy Offers | TPTF | None | <$50k |  | 90 | 2007-12-05 | 2007-12-03 | 2007-12-13 | 2008-01-17 | 2008-01-17 | 2008-02-07 | 2008-02-19
91 | NPRR | Tabled by TAC waiting on Nodal Go-Live date | Post-Baseline2 | Yes | Scarcity Pricing and Mitigated Offer Cap During the Period Commencing on the Nodal Market Implementation Date and Continuing for a Total of 45 Days | TPTF | None | $50k-$100k |  | 91 | 2007-12-05 | 2007-12-18 | 2008-05-22 | 2008-06-18 | 2008-07-17
92 | NPRR | Approved | Post-Baseline2 | Yes | Remove Voltage Schedules Requirement | ERCOT Staff | None | 0 |  | 92 | 2007-12-14 | 2008-01-22 | 2008-02-21 | 2008-03-14 | 2008-03-20 | 2008-04-04 | 2008-04-15
93 | NPRR | Withdrawn | Post-Baseline2 | N/A | Clarification to Definition of DUNS Number; Section 2, Definitions and Acronyms | ERCOT Staff | N/A | N/A |  | 93 | 2007-12-14: 2007-12-14
94 | NPRR | Approved | Post-Baseline2 | Yes | Correct Reference to Credit Limit Determination | TPTF | None | 0 |  | 94 | 2008-01-02 | 2008-01-02 | 2008-01-17 | 2008-02-14 | 2008-02-21 | 2008-03-06 | 2008-03-18
95 | NPRR | Approved | Post-Baseline2 | Yes | Clarify Recipients of McFRIs | TPTF | None | 0 |  | 95 | 2008-01-02 | 2008-01-02 | 2008-01-17 | 2008-02-14 | 2008-02-21 | 2008-03-06 | 2008-03-18
96 | NPRR | Approved | Post-Baseline2 | Yes | Nodal Protocol Revisions to the RMR Startup Energy Payment | ERCOT Staff | None | 0 |  | 96 | 2008-01-07 | 2007-12-19 | 2008-01-17 | 2008-02-14 | 2008-02-21 | 2008-03-06 | 2008-03-18
97 | NPRR | Approved | Post-Baseline2 | Yes | Changes to Section 8 to Incorporate role of TRE, the IMM, and the concept of Market Compliance | TPTF | None | $100k-$250k |  | 97 | 2008-01-08 | 2008-03-07 | 2008-04-18 | 2008-05-21 | 2008-05-22 | 2008-06-26 | 2008-08-19
98 | NPRR | Approved | Post-Baseline2 | Yes | Protocols 4 and 6 Formula Clarifications | TPTF | None | 0 |  | 98 | 2008-01-08 | 2008-01-08 | 2008-01-17 | 2008-02-14 | 2008-02-21 | 2008-03-06 | 2008-03-18
99 | NPRR | Approved | Post-Baseline2 | Yes | RMR Incentive Factor Payment | TPTF | None | 0 |  | 99 | 2008-01-09 | 2008-01-09 | 2008-02-21 | 2008-03-14 | 2008-03-20 | 2008-04-04 | 2008-04-15
100 | NPRR | Approved | Post-Baseline2 | Yes | Removing PCRR release mechanism | TPTF | None | 0 |  | 100 | 2008-01-14 | 2008-01-07 | 2008-02-21 | 2008-03-14 | 2008-03-20 | 2008-04-04 | 2008-04-15
101 | NPRR | Approved | Post-Baseline2 | Yes | Modify Time Requirements for Entry of Equipment in the Outage Scheduler | TPTF | None | 0 |  | 101 | 2008-02-06 | 2008-02-05 | 2008-02-21 | 2008-03-19 | 2008-03-20 | 2008-04-04 | 2008-04-15
102 | NPRR | Approved | Post-Baseline2 | Yes | PUCT 25.505 Publication of Resource and Load Information (Disclosure of market data (PRR697 / PUCT33490)) | TPTF | None | $1.5M-$2.0M |  | 102 | 2008-02-12 | 2008-08-12 | 2008-05-22 | 2008-09-23 | 2008-09-24 | 2008-10-02 | 2008-10-21
103 | NPRR | Approved | Post-Baseline2 | Yes | Settlement of Power Imported via DC Ties (Back to Back Ties) and Block Load Transfer Under Emergency Conditions | TPTF | None | 0 |  | 103 | 2008-02-13 | 2008-02-04 | 2008-02-21 | 2008-03-13 | 2008-03-20 | 2008-04-04 | 2008-04-15
104 | NPRR | Withdrawn | Post-Baseline2 | N/A | Corrections and Clarifications for Real Time Settlements and Ancillary Service Net Obligations | ERCOT Staff | N/A | N/A |  | 104 | 2008-01-08: 2008-02-15
105 | NPRR | Approved | Post-Baseline2 | Yes | Section 23, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 105 | 2008-02-26 | 2008-03-31 | 2008-04-18 | 2008-05-15 | 2008-05-22 | 2008-06-05 | 2008-06-17
106 | NPRR | Approved | Post-Baseline2 | Yes | Section 24, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 106 | 2008-02-26 | 2008-03-31 | 2008-04-18 | 2008-05-15 | 2008-05-22 | 2008-06-05 | 2008-06-17
107 | NPRR | Approved | Post-Baseline2 | Yes | Emergency Interruptible Load Service | ERCOT Staff | None | <$50k |  | 107 | 2008-02-29 | 2008-06-09 | 2008-05-22 | 2008-06-18 | 2008-06-19 | 2008-06-26 | 2008-07-15
108 | NPRR | Approved | Post-Baseline2 | Yes | Fuel Oil Price (FOP) Clarification | ERCOT Staff | None | 0 |  | 108 | 2008-03-03 | 2008-02-21 | 2008-03-20 | 2008-04-16 | 2008-04-18 | 2008-05-08 | 2008-05-20
109 | NPRR | Approved | Post-Baseline2 | Yes | Section 18, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 109 | 2008-03-03 | 2008-04-07 | 2008-04-18 | 2008-05-15 | 2008-05-22 | 2008-06-05 | 2008-06-17
110 | NPRR | Approved | Post-Baseline2 | Yes | Section 20, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 110 | 2008-03-03 | 2008-04-07 | 2008-04-18 | 2008-05-15 | 2008-05-22 | 2008-06-05 | 2008-06-17
111 | NPRR | Approved | Post-Baseline2 | Yes | Timelines for Response by ERCOT to TSP Requests | ERCOT Staff | None | 0 |  | 111 | 2008-03-04 | 2008-05-06 | 2008-05-22 | 2008-06-02 | 2008-06-19 | 2008-06-26 | 2008-07-15
112 | NPRR | Approved | Post-Baseline2 | Yes | Emergency Base Point Price Revision | ERCOT Staff | None | 0 |  | 112 | 2008-03-05 | 2008-02-29 | 2008-03-20 | 2008-04-16 | 2008-06-19 | 2008-06-26 | 2008-07-15
113 | NPRR | Approved | Post-Baseline2 | Yes | Load Resource Type Indicator for Ancillary Service (AS) Trades and Self-Arranged AS | ERCOT Staff | None | $500K- $1.0M |  | 113 | 2008-03-11 | 2008-03-27 | 2008-05-22 | 2008-09-24 | 2008-09-24 | 2008-10-02 | 2008-10-21
114 | NPRR | Approved | Post-Baseline2 | Yes | Section 11, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 114 | 2008-03-14 | 2008-06-05 | 2008-06-19 | 2008-07-10 | 2008-07-17 | 2008-08-07 | 2008-08-19
115 | NPRR | Withdrawn | Post-Baseline2 | N/A | Grey-Boxing of Settlement and Billing Related Information Calculation | ERCOT Staff | N/A | N/A | Light Green = Board approved | 115 | 2008-03-14: 2008-03-17
116 | NPRR | Withdrawn | Post-Baseline2 | N/A | Addition of Commercially Traded Points to Settlement Point List | DB Energy Trading | N/A | N/A | Yellow = Ready for TAC and/or Board approval | 116 | 2008-03-14: 2008-03-25
117 | NPRR | Approved | Post-Baseline2 | Yes | Resource Registration Clarification | ERCOT Staff | None | 0 | Bright Green = Tabled at TAC waiting on Nodal Go-Live date | 117 | 2008-03-26 | 2008-05-09 | 2008-05-22 | 2008-06-06 | 2008-06-19 | 2008-06-26 | 2008-07-15
118 | NPRR | Approved | Post-Baseline2 | Yes | Section 14, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 | Tan = Tabled at PRS | 118 | 2008-03-27 | 2008-05-06 | 2008-05-22 | 2008-06-02 | 2008-06-16 | 2008-06-26 | 2008-07-15
119 | NPRR | Approved | Post-Baseline2 | Yes | Resource Limit Calculator | ERCOT Staff | None | 0 | Orange = Reduction in scope | 119 | 2008-03-27 | 2008-04-21 | 2008-05-22 | 2008-06-02 | 2008-06-19 | 2008-06-26 | 2008-07-15
120 | NPRR | Approved | Post-Baseline2 | Yes | Corrections and Clarifications for Real Time Settlements | ERCOT Staff | None | 0 | Gray = post-implementation cost savings for ERCOT | 120 | 2008-03-27 | 2008-05-07 | 2008-05-22 | 2008-06-02 | 2008-06-19 | 2008-06-26 | 2008-07-15
121 | NPRR | Withdrawn | Post-Baseline2 | N/A | System Parameters Posting Frequency | ERCOT Staff | N/A | N/A | Withdrawn or rejected | 121 | 2008-03-27: 2008-03-31
122 | NPRR | Approved | Post-Baseline2 | Yes | Simplify Ancillary Services Settlement Formulas | ERCOT Staff | None | 0 | No shading = Pending at TPTF, PRS, or other subcommittee | 122 | 2008-04-07 | 2008-05-07 | 2008-05-22 | 2008-06-02 | 2008-06-19 | 2008-06-26 | 2008-07-15
123 | NPRR | Approved | Post-Baseline2 | Yes | Inadvertent Energy Account Revision | ERCOT Staff | None | 0 |  | 123 | 2008-04-09 | 2008-05-05 | 2008-05-22 | 2008-06-12 | 2008-06-19 | 2008-06-26 | 2008-07-15
124 | NPRR | Approved | Post-Baseline2 | Yes | Resource Node Updated Definitions | ERCOT Staff | None | $100k-$150k |  | 124 | 2008-04-10 | 2008-07-07 | 2008-07-17 | 2008-09-23 | 2008-09-24 | 2008-10-02 | 2008-10-21
125 | NPRR | Withdrawn | Post-Baseline2 | N/A | Creation of a New Trading Hub at Venus Switching Station | DB Energy Trading | N/A | N/A |  | 125 | 2008-04-10: 2008-04-11
126 | NPRR | Approved | Post-Baseline2 | Yes | Section 19, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 126 | 2008-04-14 | 2008-06-23 | 2008-07-17 | 2008-08-13 | 2008-08-21 | 2008-09-04 | 2008-09-16
127 | NPRR | Approved | Post-Baseline2 | Yes | Section 22 Attachments A, I, J & M, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 127 | 2008-04-23 | 2008-06-09 | 2008-06-19 | 2008-07-10 | 2008-07-17 | 2008-08-07 | 2008-08-19
128 | NPRR | Approved | Post-Baseline2 | Yes | Combined Cycle Power Blocks with Multiple Voltage Interconnections | Calpine | None | $100k-$150k |  | 128 | 2008-04-25 | 2008-06-03 | 2008-06-19 | 2008-10-13 | 2008-10-23 | 2008-11-06 | 2008-11-17
129 | NPRR | Approved | Post-Baseline2 | Yes | Section 15, Synchronization of Zonal Protocols | ERCOT Staff | None | 0 |  | 129 | 2008-05-01 | 2008-07-22 | 2008-08-21 | 2008-09-22 | 2008-09-24 | 2008-10-02 | 2008-10-21
130 | NPRR | Approved | Post-Baseline2 | Yes | CRR Settlements Revenue Equalization | TPTF | None | $50k-$100k |  | 130 | 2008-05-09 | 2008-05-04 | 2008-05-22 | 2008-06-18 | 2008-06-19 | 2008-06-26 | 2008-07-15
131 | NPRR | PRS tabled due to "Approved Post-Go-Live" status | Post-Baseline2 | Approved Post-Go-Live | Ancillary Service Trades with ERCOT | NRG Texas | TBD | TBD |  | 131 | 2008-05-01: 2008-05-15; 2008-07-22: 2008-06-10; 2008-08-21: 2008-06-19; 2008-09-24: 2008-09-24
132 | NPRR | Approved | Post-Baseline2 | Yes | Outage Clarification | ERCOT Staff | None | 0 |  | 132 | 2008-05-16 | 2008-05-22 | 2008-06-19 | 2008-07-17 | 2008-07-17 | 2008-08-07 | 2008-08-19
133 | NPRR | Approved | Post-Baseline2 | Yes | Addition of PSSE Format | ERCOT Staff | None | 0 |  | 133 | 2008-05-16 | 2008-05-22 | 2008-06-19 | 2008-07-17 | 2008-07-17 | 2008-08-07 | 2008-08-19
134 | NPRR | Approved | Post-Baseline2 | Yes | Section 7 Cleanup | TPTF | None | $500k-$1M |  | 134 | 2008-06-05 | 2008-06-05 | 2008-07-17 | 2008-10-22 | 2008-10-23 | 2008-11-06 | 2008-11-17
135 | NPRR | PRS tabled until companion PRR is submitted | Post-Baseline2 | TBD | Deletion of UFE Analysis Zone Language | ERCOT Staff | TBD | TBD |  | 135 | 2008-05-01: 2008-06-20; 2008-08-21: 2008-12-18
136 | NPRR | Approved | Post-Baseline2 | Yes | Interim Solution for 15-Minute Settlement of Advanced Meters | AEP | None | 0 |  | 136 | 2008-06-20 | 2008-09-10 | 2008-09-24 | 2008-10-23 | 2008-10-23 | 2008-11-06 | 2008-11-17
137 | NPRR | Withdrawn | Post-Baseline2 | N/A | Synchronization and Update of Section 21 | ERCOT Staff | N/A | N/A |  | 137 | 2008-05-01: 2008-06-24
138 | NPRR | Approved | Post-Baseline2 | Yes | Credit Monitoring and Management Reports | Credit Working Group | None | 0 |  | 138 | 2008-07-11 | 2008-08-12 | 2008-08-21 | 2008-10-13 | 2008-10-23 | 2008-11-06 | 2008-11-17
139 | NPRR | Approved | Post-Baseline2 | Yes | Available Credit Limit, Estimated Aggregate Liability, Future Credit Exposure Calculation Updates | Credit Working Group | None | $50k-$100k |  | 139 | 2008-07-11 | 2008-09-02 | 2008-09-24 | 2008-10-22 | 2008-10-23 | 2008-11-06 | 2008-11-17
140 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | Revision to CRR Obligation Margin Adder | J. Aron | None | 0 |  | 140 | 2008-07-14 | 2008-09-23 | 2008-11-20 | 2008-12-08 | 2008-12-18
141 | NPRR | PRS tabled pending PUCT decision (Docket No. 35994) | Post-Baseline2 | Yes | TDSP Energy Storage for Reliability | AEP | TBD | TBD |  | 141 | 2008-07-11: 2008-07-23; 2008-09-02: 2008-08-12
142 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | EECP Media Appeal Change | OWG | None | 0 |  | 142 | 2008-07-22 | 2008-08-26 | 2008-09-24 | 2008-10-13 | 2008-11-20 | 2008-12-04
143 | NPRR | Approved | Post-Baseline2 | Yes | Section 9.9.1, Invoice Recipient Payment to ERCOT for the CRR Auction, Clean-up | ERCOT Staff | None | 0 |  | 143 | 2008-07-25 | 2008-09-08 | 2008-09-24 | 2008-10-13 | 2008-10-23 | 2008-11-06 | 2008-11-17
144 | NPRR | Approved | Post-Baseline2 | Yes | Five RUC Deployments Needed Before Requiring Verifiable Costs (VCWG) | VCWG | None | 0 |  | 144 | 2008-07-25 | 2008-08-12 | 2008-08-21 | 2008-09-22 | 2008-09-24 | 2008-10-02 | 2008-10-21
145 | NPRR | Approved | Post-Baseline2 | Yes | PPAs as Resource-Specific Verifiable Costs (VCWG) | VCWG | None | 0 |  | 145 | 2008-07-25 | 2008-10-12 | 2008-09-24 | 2008-10-23 | 2008-10-23 | 2008-11-06 | 2008-11-17
146 | NPRR | Referred back to TPTF for review of comments | Post-Baseline2 | Yes | ICCP Telemetry Information Submittals | AEP | TBD | TBD |  | 146 | 2008-07-25: 2008-07-31; 2008-08-12: 2008-09-08; 2008-08-21: 2008-09-24
147 | NPRR | Remanded to WMS by PRS | Post-Baseline2 | TBD | DAM Short Pay Changes | WMS | TBD | TBD |  | 147 | 2008-07-25: 2008-08-13
148 | NPRR | Approved | Post-Baseline2 | Yes | Treatment of Financial Information as Confidential | J. Aron | None | 0 |  | 148 | 2008-08-18 | 2008-09-10 | 2008-09-24 | 2008-10-13 | 2008-10-23 | 2008-11-06 | 2008-11-17
149 | NPRR | Remanded to NPRSA by PRS | Post-Baseline2 | TBD | Change the Name of Emergency Electric Curtailment Plan (EECP) to Energy Emergency Alert (EEA) | ERCOT Staff | TBD | TBD |  | 149 | 2008-08-18: 2008-08-22; 2008-09-24: 2008-12-18
150 | NPRR | Approved | Post-Baseline2 | Yes | Responsive Reserve Service Offer Floor | DSWG | None | 0 |  | 150 | 2008-08-28 | 2008-09-10 | 2008-09-24 | 2008-10-23 | 2008-10-23 | 2008-11-06 | 2008-11-17
151 | NPRR | Referred back to TPTF for review of comments | Post-Baseline2 | Yes | Clarify Definition of a Generator Output Breaker in the Outage Scheduler | Center Point | TBD | TBD |  | 151 | 2008-08-18: 2008-09-08
152 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | References to Section 22 Attachments | ERCOT Staff | None | 0 | Light Green = Board approved | 152 | 2008-09-10 | 2008-09-23 | 2008-10-23 | 2008-10-23 | 2008-11-20 | 2008-12-04
153 | NPRR | PRS tabled due to "Approved Post-Go-Live" status | Post-Baseline2 | Approved Post-Go-Live | Generation Resource Fixed Quantity Block Offer | TPTF | TBD | TBD | Yellow = Ready for TAC and/or Board approval | 153 | 2008-08-18: 2008-09-12; 2008-09-10: 2008-09-09
154 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | Corrections of Entities Able to Bid for Point-To-Point Obligations in the Day-Ahead Market | TPTF | None | $100k-$250k | Bright Green = Tabled at TAC waiting on Nodal Go-Live date | 154 | 2008-09-15 | 2008-09-15 | 2008-10-23 | 2008-11-20 | 2008-11-20 | 2008-12-04
155 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | Clarification of Authorized Representative | ERCOT Staff | None | 0 | Tan = Tabled at PRS | 155 | 2008-09-19 |  | 2008-10-23 | 2008-11-12 | 2008-11-20 | 2008-12-04
156 | NPRR | PRS tabled due to "Approved Post-Go-Live" status | Post-Baseline2 | Approved Post-Go-Live | Transparency for PSS and Full Interconnection Studies | PSEG Texas | TBD | TBD | Orange = Reduction in scope | 156 | 2008-08-18: 2008-09-19; 2008-09-10: 2008-10-12
157 | NPRR | TPTF tabled until PRR780 is approved by the Board | Post-Baseline2 | TBD | Extending Black Start Service Bid Timeline | ROS | TBD | TBD | Gray = post-implementation cost savings for ERCOT | 157 | 2008-08-18: 2008-09-23
158 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | EILS Self-Provision Formula Correction and Clarifications | ERCOT Staff | TBD | TBD | Withdrawn or rejected | 158 | 2008-08-18: 2008-09-23
159 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | Resource Category Startup Offer Generic Cap for Wind Resources | VCWG | None | 0 | No shading = Pending at TPTF, PRS, or other subcommittee | 159 | 2008-10-03 | 2008-10-12 | 2008-10-23 | 2008-11-04 | 2008-11-20 | 2008-12-04
160 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | Elimination of the Non-ERCOT LSE Fee | AEP | None | 0 |  | 160 | 2008-10-08 | 2008-11-10 | 2008-11-20 | 2008-12-08 | 2008-12-18
161 | NPRR | PRS tabled until December meeting | Post-Baseline2 | TBD | Clarification of Establishing Decision-Making Authority of Managed Capacity | ERCOT Staff | TBD | TBD |  | 161 | 2008-10-03: 2008-10-16; 2008-10-23: 2008-12-18
162 | NPRR | Ready for Board consideration in January | Post-Baseline2 | Yes | Change the Sign Convention of Net Real Power Consumption, LPC and MPC of Load Resources | ERCOT Staff | None | 0 |  | 162 | 2008-11-06 | 2008-11-10 | 2008-11-20 | 2008-11-20 | 2008-11-20 | 2008-12-04
163 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Removal of Late Fee Language | ERCOT Staff | None | 0 |  | 163 | 2008-10-03: 2008-11-11; 2008-11-04: 2008-11-12
164 | NPRR | PRS Pending Completion of Impact Analysis | Post-Baseline2 | Yes | Resubmitting Ancillary Service Offers in SASM | TPTF | Y | $100k-$250k + $6M-$8M |  | 164 | 2008-11-11 | 2008-11-11 | 2008-11-20 | 2008-12-18
165 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Synchronizing Section 1 with PRR697 | ERCOT Staff | None | 0 |  | 165 | 2008-10-03: 2008-11-18; 2008-11-04: 2008-11-21
166 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Timing for Required Black Start Unit Load Carrying Test | ERCOT Staff | None | 0 |  | 166 | 2008-10-03: 2008-11-20; 2008-11-04: 2008-11-20
167 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Options for Filing Verifiable Costs – QSEs or Resources | VCWG | None | 0 |  | 167 | 2008-10-03: 2008-11-24; 2008-11-04: 2008-12-08
168 | NPRR | TPTF Pending Language | Post-Baseline2 | TBD | Verifiable Costs General Corrections | VCWG | None | 0 |  | 168 | 2008-10-03: 2008-11-24; 2008-11-04: 2008-12-08
169 | NPRR | Remanded to PRS by TAC | Post-Baseline2 | Yes | Clarify the Calculation and Posting of LMPs for the Load Zone and LMPs for each Hub | TPTF | TBD | TBD |  | 169 | 2008-10-03: 2008-12-15; 2008-10-12: 2008-12-15; 2008-10-23: 2008-12-18