## Slide 1: Nodal COMS Update Commercial Operations Subcommittee January 13, 2009 Clay Katskee ERCOT - Market Operations Division Projects Organization

## Slide 2: Agenda
http://nodal.ercot.com <number>
COMS Remaining Software Release Schedule
Disputes API Discussion
Questions

## Slide 3: COMS Project: S&B and Data Aggregation
http://nodal.ercot.com <number>
S&B and Data Aggregation
  Development
      Lodestar Outstanding code (to date): S&B/Data Aggregation source reports (not extracts), Memory workaround, additional error handling and performance tuning
      CSI Outstanding code (to date): Long Day/Short Day, remaining BDs, MMS4P7 and MMS5 refactoring
  Testing
    Continue testing CSI 5.4 and 6.1 with CMM and MMS
  Major issues
    iTEST refresh scheduled for March - will add some time to the validation of CSI 7.0. Continue to work towards synchronized data sets required for end to end testing.

## Slide 4: COMS Project: Registration and Disputes
http://nodal.ercot.com <number>
Registration and Disputes
  Development In Progress:
    Registration Phase 5
      Siebel Refactoring Changes (MMS, MPIM, Dispute API and changes necessary for other Integration Interfaces).
    ERCOT internal Test Scheduled: 02/02/2009 – 04/17/2009
      No March Release due to iTEST Environment refresh
  Discussion
    Seeking COPS recommendation for timeline to conduct Dispute API Certification Testing.
    ERCOT recommendation to perform Q409
      Benefits: Allow time for ERCOT environment and data prep, MP set up (DC roles, etc.), time for MPs to ensure systems are ready.
      Thoughts???

## Slide 5: COMS Project: Credit Monitoring and Mgmt
http://nodal.ercot.com <number>
Development
  CMM 4.1 – scheduled
    Scheduled weekly drops from Vendor to ERCOT starting 01/16/2009 to maintain testing schedule
    Custom Management of the internal Interface and application (screens, workflows, parameter adjustments)
      Outstanding code to date – Internal reports (4.2) and upgrade to latest software version of ROME5.0 (4.3)
Testing
  CMM 3.1 FAT complete
    Core Functionality (Calculations, ACL, and ACL file posting)
  CMM3.1 Integration Testing Complete
    All interface testing with CMM will be completed with CSI 6.1 and 6.3 test cycles
Major Issues
  Vendor and ERCOT Turnover resulted in delays to finalization of detailed analysis and designs of the internal custom management functions of 4.1 – New Triplepoint Services Manager and Project Manager have been assigned lead this effort to completion.

## Slide 6: Schedule Information for COMS Remaining Software Releaases
Project | Release | Description | FAT Complete
REG | REG/DISP | COMS REG5/DISP3: Refactoring and Disputes API – iTEST Complete New date due to iTEST refresh scheduled for March | Apr 17 09 (new)
S/B | Data Agg Core | Lodestar Bundle for Data Aggregation Re-Write (Initial) | Dec 19 08
CSI | CSI5.5 | Commercial Systems Integration with S&B | Jan 23 08
CSI | CSI6.3 | Commercial Systems Integration with CMM | Jan 23 08
CSI | CSI7.0 | Commercial Systems Integration Refactoring - MMS 5 S&B/CMM Long Day-Short Day | Apr 17 09
http://nodal.ercot.com <number>

## Slide 7: Readiness Center Reports, DDLs, and XSDs
http://nodal.ercot.com <number>
Nodal Reports Readiness Center
  The Nodal Data Services Master List (NDSML) is updated each Friday with the latest information. It is located at: http://nodal.ercot.com/about/news/2008/0118a.html
  The site will be updated each Friday with the latest extract & report specifications and DDLs and XSDs. http://nodal.ercot.com/readiness/reports/index.html
  As noted at TPTF, currently in progress on updating the NDSML with all report status (Build, Test, Post, etc…)

## Slide 8: Readiness Center Standard & Mock Statements and Invoices
http://nodal.ercot.com <number>
Mock CARD Invoice and Extracts | http://nodal.ercot.com/readiness/reports/si/kd/card_invoices_and_extracts.zip
Mock CRR Balancing Account Invoice | http://nodal.ercot.com/readiness/reports/si/kd/mock_crr_balancing_account_invoice_examples.zip
Mock DAM Late Fee Invoices | http://nodal.ercot.com/readiness/reports/si/kd/dam_late_fee_invoices.zip
Draft Invoices | http://nodal.ercot.com/readiness/reports/si/kd/Draft%20Invoices.zip
Draft Settlement Statements | http://nodal.ercot.com/readiness/reports/si/kd/draft_settlement_statements.zip
Mock DAM Settlement Examples | http://nodal.ercot.com/readiness/reports/si/kd/mock_dam_settlement_examples.zip
Release 8 Settlement Postings (Statements, Invoices, Extracts, Reports, Notices) | (http://nodal.ercot.com/readiness/eds4/documents/index.html)

## Slide 9
http://nodal.ercot.com <number>
Questions?