## Slide 1: MARS Taskforce
RMS Update January 14, 2009
Notes: <number>

## Slide 2: MARS Taskforce January 12, 2009 Meeting
ERCOT Project Status Report for Planning Phase
  Business Requirements - 12/02/2008 completed
  ERCOT Enhanced LSE Design- 12/09/2008 completed
  Conceptual Design - 01/07/2009 completed
  Detail Designs - 02/09/2009 on schedule
  Test Plan - 02/16/2009 on schedule
  Planning Complete 02/20/2009 on schedule
ERCOT’s Project Implementation Plan will be provided to the MARS Taskforce at our meeting in March. This plan will provide critical dates, dependences, and tasks necessary to complete the Interim Settlement Solution Implementation.
Notes: <number>

## Slide 3: Design Question
CRs were requested by TDSPs to provide feedback on the security technology needed for files pulled from TDSP’s FTP sites, example Secure FTP, PGP, or NAESB or does it matter which protocol is utilized by the TDSP so long as that protocol meets industry standards?
  Recommendation from Taskforce CRs – Secure FTP.
Notes: <number>

## Slide 4: January 12, 2009 Meeting
TDSPs with PUCT “approved” AMS Project Plans provided taskforce with FTP site status reports for AMS Provisioned Meters
  Oncor and CenterPoint Energy on target to meet AMIT’s Business Requirement (BR-004) for the interim solution no later than Q3-2009
  No Issues or questions identified at this stage of design/development
Notes: <number>

## Slide 5: Testing Recommendation
The Taskforce discussed testing requirements for this project, do TDSPs require testing to be part of a scheduled flight?
  Taskforce Recommendation:
    Testing should include NAESB connectivity testing between TDSPs and ERCOT independent of a scheduled flight, this would allow the TDSP’s flexibility in testing files as programming is completed and prior to project implementation.
    The TDSPs may also submit sample files to ERCOT for validation prior to implementation.
Notes: <number>

## Slide 6: Next Steps for MARS
MARS RMGRR Sub-team will schedule a meeting in February to start drafting RMGRR language and processes for “Provisioned” AMS meters in the ERCOT Market
MARS Taskforce will schedule a meeting in March to review Sub-team recommendations for Retail Market Guide Revision Request
  Additional Agenda items for this meeting:
    ERCOT’s Project Status Report (Planning Phase Update)
    TDSP’s FTP Site Project Status Report (Update)
    Review ERCOT’s Implementation Plan
      Tasks
      Dependences
      Critical Dates
    Continue to complete and resolve action items by providing timely feedback
Notes: <number>

## Slide 7: Questions?
Notes: <number>