|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for December 2008 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 254 active generation interconnection requests totaling over 106,000 MW. This includes almost 52,000 MW of wind generation. - 93 MW of new wind generation began commercial operation in December, bringing the currently installed total of wind power capacity to 8,005 MW. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $766 Million - Transmission Projects approved in 2008 total $255 Million - All projects (in engineering, routing, licensing and construction) totals approximately $4.1 Billion - Transmission Projects energized in 2008 total about $453 Million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4	Potential Future Generation Interconnections	2

2.	Regional Planning Group Project Reviews	5

3.	Other Notable Activities	6

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

# No-Trees Wind  (07INR0005) in Ector County for 93 MW

## The total installed wind capacity is now 8,005 MW, of which 7,347 (92%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements

Lorraine Wind Park (09INR0047) in Mitchell County for 251 MW

Cobisa-Greenville Combined Cycle Plant (06INR0006) in Hunt County for 1,792 MW

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 254 active generation interconnection or change requests |  |  |  |  |
| As of December 31, 2008 | North | South | West | Total |
| Security Screening Study | 2 | 6 | 12 | 20 |
| SSS Completed | 4 | 15 | 29 | 48 |
| Full Interconnect Study | 35 | 35 | 80 | 150 |
| FIS Completed | 1 | 8 | 0 | 9 |
| Interconnect Agreement Completed | 7 | 8 | 9 | 24 |
| Capacity under Interconnection Agreements | 5,308 | 2,578 | 1,262 | 9,148 |
| Capacity for Grid, MW | 25,438 | 36,868 | 43,739 | 106,045 |
| Wind Capacity, MW | 2,047 | 10,135 | 39,464 | 51,646 |

| Fuel Type | Non-Public (MW) | Public (MW) | Grand Total (MW) |
| --- | --- | --- | --- |
| Gas-CC | 22,790 | 5,229 | 28,019 |
| Gas-CT | 1,353 | 505 | 1,858 |
| Nuclear | 3,200 | 9,186 | 12,386 |
| Coal | 5,375 | 4,131 | 9,506 |
| Wind | 44,603 | 7,043 | 51,646 |
| Solar | 955 | 0 | 955 |
| Biomass | 50 | 145 | 195 |
| Other | 1,480 | 0 | 1,480 |
| Grand Total | 79,806 | 26,239 | 106,045 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections (Public Projects) as of December 31, 2008 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | Gas-CC | 255 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Mar-09 | Wind | 200 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Mar-09 | Wind | 300 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | Gas-CT | 48 |  |
| 07INR0027 | S Houston Green Power Exp | IA | Galveston | South | Apr-09 | Gas-CC | 244 |  |
| 10INR0025 | Mont Belvieu | IA | Chambers | South | Apr-09 | Gas-CT | 0 | New IA |
| 07INR0028b | Goat Wind - phase 2 | IA | Sterling | West | Apr-09 | Wind | 70 |  |
| 08INR0012 | Papalote Creek Wind Farm | IA | San Patricio | South | May-09 | Wind | 180 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | Gas-CC | 539 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | Gas-CT | 178 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 327 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Dec-09 | Wind | 251 | New IA |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Jul-10 | Gas-CT | 94 | Date |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 | Date |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1792 | Date/MW/IA |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3200 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2700 |  |
|  |  |  |  |  |  |  | 26,239 |  |

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is in ERCOT Independent Review.

# Oncor submitted a project to install an additional 300 MVar of dynamic reactive at Renner station.  The estimated cost of this project is $ 35 M with an in-service of 2010.  This project is in ERCOT Independent Review.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review.

# Austin Energy submitted a project to establish a 138 kV circuit from Hicross to Slaughter Lane by building 2.2 miles of new transmission line to an un-energized 1.2 mile circuit segment.  This project will cost $5.774 M with an estimated completion date of October 2010.  This project is in the comment period.

# Oncor submitted a project to add a 138/69 kV autotransformer at Stanton East into the Spraberry to Big Spring 69 kV line and rebuild the 138 kV line from Stanton East to Big Spring Switch.  This project will cost $15 M with an estimated completion date no earlier than summer 2011.  This project is in study period.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in the comment period.

# Other Notable Activities

- All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT Regional Planning has completed work on the 2013 case to be used for reliability analysis and RPG analysis.  The purpose of this effort was to extend the 2007 Five-Year plan from 2012 to 2013.  The report of this study was written as an addendum to the 2007 Five-Year plan and has been posted on the ERCOT Planning and Operation Information website.

- ERCOT Regional Planning has begun work on the 2009 Five-Year Transmission Plan utilizing the latest SSWG base cases.  This work is in the conditioning phase where projects in the base cases requiring RPG review that have not undergone that review are removed.

- ERCOT TPIT report for 11/01/08 (4th Quarter) completed and posted on 11/26/08.

- Updates to the SSWG 2008 Data Set A, 2009 Data Set A, 2009 Data Set B cases were posted.