## Sheet1
TPTF date | # | Action Items | Disposition | Area | Status
2009-01-07 | 1 | Consider adding more time for running SE 7 X 24. FIT Testing needs to complete earlier and the transition to 7 X 24 operations needs to occur earlier for publishing LMPs | Revisiting as part of SCED/LFC schedule | FIT/Telemetry | Open
2009-01-07 | 2 | Add a milestone that represents 7 X 24 telemetry support | Define and link SCED/Telem Specs/Testing/Qual/Submits/MPreqts | FIT/Telemetry | Open
2009-01-07 | 3 | Add note in schedule that FIT testing is for telemetry only | Agree- change schedule to reflect current FITs do not include SCED submissions, and will add task when SCED will be required(issue 1) | FIT/Telemetry | Closed
2009-01-07 | 4 | There should be no start date for Verifiable costs- it should be a submit by date | Agree- change schedule to show VC as end dates for submission | VerifCost | Closed
2009-01-07 | 5 | Add the dates when the VC data would be uploaded into MMS system for EDS testing | Activity will be iterative updates, not a single milestone. EDS will work with settlements to agree on update process/timeline and come back to TPTF. | VerifCost | Open
2009-01-07 | 6 | Add task for ERCOT verification of MP qualification | Agree- add to schedule when dates determined | MP/submission | Open
2009-01-07 | 7 | Add milestones when all QSEs have to be ready | Agree- add to schedule when dates determined | MP/submission | Open
2009-01-07 | 8 | Add specifics of MMS and EIP versions tied to specific EDS activities and dates (will address after discussion with MMS & EIP re: investigation of moving up the releases of EIS v1.19 since this will involve what will be available when from ABB/MMS to EIP; joint effort between EIP/MMS/ABB) | Agree- add to schedule when dates determined | MP/submission | Open
2009-01-07 | 9 | Add milestone when ERCOT will re-publish MMS validation rules document | Agree- add to schedule when dates determined | MP/submission | Open
2009-01-07 | 10 | Add milestone when MPIM will be ready and for MPs to get ready | Agree- add to schedule when dates determined | MP/submission | Open
2009-01-07 | 11 | Suggestion to remove Planning Model go-live from Nodal schedule | TPTF action to determine if there is change in scope to remove this from NMMS - Confirmed ERCOT is working with SSWG | NMMS | TPTF
2009-01-07 | 12 | Change LFC duration of 48 hour test to 2 days | Agree- change schedule | LFC | Closed
2009-01-07 | 13 | Include tasks showing MMS, EIP etc ready for SCED submissions | Duplicate of #8 | MP/submission | Closed
2009-01-07 | 14 | Include MP tasks that show how they will be ready for open loop tests and LMPs | Define and link SCED/Telem Specs/Testing/Qual/Submits/MPreqts | SCED/RT/Telem | Open
2009-01-07 | 15 | Add linking from FIT testing to open loop tests | Define and link SCED/Telem Specs/Testing/Qual/Submits/MPreqts | SCED/RT/Telem | Open
2009-01-07 | 16 | Include tasks showing MMS, EIP etc ready for LMP publishing | Duplicate of #14 | SCED/RT/Telem | Closed
2009-01-07 | 17 | Include MP tasks that show how they will be ready for LMPs | Duplicate of #14 | SCED/RT/Telem | Closed
2009-01-07 | 18 | add linking from FIT testing to open loop tests to LMPs | Duplicate of #15 | SCED/RT/Telem | Closed
2009-01-07 | 19 | Add link showing that NMMS and CRR are working together | CRR- This CRR integration activity is part of IR4-TC3. For EDS/MPs, when CRR auction is conducted in Feb 2010, NMMS and CRR integration will be in place. Flag this activity in schedule. | CRR | Closed
2009-01-07 | 20 | Add task to show when test CRR network model gets posted and if posted does it get posted in PSS/E format also | CRR- This CRR model posting will be part of existing CRR testing activity timeline for Feb-April 2010. CRR model will be posted in PSS/E format. Ensure fits in 2010 CRR testing timeline (hanbook/schedule) | CRR | Open
2009-01-07 | 21 | Show the PCRR allocation window | CRR- The PCRR allocation activity will be part of existing CRR testing activitity timeline from Feb-Apr 2010. | CRR | Closed
2009-01-07 | 22 | Show when MPs can download CRR auction results and other posting requirements | CRR- This CRR posting is also included as part of planned CRR Reminder there are is no API for CRR | CRR | Closed
2009-01-07 | 23 | How does CRR ownership info get to the 1st DAM. Show task for running an auction or for mocking up the data | CRR- Ownership in DAM in EDS Option 1- ERCOT stubs in first few weeks of CRR ownership in 2010 Option 2- Engage market in 2009 to run additional mock auction - TPTF comment to use data in testing systems, no additional CRR Auction needed prior to DAM. | CRR | Open
2009-01-07 | 24 | Add task for credit limit verification | Agree- change "ACL published task" to "Calculated ACL publishing begins for EDS" | CRR | Closed
2009-01-07 | 25 | Consider adding task for Outage Scheduler API training | Agree- add new activity to provide another API workshop in 2009, date and task to be added when Issue #1/APIs implemented for testing resolved | OS | Open
2009-01-07 | 26 | Consider OS go-live earlier than TNMID | Internal discussion of option/risks | OS | Open
2009-01-07 | 27 | Add task for OE testing | Agree- will make visible in schedule to market | SCED/RT/Telem | Closed
2009-01-07 | 28 | add task for testing of TCM and other EMS functions | Looking to add detail to schedule of what/when EMS functionality is part of SCED | SCED/RT/Telem | Open
2009-01-07 | 29 | add milestone to show when COP must be updated continuously | Define and link SCED/Telem Specs/Testing/Qual/Submits/MPreqts | SCED/RT/Telem | Open
2009-01-07 | 30 | Consider if/when can MPs see sample extracts | ERCOT is considering collective view of comments received and will prepare a response | Report/Extract | Open
2009-01-07 | 31 | Why is there a month lag after the 1st DAM and the 1st settlement statement | Discussion of S&B timing and deliverables | S&B | Open
2009-01-07 | 32 | Consider providing MPs sample shadow settlement extracts earlier than the current date | ERCOT is considering collective view of comments received and will prepare a response | Report/Extract | Open
2009-01-07 | 33 | Consider adding task for MPs to try and break the system | Agree- add activity to EDS4-R9.3 | SCED/RT/Telem | Closed
2009-01-07 | 34 | Add task for MP performance test | Agree- add activity to EDS4-R9.3 | SCED/RT/Telem | Closed
2009-01-07 | 35 | What is the MP engagement level between full market timeline test and the 168 hour test | Detail to be agreed to with ERCOT/MPs in developing handbook for 2010- to be worked with TPTF | EDS | Open
2009-01-07 | 36 | Add milestone to show that PUCT and IMM bless the data Clarification. Request for a milestone of the IMM and PUCT Staff confirming their validation of ERCOT nodal data. In other words, there are many data extract requirements by both parties, and much of this we will not seen until several months after the trade day. We want to see milestones reflecting their completion of their data validation. Although there may be no MP view of the data, there should be IMM/PUCT signoff/approval/confirmation that they are comfortable with their test results. | Schedule being developed with IMM and these milestones have not yet been defined. | IMM | Open
2009-01-07 | 37 | Consider adding tasks for scenario testing | Agree- add activity to EDS4-R9.3 | SCED/RT/Telem | Closed
2009-01-07 | 38 | When are business processes going to be provided | Scheduled review for TPTF 1/13/09 of Level 1& 2 with timeline. Timeline to be discussed. | BusProc | Open
Action items 1/7/09 meeting
2009-01-07 | 39 | MOTE "value"; migration/progression of EIP EIS lifecycle i.e., v1.17 to v1.19 | Considering market feedback on MOTE and determining feasibility for market submissions and other market facing activities. | MP/submission | Closed
2009-01-07 | 40 | Requirements for MOTE | Considering market feedback on MOTE and determining feasibility for market submissions and other market facing activities. | MP/submission | Closed
2009-01-07 | 41 | Need validation activities for model | Activities have been made visible in the market view of the schedule, and are further detailed in the SEM go-live document. | NMMS | Closed
2009-01-07 | 42 | Data availability on MIS and in other environments | ERCOT is considering collective view of comments received and will prepare a response | Report/Extract | Open
2009-01-07 | 43 | Consider VC applicability to zonal market | n/a | NA | Closed
2009-01-07 | 44 | Parking lot item- nodal reports/formats/extracts | ERCOT is considering collective view of comments received and will prepare a response | Report/Extract | Open
2009-01-07 | 45 | Additional Posting requirements for CRR (more specifics) | Duplicate of #20 | CRR | Closed
2009-01-07 | 46 | Dual entry of outages/Go-Live data | Dual entry scheduled for up to 45-days in Go-Live doc | OS | Closed
2009-01-07 | 47 | ERCOT’s telemetry validation process | TPTF meeting for 1/26/09 from EDS | FIT/Telemetry | Open
2009-01-07 | 48 | FIT Reports need to be “restarted” and need to include Action Item accountability | TPTF meeting for 1/26/09 from EDS | FIT/Telemetry | Open
2009-01-07 | 49 | Test Scenario w/ no Verifiable Cost data | Agree- add activity to EDS4-R9.3 for scenario consideration | VerifCost | Closed
2009-01-07 | 50 | Update SEM Go-Live Document w/ dates | SEM Go-Live does not contain any dates by design. Detailed dates are to be maintained in the market view of the integrated program schedule. | EDS | Closed
2009-01-07 | 51 | Update compliance matrix | TPTF/Mkt Rules when the nodal schedule when updated/approved | TPTF | Open
2009-01-07 | 52 | Submittal validation rules documentation provided to MPs (add to schedule) | Duplicate of #9 | MP/submission | Closed
2009-01-07 | 53 | Investigate moving up the releases of EIS v1.19 (working w/MMS team/EIP team/ABB | Duplicate of #8 | MP/submission | Closed
2009-01-07 | 54 | Investigate moving MMS 5 into external-facing environment in 3rd Quarter 2009 | Duplicate of #8 | MP/submission | Closed
2009-01-07 | 55 | Investigate alternative go-live date for Outage Scheduler | Duplicate of #26 | OS | Closed
2009-01-07 | 56 | Review EDS Handbooks and extract all dates and include in Market Participant view of schedule | In progress | EDS | Open
2009-01-07 | 57 | Consider providing sample of shadow settlement extract so MP developers will have something to shoot at well ahead of time | Duplicate of #30 | Report/Extract | Closed
2009-01-07 | 58 | Include MP and ERCOT training timetable into the schedule | Program to follow-up to align training with new schedule | Training | Open
2008-12-15 | 1 | Update the preliminary nodal program schedule to provide a more detailed Market Participant view of Early Delivery System (EDS) activities, including: a- Market Participant activities leading up to milestone dates b- A breakdown of milestones to indicate which ones affect QSEs with Resources and which ones affect QSEs without Resources c- A specific milestone for the Enterprise Integration Project (EIP) External Interfaces Specification, including the lead time that will be provided between the publication of the final specification and the initiation of submissions testing | Work in progress to work through comments from Dec 12 TPTF and Jan 7 workshop. | PMO | Open
2008-12-15 | 2 | Identify the change process to be followed for the EIP External Interfaces Specification (MPs requested four to six months of lead time to provide feedback and to make upgrades whenever interface specifications are updated) | EIP release dates are in MP view of schedule | MP/submission | Closed
2008-12-15 | 3 | Identify the change process to be followed for the Nodal Data Services Master List (NDSML) | ERCOT is considering collective view of comments received and will prepare a response | Report/Extract | Open
2008-12-15 | 4 | Identify project tasks on the critical/near-critical path that have less than ten days of schedule float | This view can be requested, please email EDS3@ercot.com. | PMO | Closed
2008-12-15 | 5 | Provide assurance that no new nodal functionality will be implemented going forward without prior TPTF review and approval | Part of NPRR tracking discussion in item #6 | PMO | Closed
2008-12-15 | 6 | Maintain a posting of Mr. Anderson's NPRR-tracking spreadsheet on the nodal website and link it to nodal project pages | Scheduled for TPTF discussion 1/12/09 | PMO | Closed
2008-12-15 | 7 | Confirm the status of “grey boxed” change items (i.e., items to be approved post-go-live or to be prioritized on deferred projects listing) | No current grey-boxing, TPTF would address if needed- not part of schedule discussion | PMO | Closed
2008-12-15 | 8 | Discuss the updated change-process flowchart with TPTF (targeted for January 2009) | Scheduled for TPTF discussion 1/12/09 | PMO | Closed
2008-12-15 | 9 | Confirm that recent updates in Business Requirements documentation covers the reporting requirements per PUC Subst. R. 25.505(d), Projected Assessment of System Adequacy (PASA), and (f), Publication of Resource and Load Information in ERCOT Markets; also confirm how these reports will be provided | Business requirements review with BettyL/TPTF | PMO | Open
2008-12-15 | 10 | Align the effective dates identified in the Protocol Transition Plan with the new milestone dates identified in new integrated nodal program schedule | TPTF/Mkt Rules when the nodal schedule when updated/approved | TPTF | Open
2008-12-15 | 11 | Clarify schedule details related to Single-Entry Model (SEM), including: a- Update the previously approved SEM Go-Live Procedure document to incorporate the new milestone dates identified in the new integrated nodal program schedule b- Clarify the NOMCR process to indicate how ERCOT will translate QSE-submitted service requests into NOMCRs c- Publish the NMMS validation rules (currently targeted in March 2009, with potential draft in late January 2009) c- Publish the Modeling Guidelines (currently targeted in May 2009) d- Set up a WebEx workshop to discuss Modeling Guidelines once they become available | Activities have been made visible in the market view of the schedule, and are further detailed in the SEM go-live document. | NMMS | Closed
2008-12-15 | 12 | Adjust nodal critical path to incorporate verification/validation activities for Transmission Service Providers (TSPs) | Activities have been made visible in the market view of the schedule, and are further detailed in the SEM go-live document. | NMMS | Closed
2008-12-15 | 12a | Work with the Network Data Support Working Group (NDSWG) to flesh out details for TSP activities, including training and entrance criteria | NDSWG will be engaged in Feb 2009 | NMMS | Open
2008-12-15 | 13 | Review MMS Detailed User Interface (UI) Design with TPTF a- Review any comments received during the TPTF Review ending December 31, 2008 b- Review any remaining wish-list items from the UI Subgroup to discuss whether those items are in scope or out of scope for the MMS UI | Scheduled for TPTF discussion 1/26/09 | PMO | Closed
2008-12-15 | 14 | Schedule January 2009 TPTF discussion of feasibility study for SCR752, Allow QSEs to Enter Outages for All Assets | TPTF discussion Jan 12, 2009 | PMO | Closed
2008-12-15 | 15 | Incorporate additional activities into the schedule to indicate how ERCOT will engage Market Participants for each EDS testing activity in 2009 and 2010 | MP view created and discussed schedule at Jan 7 meeting | PMO | Open
2008-12-15 | 16 | Schedule a one-day workshop on January 7, 2009, to review these additional activities with TPTF and to determine whether they are valuable, whether enough time has been allotted to them, and whether the current nodal scorecard is the best way to measure them | Conducted Jan 7 meeting. Metrics were not addressed- but plan to re-align to approved schedule. | PMO | Closed
Additional Comments received on 1/14/09
2009-01-14 | 1 | The Transmission Asset Registration activities have already been performed; MPs should not be required to re-verify transmission asset information ERCOT should establish a date at which the submitted Transmission Asset Registration Information is considered final |  | RARF | New
2009-01-14 | 2 | Categorize activities by Market Participant type | Duplicate | EDS | New
2009-01-14 | 3 | When can MPs test the EIP market queries in an early market facing environment. MPs should have atleast one dataset that they can query through webservices |  | EDS | New
2009-01-14 | 4 | There needs to be a milestone that indicates SE and telemetry criteria have been attained before LMPs are published. |  | EDS | New
2009-01-14 | 5 | We need a milestone that indicates when the draft Planning Model Go-Live procedure will be published for MP comments |  | NMMS | New
2009-01-14 | 6 | There needs to be a task that shows how TSPs will be engaged in Planning Model Go-Live process |  | NMMS | New
2009-01-14 | 7 | Show milestone in schedule that shows when the NMMS tool can produce a baseline Annual Planning Model from the NMMS system to meet planning fidelity |  | NMMS | New
2009-01-14 | 8 | Add milestone that shows when we'll evaluate the need for implementing fall back plan for Annual Planning Models |  | NMMS | New
2009-01-14 | 9 | Add milestone in schedule that shows when EDS / production quality Settlement Statements and extracts will be generated according to Nodal Protocol timelines |  | S&B | New
2009-01-14 | 10 | Add milestone that shows when system generated, sample settlement statements and extracts will be published - would not be QSE specific data |  | S&B | New
2009-01-14 | 11 | Add TSP API training for Outage Scheduler in the schedule |  | EDS | New
LCRA comments received on 1/14/2009 - tasks to be added into the schedule
2009-01-14 | 1 | Publish integrated CRR Auction, Balancing Account, CARD and Late Fee Invoices |  | EDS | New
2009-01-14 | 2 | (test CRR Auction invoices should be based on output from test CRR Auction) |  | EDS | New
2009-01-14 | 3 | Publish CRR Balancing Account Extract, CARD Extract and Late Fee Extract |  | EDS | New
2009-01-14 | 4 | EDS 4 Release 8.2 (DAM Extracts, Statements & Invoices) |  | EDS | New
2009-01-14 | 5 | Publish DAM Settlement Statements & Invoices based on Release 9 DAM execution |  | EDS | New
2009-01-14 | 6 | Publish DAM Settlement and Resettlement Statement |  | EDS | New
2009-01-14 | 7 | Publish DAM Invoices based on Release 9 DAM |  | EDS | New
2009-01-14 | 8 | Publish DAM Settlement, Resettlement and Late Fee Invoice |  | EDS | New
2009-01-14 | 9 | Publish DAM Settlements extracts based on Release 9 DAM execution |  | EDS | New
2009-01-14 | 10 | Publish DAM Consolidated Data Extract (CODE), MODE, Public Reference and Settlement Input Data Extracts |  | EDS | New
2009-01-14 | 11 | EDS 4 Release 8.3 (RT Extracts, Statements & Invoices) |  | EDS | New
2009-01-14 | 12 | Publish RT Settlement Statements & Invoices based on Release 9.3 execution |  | EDS | New
2009-01-14 | 13 | Publish RTM Initial, Final, True-up and Resettlement Statement |  | EDS | New
2009-01-14 | 14 | Publish RT Invoices based on Release 9.3 |  | EDS | New
2009-01-14 | 15 | Publish RT Settlements extracts based on Release 9.3 RT execution |  | EDS | New
2009-01-14 | 16 | Publish RTM CODE, MODE, Public Reference and Settlement Input Data Extracts |  | EDS | New

## Sheet2
ID# | Integrated Project Schedule EDS 4 (as of 01/06/09)
184 | Publish integrated CRR Auction, Balancing Account, CARD and Late Fee Invoices
(test CRR Auction invoices should be based on output from test CRR Auction)
Publish CRR Balancing Account Extract, CARD Extract and Late Fee Extract
187 | EDS 4 Release 8.2 (DAM Extracts, Statements & Invoices)
188 | Publish DAM Settlement Statements & Invoices based on Release 9 DAM execution
Publish DAM Settlement and Resettlement Statement
190 | Publish DAM Invoices based on Release 9 DAM
Publish DAM Settlement, Resettlement and Late Fee Invoice
192 | Publish DAM Settlements extracts based on Release 9 DAM execution
Publish DAM CODE, MODE, Public Reference and Settlement Input Data Extracts
193 | EDS 4 Release 8.3 (RT Extracts, Statements & Invoices)
194 | Publish RT Settlement Statements & Invoices based on Release 9.3 execution
Publish RTM Initial, Final, True-up and Resettlement Statement
196 | Publish RT Invoices based on Release 9.3
198 | Publish RT Settlements extracts based on Release 9.3 RT execution
Publish RTM CODE, MODE, Public Reference and Settlement Input Data Extracts