## 2008
No. | PWG 2008 Goals | Target Date | % Complete
18 | Distributive Generation load profiling implementation (PRR756 and LPGRR030) | 2008-05-25 | 100%
1 | Implementation of LRS sample selection round two. | 2008-07-01 | 100%
4 | Review 2007 UFE Analysis (final complete, true-up pending) | 2008-07-30 | 100%
10 | Review IDR installation procedure language to ensure compliance (Pending AMR Rule) | 2008-08-25 | 100% | CHG
18b | Distributive Generation load profiling implementation issues | 2008-08-26 | 100% | CHG
2 | 2008 Annual Validation. | 2008-11-07 | 100% | CHG
17 | Advanced Metering Implementation LPG changes if needed | 2008-12-01 | 100% | CHG
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2008-12-07 | 10% | CHG
5 | Examine ways to accommodate extreme events in Settlement process. | 2008-12-27 | 90% | CHG
14 | Review analysis of DLC demonstration programs (Pilot) | 2008-12-27 | 0% | CHG
16 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2008-12-27 | 0% | CHG
3 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16) | 2008-12-31 | 15%
6 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2008-12-31 | 0%
8 | Review if having more weather stations adds accuracy | 2008-12-31 | 0%
9 | Review if the weighting of weather stations is appropriate | 2008-12-31 | 0%
11 | Review LPG language on list based profiles and universality | 2008-12-31 | 0%
12 | Demand Response Implementation | 2008-12-31 | 0% |  | CHG
13 | Investigate ways to improve Business Profile ID assignments | 2008-12-31 | 0% |  | New
15 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2008-12-31 | 0% |  | CHG
*** | Not completed in 2008 due to market status |  |  |  | CHG
*** | Working or on the next Agenda
*** | Parked items to large projects or waiting on Advanced Metering
*** | Shall be on the November Agenda