## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
January 22, 2009

## Slide 2: PMO Update - Agenda
  2008 Project Spending and Delivery Update
  2009 Project Reforecast Update
  Recent Project Implementations
    December 2008

## Slide 3: 2008 Project Spending Update – 1/15/2009
CART | Initial Budget | Current Budget | Spending Forecast
CO | $ 8,450,000 | $ 5,676,754 | $ 5,288,992
IO | $ 6,400,000 | $ 8,031,000 | $ 7,987,798
MO | $ 1,200,000 | $ 1,394,906 | $ 1,269,779
RO | $ 6,100,000 | $ 3,635,094 | $ 2,584,003
SO | $ 50,000 | $ 1,071,795 | $ 863,221
Nodal / Zonal Interdependent | $ 5,314,000 | $ 6,715,129 | $ 6,715,129
Released but Not Reallocated | $ 0 | $ 989,322 | $ 0
Total | $ 27,514,000 | $ 27,514,000 | $ 24,708,922
CO – Met Center * | $ 0 | $ 6,232,880 | $ 1,208,617
* Met Center project is not funded by initial project budget allocation
Arrows indicate trend since last report (December 2008)

## Slide 4: 2008 Project Deliveries (“Go-Live”) – 1/15/2009
CART | Projected Project Delivery Count 1/1/2008 | Actual Project Delivery Count 12/31/2008 | Variance
CO | 16 | 12 | (4)
IO | 16 | 12 | (4)
MO / RO | 12 | 10 | (2)
SO | 4 | 4 | -
Total | 48 | 38 | (10)

## Slide 5: 2009 Project Reforecast – Recent Changes
2009 project budget has increased from $12.7M to $17.75M
Primary driver:
  ERCOT determined there is a critical need to expand the Taylor data center in order to properly maintain current operations
  This is in addition to the data center work planned as part of the Met Center Disposition project
  $6.75M project added to the CO list to expand the current Taylor data center into the remaining raised floor space of TCC1
ERCOT-wide effort to fund the data center expansion project and maintain the current 41.71 cent System Administration Fee
  ERCOT Strategic Review Team (SRT) recommended various reductions to the project budget to assist in the effort
  ERCOT executives elected to take several measures impacting projects
    Deferred 2 CO projects (TCC1 Reconfiguration and Blue Bldg Evacuation Route)
    Reduced the project contingency on all projects that are not yet started from 35% to 25%
      PUCT and market projects were exempt from the contingency reduction

## Slide 6: 2009 Project Reforecast – Schedule
2009 Project Prioritization Schedule
  Q1 2008
    2009 Initiative Lists drafted, revised and approved
  September 2008
    CARTs revise 2009 Initiative Lists to prepare for market review
  October 2008
    Initial review by market subcommittees
      Approved by COPS and RMS
  November 2008
    Additional updates by ROS, WMS (November 13 / November 19)
    PRS approved all project lists (November 20)
  January 2009
    Review by TAC (January 8)
      ** Endorsed ** with concern expressed about data center outsourcing considerations
    Available for F&A and Board (January 20)
      ** Approved ** as part of 2009 ERCOT budget – Sys Admin Fee remains at 41.71 cents

## Slide 7: 2009 Project Reforecast – Activity Since PRS Approval
CO (Corporate Operations)
  Addition of Data Center Expansion to meet short term data center needs
  Deferral of Taylor TCC1 Office Reconfiguration and Blue Building Evacuation Route
  Reduced Met Center Disposition by $400k
  Reduce contingency for projects not yet started
IO (IT Operations)
  Reduce contingency for projects not yet started
MO (Market Operations)
  Reduce contingency for projects not yet started (excludes market projects)
RO (Retail Operations)
  Reduce contingency for projects not yet started (excludes market projects)
SO (System Operations)
  Reduce contingency for projects not yet started (excludes market projects)
  Continuing effort to update Impact Analyses and CBAs for:
    PRR601, PRR675, PRR409, SCR720, SCR728
    Expect to have the updated IAs and CBAs available for PRS on 1/22
PRS reviewed and approved the combined project lists on 11/20/2008
  Project budget estimate at time of PRS approval = $12.7M
  New project budget estimate = $18.15M
    No impacts to PUCT and market projects

## Slide 8: 2009 Project Reforecast – Summary by CART
Met Center | $ 20,400,000 | $ 20,000,000 | ($ 400,000)
Program Area | 2009 Budget Prior Revision | 2009 Budget Updated Revision | Change
CO | $ 1,775,000 | $ 7,895,000 | $ 6,120,000
IO | $ 5,525,000 | $ 4,995,000 | ($ 530,000)
MO | $ 550,000 | $ 520,000 | ($ 30,000)
RO | $ 3,450,000 | $ 3,390,000 | ($ 60,000)
SO | $ 1,400,000 | $ 1,350,000 | ($ 50,000)
Total | $ 12,700,000 | $ 18,150,000 | $ 5,450,000

## Slide 9: PMO Update - YTD 2008 Project Implementations
January 2008
  IO PR-70050_01 EIS ETL Tool Implementation
February 2008
  CO PR-70044_01 MET Center Facility Analysis
  RO PR-70005_01 MO SAS70 Procedures Optimization
  IO PR-70012_01 Cyber Security Project #14
  IO PR-70037_01 OC-3 Microwave Replacement
  SO PR-70035_01 2007 REC Program Modifications
March 2008
  IO PR-60055_01 Enterprise Service Management
  IO PR-60013_01 Enhanced Digital Certificate Program
  MO PR-70038_01 ERCOT.com Infrastructure Enhancement
        (Collage Infrastructure Redesign)
  CO PR-70013_01 Corporate Document Management
  CO PR-70041_01 Taylor Control Room Display System Replacement
April 2008
  None

## Slide 10: PMO Update - YTD 2008 Project Implementations (cont’d)
May 2008
  MO PR-70048_01 MV90xi System Upgrade
  CO PR-70053_01 Video Teleconferencing
  IO PR-70055_01 Additional Production SAN Capacity
June 2008
  MO PR-60077_01 ERCOT.com Registered Area
  IO PR-70030_01 Tellabs DCCS System Replacement
  IO PR-80022_01 Additional SAN Capacity for Projects
July 2008
  RO PR-60008_01 Terms and Conditions & Performance Measures
  CO PR-70023_01 CyberSecurity Project #2
  CO PR-70047_01 Corporate Application Environment True-Up
  CO PR-80010_01 Ruby Standardization
  CO PR-60073_01 eRecruiting

## Slide 11: PMO Update - YTD 2008 Project Implementations (cont’d)
August 2008
  RO PR-60015_01 Siebel Data Model Assessment
  CO PR-80035_01 Intranet Assessment HR & Communications
  IO PR-70054_01 Blade Refresh
September 2008
  MO PR-40066_04 Lodestar 4.7 Upgrade
  SO PR-50070_01 Unit Testing Automation and Electronic Submittal – Phase 1
October 2008
  IO PR-80023_01 Firewall Replacement
  CO PR-60094_01 Physical Access Control Upgrade
  CO PR-50015_03 Lawson Procurement Process Flow
  CO PR-60020_02 Lawson 9x Upgrade

## Slide 12: PMO Update - YTD 2008 Project Implementations (cont’d)
November 2008
  SO PR-80037_01 Starter Phasor Monitoring System (SPMS)
  RO PR-70006_02 Website Enhancements for ERCOT Outage Notification Phase 2
  MO PR-70057_01 AMIT Study for Long Term Settlement Solution
December 2008
  SO PR-50072_02 Phase II NDCRC (Net Dependable Capability & Reactive Capability)
  MO PR-80028_01 Small Renewables / Distributed Generation
  IO PR-70054_02 Blade Refresh
  IO PR-09908 2008 Minor Capital