## Market Design
ERCOT
Renewable Technology Working Group (RTWG)
List of Market Design Issues
January 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other REF No. | Action Date
MD | 1 | Ancillary Services Cost Allocations applicable to Wind | CATF | Near Term |  | CATF recommended to WMS/TAC that no changes be made. |  | TAC to make recommendatio to BOD in January
MD | 2 | Ancillary Services Procurement Optimization for 2009 | QMWG | Near Term |  | Under active discussion at QMWG
MD | 3 | Non-Spin requirements | PERTF | Near Term |  | Under discussion at PERTF
MD | 4 | Consideration of new ancillary service products in order to support reliability needs | ROS | Long Term |  | Eric Goff will develop list of questions to be developed into a white paper |  | Circulated prior to Feb meeting
MD | 5 | Storage technologies benefits (e.g., flywheels) to the integration of wind and provision of necessary ancillary services (regulation, responsive reserves) | RTWG | Long Term |  | Steve Isser will bring white paper to RTWG |  | Presented at Jan 29 meeting
MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF | Complete | ERCOT Procedure | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 7 | Protocol changes to allow wind resources to provide ancillary services | ROS | Undetermined | PRR | Walter Reid will develop list of questions to be developed into a white paper |  | Circulated prior to Jan 29 meeting
MD | 8 | Review of current Protocol to ensure requirements are applicable to all technologies re: reactive and voltage requirements | WOTF | Near Term | PRR | Docket 36482 open at PUCT. Future actions will be determined by the results of the proceeding. | WOTF 1a
MD | 9 | Review nodal protocols for proper treatment of wind generation re: dispatch response | TPTF | Near Term | NPRR | White paper with options will presented to TPTF | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 10 | Review nodal protocols for proper treatment of wind generation re: performance metrics with negative pricing | TPTF | Near Term | NPRR | White paper with options will presented to TPTF | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 11 | Review nodal protocols for proper treatment of wind generation re: base point deviaton charges as applicable to wind generation | TPTF | Near Term | NPRR | White paper with options will presented to TPTF | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 12 | WGR LSL as % of HSL | QMWG | Complete | PRR 773 | COMPLETE | WOTF 2a
MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans |  | Complete | PRR 763 | COMPLETE | WOTF 3b

## System Ops
ERCOT
Renewable Technology Working Group (RTWG)
List of System Operations Issues
January 2009
Issue Category | System Ops Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information | WOTF | Near Term | ERCOT Forms | Assigned to WOTF Modeling Subgroup. Currently being reviewed | WOTF 1d
SO | 2 | Identifying nodal tools to more effectively integrate wind into the grid | RTWG | Undetermined |  | Will be reviewed at January 29 meeting.
SO | 3 | Response to down balancing instructions (QMWG); SCE issues, clarity on expected following instructions, requirements | QMWG | Near Term |  | Being worked on currently by QMWG
SO | 4 | Smart grid implications on market design and integration of renewable resources | RTWG | Long Term |  | Eric Goff and Steve Isser will develop a white paper
SO | 5 | Operational studies re: Wind (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Walter Reid to develop a white paper to be presented to RTWG in March
SO | 6 | Qualification testing of reactive capability for wind generation | ERCOT | Near Term | OGRR | ERCOT drafting change to OG because the current procedure is inadequate
SO | 7 | High frequency: Develop alternate solutions | WOTF | Near Term |  | WOTF currently reviewing 4 possible solutions. Walter Reid will submit white paper. | WOTF 5
SO | 8 | System intertia capabilityof wind generators | PDCWG | Long Term |  | Mark Garrett to ask ROS for status update | WOTF 1e
SO | 9 | Better defined SCADA control on generation breakers | OGRR TF | Near Term | OGRR | Draft OGRR will be discussed at January 20 meeting | WOTF 1b
SO | 10 | ERCOT/TSP/Generator voltage management practices | WOTF | Near Term |  | Ask ERCOT and the TSPs for update at a WOTF meeting | WOTF 1c
SO | 11 | Protocols, Operating Guides, Interconnection Procedure and the Interconnection Agreement need to be updated to make requirements less ambiguous and more generic to include all types of generation | ROS | Near Term | PRR, OGRR, ERCOT Procedures and Agreements | Draft language being developed - will be circulated in two weeks
SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs |  | Complete | OGRR 208 | COMPLETE
SO | 13 | Performance metrics for wind | QMWG | Near Term | PRR 793 (Urgent) | PRR793 at January 22 meeting. Add'l PRRs are being developed
SO | 14 | What can we do to identify upcoming transmission outages and what can we do to minimize outage times and wind power production? | CMWG | Long Term |  | Under active discussion at CMWG | WOTF 3e
SO | 15 | 24/7 communication must be available for TSP to reach wind generators. | WOTF | Near Term | OGRR | Draft OGRR will be discussed at January 20 meeting | WOTF 2a
SO | 16 | Wind generation ramp rate limitations | ROS | Complete | PRR 771, PRR 788 | PRR 771 is APPROVED and PRR 788 approved by TAC | WOTF 3a
SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | Complete | ERCOT Procedures | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3b
SO | 19 | Run multiple CSC limit studies | WOTF | Complete | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3f
SO | 20 | Dynamic line ratings | WOTF | Complete | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3g
SO | 21 | Reexamine EECP Steps | OWG | Complete | PRR 769 NPRR 142 | COMPLETED: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting | WOTF 3h
SO | 23 | Integrating advanced meters and other demand response into the existing and Nodal Ancillary Service markets | DSWG | Long Term |  | 2009 Goal for WMS
SO | 24 | Long term solutions for advanced meter settlement; incuding, impact of plug-in hybrid vehicles on storage and use of renewable resources. | AMIT | Long Term |  | Complete work suggested by EDS B&V study
SO | 25 | Governor Generator Response of wind generators | WOTF | Undetermined |  | Under active discussion at WOTF | WOTF 1e
SO | 26 | Operational studies: Solar (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Steve Isser to develop a white paper to be presented to RTWG in March
SO | 27 | ERCOT Operations is currently analyzing and deploying all wind generation local curtailment manually - what, if any, problems is this causing? | QMWG | Near Term |  | ERCOT to discuss at February QMWG

## System Planning
ERCOT
Renewable Technology Working Group (RTWG)
List of System Planning Issues
January 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref. No.
SP | 1 | Verify technical data (installed technology) | ERCOT | Near Term | ERCOT Survey | ERCOT to coordinate a meeting with stakeholders in December
SP | 2 | Verify computer models for wind generation | ERCOT | Near Term |  | Included in ERCOT's LVRT Study
SP | 3 | Fault Tolerance Studies (OGRR208) | ERCOT | Near Term | OGRR | Included in ERCOT's LVRT Study
SP | 4 | Updated Voltage Transient and Small Signal Stability Study (West to North Transfer Study) | ERCOT | Near Term |  | ERCOT to report on status at January RTWG
SP | 5 | Inertia Study | ERCOT | Long Term |  | Will be undertaken following completion of LVRT study
SP | 6 | Use of VFTs to solve stability problems | RTWG | Long Term |  | Walter Reid/Paul Hassink to develop white paper
SP | 7 | Voltage Swing Management (Voltage Control Process) | ERCOT | Long Term |  | Will revisit after CREZ decision
SP | 8 | Low Voltage Ride Through Study | ERCOT | Near Term |  | All study results due to ROS no later than June 2010

## WT
ERCOT
Renewable Technology Working Group (RTWG)
List of Workshop/Training Opportunities
January 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Status | Other Ref. No.
WT | 1 | WGR QSE Resource Plan and Energy Schedule Update Process | RTWG/ERCOT | Undetermined | Included with Workshop III
WT | 2 | ERCOT Wind Workshop III - Spring 2009 | RTWG/ERCOT | Near Term | ERCOT Operations to develop draft outline
WT | 3 | WGR Operator Training | RTWG/ERCOT | Long Term | Ask ERCOT training to discuss with RTWG

## COMPLETED
ERCOT
Renewable Technology Working Group (RTWG)
List of All Completed Issues
Issue Category | System Ops Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs |  |  | OGRR 208 | COMPLETE
MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF | Complete |  | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 12 | WGR LSL as % of HSL | QMWG | Complete | PRR 773 | COMPLETE | WOTF 2a
MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans |  | Complete | PRR 763 | COMPLETE | WOTF 3b
SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs |  | Complete | OGRR 208 | COMPLETE
SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | Complete |  | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3b
SO | 19 | Run multiple CSC limit studies | WOTF | Complete | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3f
SO | 20 | Dynamic line ratings | WOTF | Complete | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3g

## Summary
ERCOT
Renewable Technology Working Group (RTWG)
List of Issues
January 2009
No. | Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Action Date
1 | MD | 1 | Ancillary Services Cost Allocations applicable to Wind | CATF | Near Term | 0 | CATF recommended to WMS/TAC that no changes be made.
2 | MD | 2 | Ancillary Services Procurement Optimization for 2009 | QMWG | Near Term | 0 | Under active discussion at QMWG
3 | MD | 3 | Non-Spin requirements | PERTF | Near Term | 0 | Under discussion at PERTF
4 | MD | 4 | Consideration of new ancillary service products in order to support reliability needs | ROS | Long Term | 0 | Eric Goff will develop list of questions to be developed into a white paper
5 | MD | 5 | Storage technologies benefits (e.g., flywheels) to the integration of wind and provision of necessary ancillary services (regulation, responsive reserves) | RTWG | Long Term | 0 | Steve Isser will bring white paper to RTWG
6 | MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF | Complete | ERCOT Procedure | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009
7 | MD | 7 | Protocol changes to allow wind resources to provide ancillary services | ROS | Undetermined | PRR | Walter Reid will develop list of questions to be developed into a white paper
8 | MD | 8 | Review of current Protocol to ensure requirements are applicable to all technologies re: reactive and voltage requirements | WOTF | Near Term | PRR | Docket 36482 open at PUCT. Future actions will be determined by the results of the proceeding.
9 | MD | 9 | Review nodal protocols for proper treatment of wind generation re: dispatch response | TPTF | Near Term | NPRR | White paper with options will presented to TPTF
10 | MD | 10 | Review nodal protocols for proper treatment of wind generation re: performance metrics with negative pricing | TPTF | Near Term | NPRR | White paper with options will presented to TPTF
11 | MD | 11 | Review nodal protocols for proper treatment of wind generation re: base point deviaton charges as applicable to wind generation | TPTF | Near Term | NPRR | White paper with options will presented to TPTF
12 | MD | 12 | WGR LSL as % of HSL | QMWG | Complete | PRR 773 | COMPLETE
13 | MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans | 0 | Complete | PRR 763 | COMPLETE
14 | SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information | WOTF | Near Term | ERCOT Forms | Assigned to WOTF Modeling Subgroup. Currently being reviewed
15 | SO | 2 | Identifying nodal tools to more effectively integrate wind into the grid | RTWG | Undetermined | 0 | Will be reviewed at January 29 meeting.
16 | SO | 3 | Response to down balancing instructions (QMWG); SCE issues, clarity on expected following instructions, requirements | QMWG | Near Term | 0 | Being worked on currently by QMWG
17 | SO | 4 | Smart grid implications on market design and integration of renewable resources | RTWG | Long Term | 0 | Eric Goff and Steve Isser will develop a white paper
18 | SO | 6 | Qualification testing of reactive capability for wind generation | ERCOT | Near Term | OGRR | ERCOT drafting change to OG because the current procedure is inadequate
19 | SO | 7 | High frequency: Develop alternate solutions | WOTF | Near Term | 0 | WOTF currently reviewing 4 possible solutions. Walter Reid will submit white paper.
20 | SO | 8 | System intertia capabilityof wind generators | PDCWG | Long Term | 0 | Mark Garrett to ask ROS for status update
21 | SO | 9 | Better defined SCADA control on generation breakers | OGRR TF | Near Term | OGRR | Draft OGRR will be discussed at January 20 meeting
22 | SO | 11 | Protocols, Operating Guides, Interconnection Procedure and the Interconnection Agreement need to be updated to make requirements less ambiguous and more generic to include all types of generation | ROS | Near Term | PRR, OGRR, ERCOT Procedures and Agreements | Draft language being developed - will be circulated in two weeks
23 | SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs | 0 | Complete | OGRR 208 | COMPLETE
24 | SO | 13 | Performance metrics for wind | QMWG | Near Term | PRR 793 (Urgent) | PRR793 at January 22 meeting. Add'l PRRs are being developed
25 | SO | 14 | What can we do to identify upcoming transmission outages and what can we do to minimize outage times and wind power production? | CMWG | Long Term | 0 | Under active discussion at CMWG
26 | SO | 15 | 24/7 communication must be available for TSP to reach wind generators. | WOTF | Near Term | OGRR | Draft OGRR will be discussed at January 20 meeting
27 | SO | 16 | Wind generation ramp rate limitations | ROS | Complete | PRR 771, PRR 788 | PRR 771 is APPROVED and PRR 788 approved by TAC
28 | SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | Complete | ERCOT Procedures | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action.
29 | SO | 19 | Run multiple CSC limit studies | WOTF | Complete | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008
30 | SO | 20 | Dynamic line ratings | WOTF | Complete | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems
31 | SO | 21 | Reexamine EECP Steps | OWG | Complete | PRR 769 NPRR 142 | COMPLETED: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting
32 | SO | 23 | Integrating advanced meters and other demand response into the existing and Nodal Ancillary Service markets | DSWG | Long Term | 0 | 2009 Goal for WMS
33 | SO | 24 | Long term solutions for advanced meter settlement; incuding, impact of plug-in hybrid vehicles on storage and use of renewable resources. | AMIT | Long Term | 0 | Complete work suggested by EDS B&V study
34 | SO | 25 | Governor Generator Response of wind generators | WOTF | Undetermined | 0 | Under active discussion at WOTF
35 | SO | 26 | Operational studies: Solar (ramp rate, low load situations, forecasting) | RTWG | Long Term | 0 | Steve Isser to develop a white paper to be presented to RTWG in March
36 | SO | 27 | ERCOT Operations is currently analyzing and deploying all wind generation local curtailment manually - what, if any, problems is this causing? | QMWG | Near Term | 0 | ERCOT to discuss at February QMWG
37 | SP | 1 | Verify technical data (installed technology) | ERCOT | Near Term | ERCOT Survey | ERCOT to coordinate a meeting with stakeholders in December
38 | SP | 2 | Verify computer models for wind generation | ERCOT | Near Term | 0 | Included in ERCOT's LVRT Study
39 | SP | 3 | Fault Tolerance Studies (OGRR208) | ERCOT | Near Term | OGRR | Included in ERCOT's LVRT Study
40 | SP | 4 | Updated Voltage Transient and Small Signal Stability Study (West to North Transfer Study) | ERCOT | Near Term | 0 | ERCOT to report on status at January RTWG
41 | SP | 5 | Inertia Study | ERCOT | Long Term |  | Will be undertaken following completion of LVRT study
42 | SP | 6 | Use of VFTs to solve stability problems | RTWG | Long Term |  | Walter Reid/Paul Hassink to develop white paper
43 | SP | 7 | Voltage Swing Management (Voltage Control Process) | ERCOT | Long Term |  | Will revisit after CREZ decision
44 | SP | 8 | Low Voltage Ride Through Study | ERCOT | Near Term |  | All study results due to ROS no later than June 2010
45 | WT | 1 | WGR QSE Resource Plan and Energy Schedule Update Process | RTWG/ERCOT | Undetermined | #REF! | Included with Workshop III
46 | WT | 2 | ERCOT Wind Workshop III - Spring 2009 | RTWG/ERCOT | Near Term | #REF! | ERCOT Operations to develop draft outline
47 | WT | 3 | WGR Operator Training | RTWG/ERCOT | Long Term | #REF! | Ask ERCOT training to discuss with RTWG
MD = Market Design
SO = System Operations
SP = System Planning
WT = Workshop/Training