## Slide 1: ERCOT and TSP activities for Planning Model Go-Live
February 12, 2009
ROS

## Slide 2: What is Planning Model Go-Live?
Planning Model Go-Live is the deployment of ERCOT’s NMMS application in ERCOT’s production environment, along with an SSWG approved Year Ahead Planning Model, for use by ERCOT and Market Participants for the generation of Annual Planning Models
ERCOT intends to go-live with the NMMS tool for Planning Model management, in April 2010

## Slide 3: Planning Model Go-Live – Steps involved
# | Task
1 | Single Entry Model Go-Live
2 | TSPs perform data synchronization on Network Operations Model
3 | ERCOT conducts TSP training on PMCR process and MOD tool
4 | EDS testing of PMCR process and MOD by TSPs
5 | ERCOT generates Year Ahead Planning Model using MOD
6 | ERCOT seeks TPTF approval for proceeding with Planning Model Go-Live
7 | ERCOT generates Annual Planning Models for 2011 and 2012
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
SEM Go-Live
TSP Network Model Synchronization
TSP Training on PMCR and MOD
TSP EDS testing of MOD
ERCOT generates
Year Ahead Planning Model
Planning Model
Go-Live
Go-Live
sequence
Single Entry
Model
MOD training &
testing
MOD go-live
2009
2010

## Slide 4: Next Steps
ERCOT is requesting the ROS’ permission to work closely with the SSWG to detail the schedule and activities of ERCOT and TSPs related to Planning Model Go-Live.
Meeting organized for Feb 24, 2009 with SSWG to begin discussing TSP and ERCOT activities for Planning Model Go-Live
Work iteratively with SSWG to finalize Planning Model Go-Live procedure and schedule, before seeking ROS’ endorsement