|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for January 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 256 active generation interconnection requests totaling over 106,000 MW. This includes 52,000 MW of wind generation. - 60 MW of new wind generation began commercial operation in January, bringing the currently installed total of wind power capacity to 8,065 MW. - Pursuant to PRR 779, a listing of projects undergoing Full Interconnection Studies has been made public in Section 1.5 |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $770 Million - Transmission Projects approved in 2008 total $255 Million - All projects (in engineering, routing, licensing and construction) totals approximately $4.1 Billion - Transmission Projects energized in 2008 total about $453 |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements  -       none for January 2009	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4	Potential Future Generation Interconnections	2

1.5	Potential Future Generation Projects Undergoing Full Interconnection Studies	3

1.6	Wind Capacity Installed by Year	5

2.	Regional Planning Group Project Reviews	6

3.	Other Notable Activities	7

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

# No-Trees Wind (07INR0005) in Ector County for an additional 60 MW

## The total installed wind capacity is now 8,065 MW, of which 7,407 (92%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements -       none for January 2009

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 254 active generation interconnection or change requests |  |  |  |  |
| As of January 31, 2009 | North | South | West | Total |
| Security Screening Study | 2 | 4 | 6 | 12 |
| SSS Completed | 5 | 14 | 34 | 53 |
| Full Interconnect Study | 34 | 40 | 82 | 156 |
| FIS Completed | 2 | 8 | 1 | 11 |
| Interconnect Agreement Completed | 7 | 8 | 9 | 24 |
| Capacity under Interconnection Agreements | 5,308 | 2,578 | 1,262 | 9,148 |
| Capacity for Grid, MW | 25,438 | 36,997 | 43,799 | 106,234 |
| Wind Capacity, MW | 2,047 | 10,429 | 39,524 | 52,000 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC | 5,216 |  | 5,229 | 10,445 |
| Gas-CT | 400 |  | 505 | 905 |
| Total Gas | 5,616 | 18,361 | 5,734 | 29,711 |
| Nuclear | 0 | 3,200 | 9,186 | 12,386 |
| Coal | 2,943 | 2,432 | 4,131 | 9,506 |
| Wind | 15,704 | 29,253 | 7,043 | 52,000 |
| Solar | 955 | 0 | 0 | 955 |
| Biomass | 0 | 50 | 145 | 195 |
| Other | 0 | 1,480 | 0 | 1,480 |
| Grand Total | 25,218 | 54,776 | 26,239 | 106,233 |

## Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections as of January 31, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Mar-09 | Wind | 200 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | Gas-CC | 255 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Mar-09 | Wind | 300 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | Gas-CT | 48 |  |
| 10INR0025 | Mont Belvieu | IA | Chambers | South | Apr-09 | Gas-CT | 0 |  |
| 07INR0028b | Goat Wind - phase 2 | IA | Sterling | West | Apr-09 | Wind | 70 |  |
| 07INR0027 | S Houston Green Power Exp | IA | Galveston | South | Apr-09 | Gas-CC | 244 |  |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 08INR0040 | Lenorah Project | PL | Martin | West | May-09 | Wind | 350 |  |
| 08INR0012 | Papalote Creek Wind Farm | IA | San Patricio | South | May-09 | Wind | 180 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-09 | Wind | 300 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | Gas-CC | 539 |  |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jul-09 | Gas-CT | 178 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Jul-09 | Coal | 581 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 327 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Dec-09 | Wind | 251 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
|  |  |  |  |  |  |  | 26,239 |  |

## Potential Future Generation Projects Undergoing Full Interconnection Studies

| Project | County | Capacity (MW) | COD | Fuel |  | Project | County | Capacity (MW) | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0009 | Jack | 150 | TBD | Wind |  | 10INR0013 | Upton | 400 | Jul-10 | Wind |
| 08INR0044 | Concho | 200 | TBD | Wind |  | 10INR0038 | Glasscock | 350 | Aug-10 | Wind |
| 08INR0011 | Jack | 150 | TBD | Wind |  | 10INR0071 | Matagorda | 88 | Sep-10 | Wind |
| 06INR0022c | Kenedy | 200 | TBD | Wind |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 08INR0061 | Hardeman | 200 | TBD | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 08INR0062 | Archer | 249 | TBD | Wind |  | 10INR0070 | Hunt | 50 | Nov-10 | Gas |
| 08INR0020 | Eastland | 200 | TBD | Wind |  | 10INR0039 | Dickens | 200 | Nov-10 | Wind |
| 09INR0064 | Borden | 41 | Mar-09 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 08INR0042 | Coke | 200 | Mar-09 | Wind |  | 10INR0032 | Navarro | 800 | Dec-10 | Gas |
| 08INR0041 | Coke | 200 | Mar-09 | Wind |  | 10INR0060 | Willacy | 401 | Dec-10 | Wind |
| 09INR0005 | Calhoun | 280 | Apr-09 | other |  | 10INR0059 | Zapata | 251 | Dec-10 | Wind |
| 09INR0059 | Freestone | 20 | May-09 | Coal |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 07INR0026 | Baylor | 400 | May-09 | Wind |  | 10INR0077 | Callahan | 101 | Dec-10 | Wind |
| 08INR0005 | Wise | 400 | Jun-09 | Gas |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 09INR0079 | Frio | 203 | Jun-09 | Gas |  | 10INR0049 | Pecos | 200 | Dec-10 | Wind |
| 09INR0025 | Concho | 180 | Jun-09 | Wind |  | 10INR0033 | Armstrong | 420 | Dec-10 | Wind |
| 09INR0044 | Coke | 60 | Sep-09 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 09INR0075 | Kinney | 248 | Oct-09 | Wind |  | 09INR0031 | Ector | 275 | Dec-10 | Gas |
| 10INR0027 | Nueces | 35 | Oct-09 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-09 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 10INR0026 | Tom Green | 186 | Oct-09 | Wind |  | 07INR0015 | Foard | 180 | Dec-10 | Wind |
| 09INR0055 | McCulloch | 299 | Oct-09 | Wind |  | 07INR0017 | Erath | 210 | Dec-10 | Wind |
| 09INR0041 | Mitchell | 300 | Oct-09 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-09 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 09INR0048 | Jack | 150 | Oct-09 | Wind |  | 11INR0036b | Matagorda | 200 | Jan-11 | Wind |
| 08INR0054 | Comanche | 401 | Oct-09 | Wind |  | 11INR0037 | Smith | 55 | May-11 | Biomass |
| 09INR0073 | Scurry | 200 | Nov-09 | Wind |  | 11INR0028 | Grimes | 1,280 | May-11 | Gas |
| 11INR0015 | Concho | 249 | Nov-09 | Wind |  | 11INR0046 | Brazoria | 300 | May-11 | Gas |
| 08INR0031 | Childress | 100 | Nov-09 | Wind |  | 10INR0009 | Castro | 200 | May-11 | Wind |
| 11INR0013 | Mills | 150 | Dec-09 | Wind |  | 11INR0009 | Navarro | 1,200 | Jun-11 | Gas |
| 08INR0039 | Hamilton | 90 | Dec-09 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 11INR0012 | Duval | 400 | Dec-09 | Wind |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 09INR0065 | Webb | 150 | Dec-09 | Wind |  | 11INR0021 | Upton | 200 | Jun-11 | Wind |
| 09INR0061 | Kent | 258 | Dec-09 | Wind |  | 11INR0022 | Upton | 200 | Jun-11 | Wind |
| 09INR0058 | Howard | 250 | Dec-09 | Wind |  | 11INR0020 | Upton | 200 | Jun-11 | Wind |
| 09INR0054 | Stonewall | 149 | Dec-09 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 09INR0051 | Borden | 249 | Dec-09 | Wind |  | 06INR0041 | Newton | 1,160 | Jul-11 | Gas |
| 08INR0056 | Nolan | 149 | Dec-09 | Wind |  | 11INR0040 | freestone | 749 | Aug-11 | Gas |
| 08INR0023 | Floyd | 100 | Dec-09 | Wind |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 08INR0022 | Floyd | 100 | Dec-09 | Wind |  | 11INR0008c | Roberts | 600 | Sep-11 | Gas |
| 10INR0011 | Johnson | 275 | Jan-10 | Gas |  | 11INR0008b | Roberts | 750 | Sep-11 | Coal |
| 10INR0047 | Kendall | 1,000 | Jan-10 | wind |  | 11INR0008a | Roberts | 4,000 | Sep-11 | Wind |
| 11INR0036a | Matagorda | 200 | Jan-10 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0033a | Cameron | 200 | Jan-10 | Wind |  | 09INR0016 | Yoakum | 680 | Nov-11 | Gas |
| 10INR0048 | Hardeman | 1,000 | Jan-10 | wind |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 11INR0014 | Harris | 50 | Feb-10 | Gas |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 10INR0018 | Madison | 550 | Mar-10 | Gas |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 10INR0022 | Harris | 3,500 | Mar-10 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 08INR0026 | Galveston | 200 | Mar-10 | Wind |  | 12INR0006 | Limestone | 875 | Jun-12 | Coal |
| 10INR0045 | Webb | 734 | Apr-10 | wind |  | 12INR0020 | Wharton | 660 | Jun-12 | gas |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | wind |  | 12INR0002 | Briscoe | 750 | Jul-12 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 12INR0016 | Nueces | 1,200 | Nov-12 | other |
| 10INR0028 | Harris | 641 | May-10 | Gas |  | 08INR0019a | Gray | 250 | Nov-12 | Wind |
| 09INR0070 | Reagan | 42 | May-10 | Wind |  | 08INR0019b | Gray | 250 | Nov-12 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 08INR0019c | Gray | 250 | Nov-12 | Wind |
| 10INR0023 | Haskell | 386 | May-10 | Wind |  | 06INR0022b | Kenedy | 200 | Dec-12 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 09INR0035 | Concho | 750 | May-10 | Wind |  | 11INR0023 | King | 400 | Dec-12 | Wind |
| 09INR0018 | Concho | 249 | May-10 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 07INR0032 | Tom Green | 249 | May-10 | Wind |  | 12INR0009 | Nueces | 875 | May-13 | Gas |
| 10INR0069 | Rusk | 818 | May-10 | Coal |  | 06INR0022e | Kenedy | 200 | Dec-13 | Wind |
| 10INR0076 | Webb | 225 | May-10 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 09INR0081 | Rusk | 818 | Jun-10 | Coal |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 15INR0003 | Matagorda | 3,200 | Jan-15 | Nuclear |
| 10INR0035 | Harris | 416 | Jun-10 | Gas |  | 09INR0082 | Webb | 300 | Dec-09 | Wind |
| 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |  | 10INR0079 | Nolan | 60 | May-10 | Wind |
| 10INR0052a | Knox | 21 | Jul-10 | Wind |  |  |  |  |  |  |

## Wind Capacity Installed by Year

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is in ERCOT Independent Review.

# Oncor submitted a project to install an additional 300 MVar of dynamic reactive at Renner station.  The estimated cost of this project is $ 35 M with an in-service date of 2010.  The review of this project is complete and a RPG Acceptance Letter is being prepared.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Austin Energy submitted a project to establish a 138 kV circuit from Hicross to Slaughter Lane by building 2.2 miles of new transmission line to an un-energized 1.2 mile circuit segment.  This project will cost $5.774 M with an estimated completion date of October 2010.  The review of this project is complete and a RPG Acceptance Letter is being prepared.

# Oncor submitted a project to add a 138/69 kV autotransformer at Stanton East into the Spraberry to Big Spring 69 kV line and rebuild the 138 kV line from Stanton East to Big Spring Switch.  This project will cost $15 M with an estimated completion date no earlier than summer 2011.  This project is in study period.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in study period.

- Austin Energy submitted a project to relocate the Decker to Techridge circuit to new ROW so that the existing structures can be utilized for the new Gilleland to Techridge circuit.  The estimated completion date of this project is November 2010 and estimated cost is $ 4.3 M.   This project is in study period.

# Other Notable Activities

- All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT Regional Planning has begun work on the 2009 Five-Year Transmission Plan utilizing the latest SSWG base cases.  This work is in the conditioning phase where projects in the base cases requiring RPG review that have not undergone that review are removed.  These projects have been identified and submitted to Transmission Owners for their review and creation of IDEV’s to remove the projects from the base cases.

- The Annual Load Data Request (ALDR) training was held on January 21, 2009.

- ERCOT TPIT report for 2009 first quarter is due to be filed on or before March 1, 2009.

- With increased legislative activities and interest in renewable energy and emissions, the REC program is reviewing several senate and house bills that will bring change to the program and to Texas.  The REC program also successfully issued the RPS Mandate for 2008.