## Notes
Review analysis of CCET demonstration programs (Pilot)
Review LPG language on list based profiles and universality
Evaluate latest bill for NIDR data estimation for initial settlement
To improve distribution loss estimations, PWG should consider recommending that TDSP’s perform updated loss studies.
Evaluate the application of lagged dynamic profiling techniques to the ERCOT System
Implement settlement using 15 minute interval data from AMI meters where appropriate
Advanced Metering Implementation LPG changes if needed
From UFE 2007 Final Report
*** | Not expected to be completed in 2008 due to market status |  |  |  | CHG
*** | Working or on the next Agenda
*** | Parked items to large projects or waiting on Advanced Metering
*** | Shall be on the November Agenda
18 | Distributive Generation load profiling implementation (PRR756 and LPGRR030) | 2008-05-25 | 100%
10 | Review IDR installation procedure language to ensure compliance (Pending AMR Rule) | 2008-08-25 | 90% | CHG
18b | Distributive Generation load profiling implementation issues | 2008-08-26 | 60% | CHG
10 |  | 2008-08-25 | 90% | CHG
5 | Examine ways to accommodate extreme events in Settlement process. | 2008-12-27 | 90% | CHG
15 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2008-12-31 | 0% |  | CHG
13 |  | 2008-12-31 | 0% |  | New
1 | Profile calibration with round two sample | 2008-07-01 | 100%

## 2009
No. | PWG 2009 Goals | Target Date | % Complete
1 | Review 2008 UFE Analysis (April 30, true-up in Aug or Sept) | 2009-09-23 | 0%
2 | 2009 Annual Validation. | 2009-12-15 | 0%
3 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2009-12-09 | 0%
4 | Review Weather Sensitivity Correlation | 2009-07-31 | 0%
5 | Review Proxy Day Method | 2009-06-30 | 0%
6 | Evaluate Hurricane Ike affect on settlement for possible improvements | 2009-12-09 | 0%
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2009-04-30 | 0%
8 | Review profile models using Round 2 load research data, review if having more weather stations adds accuracy, and review if the weighting of weather stations is appropriate. | 2009-12-09 | 0%
9 | Improve Business Profile ID assignment process | 2009-12-09 | 0%
10 | Reevaluate distribution loss methodology due to advanced metering. | 2009-12-09 | 0%
11 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16, 2007) | 2009-06-30 | 0%
12 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2009-12-09 | 0%
13 | Demand Response LPG or PRR language changes as needed | 2009-12-09 | 0%

## 2008
No. | PWG 2008 Goals | Target Date | % Complete
18 | Distributive Generation load profiling implementation (PRR756 and LPGRR030) | 2008-05-25 | 100%
1 | Implementation of LRS sample selection round two. | 2008-07-01 | 100%
4 | Review 2007 UFE Analysis (final complete, true-up pending) | 2008-07-30 | 100%
10 | Review IDR installation procedure language to ensure compliance (Pending AMR Rule) | 2008-08-25 | 100% | CHG
18b | Distributive Generation load profiling implementation issues | 2008-08-26 | 100% | CHG
2 | 2008 Annual Validation. | 2008-11-07 | 100% | CHG
17 | Advanced Metering Implementation LPG changes if needed | 2008-12-01 | 100% | CHG
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2008-12-07 | 10% | CHG
5 | Examine ways to accommodate extreme events in Settlement process. | 2008-12-27 | 90% | CHG
14 | Review analysis of DLC demonstration programs (Pilot) | 2008-12-27 | 0% | CHG
16 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2008-12-27 | 0% | CHG
3 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16) | 2008-12-31 | 15%
6 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2008-12-31 | 0%
8 | Review if having more weather stations adds accuracy | 2008-12-31 | 0%
9 | Review if the weighting of weather stations is appropriate | 2008-12-31 | 0%
11 | Review LPG language on list based profiles and universality | 2008-12-31 | 0%
12 | Demand Response Implementation | 2008-12-31 | 0% |  | CHG
13 | Investigate ways to improve Business Profile ID assignments | 2008-12-31 | 0% |  | New
15 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2008-12-31 | 0% |  | CHG
*** | Not completed in 2008 due to market status |  |  |  | CHG
*** | Working or on the next Agenda
*** | Parked items to large projects or waiting on Advanced Metering
*** | Shall be on the November Agenda

## 2007
No. | PWG 2007 Goals | Target Date | % Complete
1 | Implement new Version 2 ERCOT Profiles. | 2007-05-07 | 100%
2 | LRS sample selection round two. | 2007-04-01 | 100%
3 | New Oil & Gas Profile - BUSOGFLT | 2007-09-07 | 100%
4 | 2007 Annual Validation. | 2007-11-07 | 80% to 100% | CHG
5 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16) | 2007-12-07 | 0% | CHG
6 | Review 2004, 2005 & 2006 UFE Analysis. | 2007-12-07 | 67 to 100% | CHG
7 | Examine ways to accommodate extreme events in Settlement process. | 2007-12-07 | 5% | CHG
8 | Establish Long Term Strategy of Load Profiles including refresh timeline | 2007-09-07 | 5% to 100% | CHG
9 | IDR Analysis – 2 issues outstanding from original analysis. | 2007-12-07 | 0% | CHG
10 | Review if having more weather stations adds accuracy | 2007-12-01 | 0%
11 | Review if the weighting of weather stations is appropriate | 2007-12-01 | 0%
12 | Review IDR installation procedure language to ensure compliance (Pending AMR Rule) | 2007-12-07 | 0% | CHG
13 | Does having 2 decimals on load profiles significantly affect settlement | 2007-06-07 | 100%
14 | Review LPG language on list based profiles and universality | 2007-12-07 | 0%
15 | PUCT Docket responses to demand response or AMR rule, etc. (DLC Implementation) | 2007-12-07 | 65 to 70% | CHG
16 | Set up area on PWG web page for key documents | 2007-05-07 | 100%
17 | Annual Review of load profiles as specified in market language | NA | NA
18 | Analysis to identify new profiles as specified in market language (Primary Voltage) | 2007-12-07 | 20% to 100% | CHG
19 | Update the TOU procedures on the Load Profiling web site | 2007-12-07 | 25% to 100% | CHG
20 | Investigate ways to improve Business Profile ID assignments | 2007-12-07 | 0%
21 | Review analysis of DLC demonstration programs (Pilot) | 2007-12-07 | 0% |  | CHG
22 | Review Protocol and LPG language for appropriateness for large Opt-in Entity | 2007-12-07 | 5% | CHG | CHG
23 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2007-12-07 | 15% | CHG | CHG
24 | Advanced Metering Implementation for IDR Requirement and TOU | 2007-12-07 | 0% to 50% | CHG | New
Color Legend:
Completion in 2007 shall not occur - moved to 2008 |  |  |  | CHG