## TPTF Punchlist - OPEN Items
This worksheet contains all TPTF Punchlist items identified as "OPEN" by TPTF during the final Punchlist audit conducted by TPTF on 2/24/2009. Please note that five of the line items in this listing have been replicated from the worksheet of follow-up items for the nodal program schedule (see the workseet named "012909 ScheduleResponses 35" in this workbook). These replicated items have been flagged in the "Notes" section.
# | Description | Comments | Document that initiated item | Date added | STATUS (closed, open) | Notes
1 | Informal review needed of System Change Request (SCR) 746, Dynamic Rating Data to TSP using Inter-Control Center Communications Protocol (ICCP) Link, to determine if an NPRR is required | SCR746, Dynamic Rating Data to TSP using ICCP Link. Projected increase for exported Supervisory Control and Data Acquisition (SCADA) values. | SCADA EMS Requirements | 2007-01-23 | OPEN | Trip Doggett will consult with Richard Howard and the ICCP group in order to find out if they are interested in producing an NPRR to reverse the decision in SCR746. 7/9/2007: Richard Howard - will capture requirement in nodal without any additional SCRs or NPRRs. Check with Bill Blevins whether this requirement is in the ICCP Handbook and what the speed is
2 | Funding/Accounting during market trials |  | Metrics review | 2007-03-06 | OPEN | 7/9/2007: Cheryl Yager will talk with TPTF regarding credit transition to nodal at the July 23-25 TPTF meeting. Request Daryl Cote to follow up on this issue after LFC test procedures are finalized. 2/24/2009: To remain open as a TPTF action item and referred to the Credit Work Group (CWG) for input and guidance on testing the credit integration into EDS 4 currently scheduled for Spring 2010.
3 | Issue of .xml version of Statements and Invoices by Application Programming Interface (API) should be available Market Participants via additional formats including .csv, xls, etc. |  | COMS Requirements | 2007-05-24 | OPEN | 2/24/2009: Awaiting response from Commercial Systems (COMS)/Program Management Office (PMO).
4 | Discuss HSL and URL issues at a future TPTF meeting |  | IDA Whitepaper IDA013, "Seasonal/ Temperature/ Hydrogen Pressure based Reactive Capacity Curves and MW Capability Curves" | 2007-06-21 | OPEN | Diran Obadina to follow up with TPTF. 2/24/2009: Awaiting the ERCOT Operations Business Process for managing system voltage and expectation for modeling of the reactive capability curve.
5 | Confirm billing determinants for the results are included in settlements extracts |  |  | 2007-07-09 | OPEN | 2/24/2009: Need to provide billing determinants that will be available in the settlements extract to support Market Participant building its shadow settlement system. Action item: Stacy Bridges is requested to pass ownership of this item to the Commercial Operations Subcommittee (COPS).
6 | Issue of substation names in retail market business; should they be consistent with the ERCOT network model and if so, what is the plan to get that done including the timeline |  |  | 2007-07-09 | OPEN | Trip Doggett will touch base with Raj Chudgar. 2/24/2009: This item is discussed and needs to be verified if it becomes a major updating issue.
7 | Update the Credit Monitoring and Management (CMM) CSD to indicate that the definition of Congestion Revenue Right (CRR) includes Pre-Assigned CRRs (PCRRs) and McCamey Flowgate Rights (MCFRIs). |  | CMM CSD | 2007-07-11 | OPEN | 2/24/2009: Action Item: Stacy Bridges is requested to pass ownership of this item to the CWG regarding the need to create a value for PCRRs and MCFRIs to properly calculate the credit constraint in the CRR auction for owners of these instruments.
8 | Elaborate the manual processes for CMM and document them in the CMM Operating Procedures (See the CMM Punch Tab in this workbook) |  | CMM Requirements/ CMM CSD | 2007-07-11 | OPEN | 2/24/2009: CMM Business Procedures should be reviewed by Market Participants. TPTF has begun reviews of the ERCOT Business Procedures. The ERCOT Nodal Project Manager supporting this activity has brought to TPTF the Level 1 and Level 2 documents describing ERCOT’s Business Procedures. Levels 3 and 4 are currently under development and TPTF has been requested to review these documents and provide comments as they become available. ERCOT has presented TPTF with draft procedures for the DAM and the Reliability Unit Commitment (RUC) Market Operations and made updates with TPTF comments. TPTF Recommendation: TAC, or its designee, should review the Levels 3 and 4 Business Procedure documents as they are developed by the ERCOT Nodal Project Manager and provide comments for ERCOT consideration.
9 | ERCOT’s telemetry validation process | ERCOT’s Business Process of validating new telemetry when it’s first made available to the ERCOT system needs to be described and implemented. TSPs and other Market Participants should support this new process. |  | 2009-01-07 | OPEN | 2/24/2009: This issue is being resolved by ERCOT and the Network Data Support Working Group (NDSWG). Once this item is resolved by ERCOT and the NDSWG, TAC, or its designee, needs to determine how much, if any, regression testing needs to be done on the checkout performed on EDS 1 and EDS 2. NOTE: This TPTF Punchlist entry has been replicated from Line Item #1 in the worksheet named "012909 ScheduleResponses 35" in this workbook.
10 | Discuss the updated change-process flowchart with TPTF (targeted for January 2009) |  |  | 2008-12-15 | OPEN | 2/24/2009: TAC, or its designee, needs to review the process flowchart. NOTE: This TPTF Punchlist entry has been replicated from Line Item #3 in the worksheet named "012909 ScheduleResponses 35" in this workbook.
11 | TPTF developed an action plan in meetings with the PMO on the Project Schedule. Several pending action items require final resolution by ERCOT and other working groups. |  |  | 2009-02-24 | OPEN | 2/24/2009: TAC, or its designee, needs to review the final resolution of the remaining action plans of the PMO and the other working group, as posted in this workbook under the worksheet tab labeled “012909 ScheduleResponses 35.”
12 | Identify the change process to be followed for the Nodal Data Services Master List (NDSML). | ERCOT is considering collective view of comments received and will prepare a response—not applicable for inclusion into the Integration Program Schedule |  | 2008-12-15 | OPEN | 2/24/2009: TAC, or its designee, needs to review the final resolution of updating the NDSML. NOTE: This TPTF Punchlist entry has been replicated from Line Item #2 in the worksheet named "012909 ScheduleResponses 35" in this workbook.
13 | Confirm that recent updates in Business Requirements documentation covers the reporting requirements per PUC Subst. R. 25.505(d), Projected Assessment of System Adequacy (PASA), and (f), Publication of Resource and Load Information in ERCOT Markets; also confirm how these reports will be provided |  |  | 2008-12-15 | OPEN | 2/24/2009: TAC, or its designee, needs to review the final resolution of updating the Business Requirements and Conceptual System Design documents. NOTE: This TPTF Punchlist entry has been replicated from Line Item #4 in the worksheet named "012909 ScheduleResponses 35" in this workbook.
14 | Requested Diran Obadina to discuss the Data Consistency check Whitepaper at the next NDSWG in February 2009 |  |  | 2009-01-20 | OPEN | 2/24/2009: TAC, or its designee, 1. Will be informed when the white paper is completed to provide TSPs information on model validation for preparations for SEM Go-Live. 2. Will verify that ERCOT does incorporate this White Paper in the SEM Go-Live Procedure document. NOTE: This TPTF Punchlist entry has been replicated from Line Item #5 in the worksheet named "012909 ScheduleResponses 35" in this workbook.
15 | Update the Nodal Protocols to include an MIS Secure Area posting requirement for electrical one-line diagrams for Resource Nodes | No Owner has been assigned to this follow-up item as of 1/27/2009 |  | 2009-01-29 | OPEN | This item requested during the Jan 13 discussion of ERCOT's methodology for EPS Meter placement with loss compensation. It was noted that the posting requirement is reflected in the Procedure for Identifying Resource Nodes as well as in the CRR Map Requirements but is not reflected in MIS Section of Nodal Protocols. On Jan 27, Kenneth Ragsdale confirmed that the posting would be provided.

## 012909 ScheduleResponses 35
This worksheet contains all remaining follow-up items for the new nodal integrated program schedule as identified by MPs and ERCOT during discussions from December 2008 through January 2009. This worksheet was last updated during the final Punchlist audit conducted by TPTF on 2/24/2009.
# | TPTF Date | Action Items | Origin of Action Item | Area | Status | Disposition | TPTF Comments
1 | 2009-01-07 | ERCOT’s telemetry validation process | Action Items from the 1/7/2009 meeting | FIT/Telemetry | OPEN | ERCOT’s Business Process of validating new telemetry when it’s first made available to the ERCOT system needs to be described and implemented. TSPs and other Market Participants should support this new process. 2/24/2009: This issue is being resolved by ERCOT and the Network Data Support Working Group (NDSWG). Once this item is resolved by ERCOT and the NDSWG, TAC, or its designee, needs to determine how much, if any, regression testing needs to be done on the checkout performed on EDS 1 and EDS 2. NOTE: This punchlist entry is replicated as Line Item #9 in the worksheet named "TPTF Punchlist - OPEN Items" in this workbook. | Agreed
2 | 2008-12-15 | Identify the change process to be followed for the Nodal Data Services Master List (NDSML) | Action Items from the 12/08/2008 meeting | Report/Extract | OPEN | ERCOT is considering collective view of comments received and will prepare a response - not applicable for inclusion into the Integration Program Schedule; 2/24/2009: TAC, or its designee, needs to review the final resolution of updating the NDSML. NOTE: This punchlist entry is replicated as Line Item #12 in the worksheet named "TPTF Punchlist - OPEN Items" in this workbook. | Agreed
3 | 2008-12-15 | Discuss the updated change-process flowchart with TPTF (targeted for January 2009) | Action Items from the 12/08/2008 meeting | PMO | OPEN | 2/24/2009: TAC, or its designee, needs to review the process flowchart. NOTE: This punchlist entry is replicated as Line Item #10 in the worksheet named "TPTF Punchlist - OPEN Items" in this workbook. | Agreed
4 | 2008-12-15 | Confirm that recent updates in Business Requirements documentation covers the reporting requirements per PUC Subst. R. 25.505(d), Projected Assessment of System Adequacy (PASA), and (f), Publication of Resource and Load Information in ERCOT Markets; also confirm how these reports will be provided | Action Items from the 12/08/2008 meeting | PMO | OPEN | PMO will bring back the documents to TPTF. 2/24/2009: TAC, or its designee, needs to review the final resolution of updating the Business Requirements and Conceptual System Design documents. NOTE: This punchlist entry is replicated as Line Item #13 in the worksheet named "TPTF Punchlist - OPEN Items" in this workbook. | Agreed
5 | 2009-01-20 | Requested Diran Obadina to discuss the Data Consistency check Whitepaper at the next NDSWG in February 2009 | Action Item from the 1/20/2009 NDSWG meeting | NMMS | OPEN | Agreed, ERCOT will provide resources for discussion 2/24/2009: TAC, or its designee, 1. Will be informed when the white paper is completed to provide TSPs information on model validation for preparations for SEM Go-Live. 2. Will verify that ERCOT does incorporate this White Paper in the SEM Go-Live Procedure document. NOTE: This punchlist entry is replicated as Line Item #14 in the worksheet named "TPTF Punchlist - OPEN Items" in this workbook. | Agreed
6 | 2009-01-07 | Suggestion to remove Planning Model go-live from Nodal schedule |  | NMMS | CLOSED | Confirmed ERCOT is working with SSWG to finalize activities and schedule for Planning Model Go-Live ERCOT will present draft approach to ROS in February and follow it up with a meeting with SSWG to work iteratively on approach for Planning Model Go-Live | Agreed
7 | 2009-01-07 | Add link showing that NMMS and CRR are working together |  | CRR | CLOSED | Will be detailed in the updated CRR handbook | Agreed
8 | 2009-01-07 | How does CRR ownership info get to the 1st DAM. Show task for running an auction or for mocking up the data |  | CRR | CLOSED | ERCOT pursuing option to retrofit previous CRR EDS auction results into the CRR system for Feb/Mar DAM activities. | Agreed
9 | 2009-01-07 | Add milestone to show when COP must be updated continuously |  | SCED/RT/Telem | CLOSED | Detail to be agreed to with ERCOT/MPs in developing handbook for 2010- to be worked with TPTF | Agreed
10 | 2009-01-07 | What is the MP engagement level between full market timeline test and the 168 hour test |  | EDS | CLOSED | Detail to be agreed to with ERCOT/MPs in developing handbook for 2010- to be worked with TPTF | Agreed
11 | 2009-01-07 | Add milestone to show that PUCT and IMM bless the data Clarification. Request for a milestone of the IMM and PUCT Staff confirming their validation of ERCOT nodal data. In other words, there are many data extract requirements by both parties, and much of this we will not seen until several months after the trade day. We want to see milestones reflecting their completion of their data validation. Although there may be no MP view of the data, there should be IMM/PUCT signoff/approval/confirmation that they are comfortable with their test results. |  | IMM | CLOSED | Working with IMM / Beth Garza for IMM and PUCT Schedule being developed with IMM and these milestones have not yet been defined. Once they are defined they will be added to the integrated schedule and identified for inclusion in the MP milestone view. | Agreed
12 | 2009-01-07 | Update SEM Go-Live Document w/ dates | Action Items from the 1/7/2009 meeting | EDS | CLOSED | Detailed dates are to be maintained in the market view of the integrated program schedule. | Agreed
13 | 2009-01-07 | Include MP and ERCOT training timetable into the schedule | Action Items from the 1/7/2009 meeting | Training | CLOSED | Once training activities are aligned with the new schedule the program will provide schedules to the MPs. | Agreed
14 | 2008-12-15 | Maintain a posting of Mr. Anderson's NPRR-tracking spreadsheet on the nodal website and link it to nodal project pages | Action Items from the 12/08/2008 meeting | PMO | CLOSED | NPRR spreadsheet to be posted on website this week 2/24/2009: Being posted weekly at:http://nodal.ercot.com/docs/po/index.html under Nodal Revision Request Status. | Agreed
15 | 2008-12-15 | Confirm the status of “grey boxed” change items (i.e., items to be approved post-go-live or to be prioritized on deferred projects listing) | Action Items from the 12/08/2008 meeting | PMO | CLOSED | 2/24/2009: Joel reports to TPTF that the item is being followed up on at PRS. | Agreed
16 | 2008-12-15 | Review MMS Detailed User Interface (UI) Design with TPTF a- Review any comments received during the TPTF Review ending December 31, 2008 b- Review any remaining wish-list items from the UI Subgroup to discuss whether those items are in scope or out of scope for the MMS UI | Action Items from the 12/08/2008 meeting | PMO | CLOSED | Resolved and will be a TPTF agenda item in the future | Agreed
17 | 2009-01-14 | Show milestone in schedule that shows when the NMMS tool can produce a baseline Annual Planning Model from the NMMS system to meet planning fidelity | Action Items from additional comments received 1/14/2009 | NMMS | CLOSED | ERCOT will work with SSWG to define the activities and schedule | Agreed
18 | 2009-01-14 | Add milestone that shows when we'll evaluate the need for implementing fall back plan for Annual Planning Models | Action Items from additional comments received 1/14/2009 | NMMS | CLOSED | ERCOT will work with SSWG to define the activities and schedule | Agreed

## TPTF Punchlist - CLOSED Items
This worksheet provides a log of TPTF Punchlist items that have been closed since the inception of the Punchlist through the final Punchlist audit conducted by TPTF on 2/24/2009. Please note that several action items from 2/24/2009 have been captured in this worksheet as indicated in red fonts below.
# | Description | Comments | Document that initiated item | Date added | STATUS (closed, open) | Notes
1 | TPTF will discuss the rules for uplifting 1) fixed quantity block offers that are cleared below their offer price and 2) fixed quantity block bids that are cleared above their bid price. | Issue # 26, 110 | DAM & SASM Requirements | 2007-01-25 | CLOSED | Based on TPTF approval of the MMS DAM Business Requirements and Conceptual Design Documents, Mssrs Siddiqi and Spangler felt that further considerations related to this matter were better conducted in the context of the PRS NPRR process rather than under the TPTF charter.
2 | ERCOT will report back to TPTF after analysing the option of changing requirements related to the confirmation of trades to allow both buyer and seller to submit the same trade and ERCOT backend processes will do the "matching" | Issue #11, 49 | DAM & SASM Requirements | 2007-01-25 | CLOSED | Confirmation logic will be changed to support both MPs submitting the same trade and ERCOT background process will manage confirmation. ERCOT to prepare NPRR to clarify confirmation of trades. Discussed on 2/12/07
3 | TPTF needs more time in reviewing the clarification note: "Explanation of Market Submission items.doc" The title in the document is " Explanation of Transaction IDs. Trade IDs, Logic for handling Overlapping ..." 1/8/2007: ERCOT will rework and resubmit for TPTF review this document to capture decisions made on 1/08/2007 TPTF meeting. | Issue # 135,5 | DAM & SASM Requirements | 2007-01-25 | CLOSED | MMS Team working on finalizing this document. As of 07/09/07, MMS Team is updating with vendor and will release the document next week. 2/24/2009: This is part of 2009 integrated project schedule. The document was updated numerous times during 2007, most recently 11/19/07. Current IPS reflects an updated release of this document to occur in 2009 with release of MMS5/EIP1.19.
4 | NPRR for section 6.4.8.2(2) |  | DAM & SASM Requirements | 2007-01-25 | CLOSED | ERCOT MMS Team will draft an NPRR to update table (eliminate 2nd para for X+30 min) for SASM to be in line with the self-provide provisisions and update AS offers described elsewhere in the Nodal protocols text (6.4.8.2.1 (paragraph 1(c) )). Work with Ronnie (GP&L),Shams & Bob Spangler.
5 | Training of scenarios regarding relation of DAM committments into RUC (DAM awards not reflected in COP) |  | RUC Requirements | 2007-01-25 | CLOSED | ERCOT to address and return to TPTF 2/24/2009: Only COP Resources Status is used as input to RUC. QSE can update the COP to reflect the DAM awards. A new NPRR which removed the protocol language corresponding to DAM awards as input to RUC is at CCB now (as discussed in the Jan. 26 -27, 2009 TPTF meeting)
6 | TPTF will discuss the following Settlement Issue: 1) How to calculate of clawback cost for Resources with Output Schedule. | Issue #10 | SCED & RT Requirements | 2007-01-25 | CLOSED | This issue is closed based on TPTF approval of the MMS DAM BusinessRequirements and Conceptual Design Documents as revised during TPTF review.
7 | How is cumulative deployment of Regulation minimized? | Issue #4 | SCED & RT Requirements | 2007-01-25 | CLOSED | Part of the GTBD discussion. General issue resolved 2/5/07 with decision to implement vendor option 4; will be added to EMS requirements. --Confirmed added to EMS requirements discussed at 2/28/07 meeting
8 | Review Generation Subsystem's Resource Limit Calculator |  | SCED & RT Requirements | 2007-01-25 | CLOSED | Resource Limit Calculator is a process that runs under the Generation Subsystem. To be reviewed with EMS requirements document. EMS Requirements approved Mar 1
9 | TPTF will discuss the impact of not distributing Pseudo Resource Dispatch to Resources providing Responsive Reserve |  | SCED & RT Requirements | 2007-01-25 | CLOSED | Pending draft NPRR that will remove the Psuedo Resource. TPTF approved draft NPRR removing the Pseudo Resource on March 7
10 | When viewing MMS approved documents on nodal.ercot.com, some of the filenames of the documents are the same |  | None | 2007-02-07 | CLOSED | Per Patricia Meyer, the filenames has different paths and that is how they are differentiated: http://nodal.ercot.com/docs/pd/mms/pd/osop/Texas%20Nodal%20Market%20Management%20Systems%20%28MMS%29%20Requirement%20Spec.doc http://nodal.ercot.com/docs/pd/mms/pd/scedrt/Texas%20Nodal%20Market%20Management%20Systems%20%28MMS%29%20Requirement%20Spec.doc http://nodal.ercot.com/docs/pd/mms/pd/cct/Texas%20Nodal%20Market%20Management%20Systems%20%28MMS%29%20Requirement%20Spec.doc
11 | More clarity required for "simple outage" | Possibly discuss March 6 or 7? | Outage Scheduler Requirements | 2007-02-12 | CLOSED | See TAC approved definition for simple outage
12 | Conference call needed to discuss confirmation of trades | Sai will send notice to the group | Outage Scheduler Requirements | 2007-02-12 | CLOSED | Closed based on discussion above regarding market submission items documents
13 | All the aforementioned data inputs (specification data, operational data and unit availability) are provided by ERCOT to the wind power production forecasting service for utilization along with their additional meteorological information. The wind-power production forecasting service will strive to produce the most accurate hourly forecast of total ERCOT wind-power production (minimum dispersion of the probability distribution for each hour), The forecast will consist of two components, a probabilistic hourly forecast of the Total ERCOT wind-power production for each of the next 48 hours and distribution factors for each individual WGR for each of the next 48 hours. The cumulative probability distribution table shall consist of at least 20 points from 5% confidence to 95% confidence that the total ERCOT wind-power production will exceed. It shall not be assumed to be a normal distribution. The distribution factors for each WGR shall be that WGRs proportion of the total ERCOT wind power production for that hour. ERCOT shall use the total ERCOT probabilistic forecast and the WGR distribution factors (which shall total to one) to calculate the STWPF and the WGRPP for each WGR. ... | Moved from the IDA Punchlist. This recommendation goes beyond what protocols require and it is not supported further by any specific functional or supplemental requirements. The requirements as written have performance criteria sufficient to require the wind power forecasting service to provide accurate forecast while allowing for flexibility by the service in producing the forecast. It is ERCOT staff opinion that as written the requirements align with the Wind Coalitions comments regarding the forecasting services performance and flexibility requirements. Update requirements to get probability distribution table for forecast generated for each WGR for each hour. TPTF will revisit the proposal from W. Reid. | Wind Power Forecasting | 2007-02-22 | CLOSED | As of 07/09/2007, there is an approved Wind Power Forecasting Requirements 2/24/2009: Action Item: Stacy Bridges is requested to pass ownership of this item to the Renewable Technologies Working Group (RTWG).
14 | Discuss beta testing for EDS 1 when testing complete |  | EDS-1 detailed plan overview | 2007-02-22 | CLOSED | Closed based on EDS 1 workshop presentations
15 | Determine status of companion NPRR to PRR 697, Posting Requirements |  |  | 2007-02-22 | CLOSED | This NPRR is currently being drafted by ERCOT Legal and will be reviewed at the March 22-23 TPTF Became NPRR057
16 | Review changes to MMS Requirements with regard to the TAC/ROS-approved Non-Spin deployment procedure | Deployment message and how it is communicated; same issue with RRS on Load | EMS Requirements (Generation Subsystem) | 2007-02-28 | CLOSED | 2/24/2009: MMS requirements document were updated based on the TAC approved Non-Spin deployment as part of requirements update for B2 changes. TPTF approved the changes.
17 | TSA shall complete all calculations within 25 min for ERCOT system with 100 contingencies. Q: How frequently are the TSA constraints active. A: The TSA constraints become active very rarely. EMS took action item on this topic and will investigate whether or not a NPRR is needed and share the results with TPTF |  | EMS Requirements (NSSA) | 2007-03-01 | CLOSED | EMS Team should follow up with TPTF on status. Will send Al Hirsch a note and cc John Adams. 2/24/2009: The current nodal TSA function is delivered the same as zonal. Some of the differences between nodal requirements and current Implementation are handled in TSA Phase 2 project and rest as gaps and will be addressed in nodal. AREVA currently working on this task. Currently the response time is unknown for 100 contingencies. Once the zonal Phase II project is implemented the response times will be checked. The performance of the TSA will be verified according to the Nodal Schedule test in July, 2010
18 | MMS Requirements to be revisted to verify incorporated on GS-FR23 from the EMS Generation Subsystem Requirements |  | EMS Requirements (Gen Subsystem) | 2007-03-01 | CLOSED | GS-FR23 - Related to adjustment of HASLs after deployment of Non Spin (v0.9) Refer to EMS Generation Subsystem Requirement GS-FR25 Confirm with Baseline 2 MMS requirements 2/24/2009: When Non-Spin is deployed, RLC will calculate the new HASL & HDL based on the QSE’s updated telemetered Non-Spin Schedule. SCED uses the limits calculated by RLC. The latest GSS requirements are scheduled to be reviewed with TPTF. We believe there are no pending issues in this item.
19 | Include validation rules for the start-state and end-state as an active part of an EDS Handbook. | Should this be documented by the MMS Team? | EDS SCED MP Handbook | 2007-06-27 | CLOSED | As of 07/09/2007, has not been updated Request clarification of what is needed 2/24/2009: TPTF required the inclusion of entry and exit criteria in each of the approved EDS Handbooks.
20 | ERCOT investigate the possibility of adjusting the format of the trade submissions to improve updates without necessary cancellations when net buyer becomes net seller. |  |  | 2007-07-09 | CLOSED | 2/24/2009: Current trade submission needs to be cancelled when changing from net buyer to net seller or vice versa. No changes will be made to the ERCOT design.
21 | Need to confirm that buyer and seller can be the same entity with a switch indicating whether it’s a net buy or sell. Need to understand how confirms work for this also. |  |  | 2007-07-09 | CLOSED | Stacy will contact Al Hirsch for confirmation 2/24/2009: Current trade submission needs to be cancelled when changing from net buyer to net seller or vice versa Additionally described in the Market Submission items paper for DSR: Each QSE representing a DSR will submit by the end of the Adjustment Period an Energy Trade where the QSE is both the buyer and the seller to indicate the net Energy Trades, DAM awards and Energy from the QSE’s non-DSR Generation Resources used to meet the QSE’s Load as well as any Energy Trade or DAM award that is satisfied by energy from the DSR Resources. These DSR trades are automatically confirmed as soon as they are validated (i.e. there is no matching that takes place). A Sale/Purchase flag will specify whether the trade is a net energy sale or a net energy purchase. The net energy sold of X MW indicates that the DSR has to generate X MW in addition to the corresponding DSR Load. The net energy purchase of Y MW indicates that the QSE is purchasing Y MW so that the DSR has to generate Y MW less than the corresponding DSR Load.
22 | ERCOT to return to TPTF with proposal for validating DSR output schedules including PCRR with refund validation. |  |  | 2007-07-09 | CLOSED | See Resmi and Kenneth Ragsdale 2/24/2009: This was presented in TPTF on 072307 and was closed. NPRR 134 (Section 7 cleanup) was approved by the Board on November 17, 2008. This NPRR included revisions to the sections that describe how to determine the “quantity” for the PTP Obligations and Options with Refunds when an Output Schedule is submitted. Sections with changes included the following: 7.9.1.5, Payments and Charges for PTP Obligations with Refund Settled in DAM 7.9.1.6, Payments for PTP Options with Refund Settled in DAM 7.9.2.3, Payments for NOIE PTP Options with Refund Settled in Real-Time 7.9.2.5, Payments and Charges for PTP Obligations with Refund in Real-Time
23 | Need update from EDS Team on plan for publishing validation rules for various phases of EDS 3 |  |  | 2007-07-09 | CLOSED | 2/24/2009: Included in Market Submission whitepaper v0.25 and will continue to be updated according to Project Schedule June 2009.
24 | ERCOT Legal to confirm NDA process in email to TPTF exploder | Chad Seely |  | 2007-07-09 | CLOSED | This was addressed. 2/24/2009: ERCOT provided standard NDA.
25 | Ask ERCOT for a decision on the possibility of converting zonal RTUs to a zonal ICCP and using that in nodal |  |  | 2007-07-09 | CLOSED | 2/24/2009: ERCOT is moving forward with zonal OGRR proposal to allow QSE ICCP switchover from RTUs prior to nodal go-live. Discussed at Feb 2009 QSEPMWG and NDSWG meetings. Action Item: Stacy Bridges is requested to pass ownership of this item to ROS.
26 | ERCOT to discuss how Quality Center is being used in testing and traceability |  | Discussion of INT testing | 2007-07-11 | CLOSED | 2/24/2009: Quality center reports are available on Nodal.ERCOT.com. This falls under the responsibility of the Executive Project Director.
27 | ERCOT to elaborate method for assigning appropriate Hub prices when DAM is executed but specific DAM SPP is not available |  | CMM CSD | 2007-07-11 | CLOSED | ERCOT does not believe this is an issue- if there is a de-energized bus it will be assigned an average SPP for energized busses at same voltage level , but it will not be included in the Hub price calculation. 2/24/2009: ERCOT to provide WMS with information on what happens to price postings if DAM is not executed.
28 | ERCOT to discuss who is leading Nodal Program in identifying Electrical Buses for Settlements | Settlements/ NMMS |  | 2007-07-11 | CLOSED | 2/24/2009: “Procedure for Identifying Resource Nodes” was endorsed by the WMS on 08-20-08. The document can be found at: http://nodal.ercot.com/mktrules/np/Procedure_for_Identifying_Resource_Nodes-082008_Nodal1.doc
29 | Discuss whether Offer validations in DAM should be based upon HRL/LRL rather than HSL/LSL | To be added as a discussion item to a future TPTF agenda |  | 2007-10-19 | CLOSED | This Punch List item arose during the discussion of the MMS DAM and SASM Requirements at the Oct.8-9 TPTF Meeting. Discussion recommendation from Shams Siddiqi. 2/24/2009: Energy Offer is not validated against HRL/LRL or HSL/LSL Currently, COP submission validation will check against HRL/LRL. There is no capacity validation for other resource specific offers/bids. In DAM clearing, all HSL/LSL will be used as resource constraints.
30 | Discuss options for linking AS Offers to Energy Offers in the DAM co-optimization following MMS discussions with vendor | S. Moorty and MMS team to follow up. |  | 2007-10-19 | CLOSED | This Punch List item arose during the discussion of the MMS CCT Requirements at the Oct.8-9 TPTF Meeting. 2/24/2009: This is implemented in Baseline 2 MMS requirements.
31 | Develop a business process for DAM execution (i.e., provisions for equipment failure, invalid submission items, aborted executions, etc.) | S. Moorty and MMS team to follow up. |  | 2007-10-19 | CLOSED | This Punch List item arose during the discussion of the MMS DAM and SASM Requirements at the Oct.8-9 TPTF Meeting. DAM business process has been developed and presented to TPTF. 2/24/2009: To be included in the Business Process review. TPTF has begun reviews of the ERCOT Business Procedures. The ERCOT Nodal Project Manager supporting this activity has brought to TPTF the Level 1 and Level 2 documents describing ERCOT’s Business Procedures. Levels 3 and 4 are currently under development and TPTF has been requested to review these documents and provide comments as they become available. ERCOT has presented TPTF with draft procedures for the DAM and the Reliability Unit Commitment (RUC) Market Operations and made updates with TPTF comments. TPTF Recommendation: TAC, or its designee, should review the Levels 3 and 4 Business Procedure documents as they are developed by the ERCOT Nodal Project Manager and provide comments for ERCOT consideration.
32 | If the number of switchable WGRs or the frequency of their switching activity indicates the need for a future solution that is more robust than what can be accommodated via the COP or the Outage Scheduler, then ERCOT may need to revisit the Reliability Unit Commitment (RUC) capacity credit in Settlements and other potential issues. |  |  | 2008-08-08 | CLOSED | This Punch List item arose during the July 21 while TPTF was preparing a statement to send to TAC to close an action item regarding future potential issues for switchable WGRs. 2/24/2009: Action Item: Stacy Bridges is requested to pass this item to RTWG for inclusion in their issues list. The issue is if a QSE with wind generation is given an 80% probability of exceedence of its WGRPP as RUC capacity credit, then switches outside of ERCOT, does the settlement formula for RUC properly account for this action.
33 | ERCOT should stipulate that switchable WGRs need to be reflected in the Resource Asset Registration Form (RARF) information that is requested of WGRs. |  |  | 2008-08-08 | CLOSED | This Punch List item arose during the July 21 while TPTF was preparing a statement to send to TAC to close an action item regarding future potential issues for switchable WGRs. 2/24/2009: Action Item: Stacy Bridges is requested to pass this item to the RTWG.
34 | There is a question as to whether the WGR provision is sufficient in Nodal Protocol Section 16.5.4, Maintaining and Updating Resource Entity Information, paragraph (2), which states, "If a Resource Entity has a Switchable Generation Resource with a requirement in a non-ERCOT Control Area for the months of July through August ('Peak Period'), it shall report to ERCOT in writing, annually by April 1, the days that the identified capacity will not be available to the ERCOT System during the Peak Period." |  |  | 2008-08-08 | CLOSED | This Punch List item arose during the July 21 while TPTF was preparing a statement to send to TAC to close an action item regarding future potential issues for switchable WGRs. 2/242009: Action Item: Stacy Bridges is requested to pass this item to the RTWG and request that they consider this item in their Training Issues list.
35 | DC Ties and Controllable Load Resources providing AS | Joel Firestone agreed to conference with Brett, Richard and Shams to discuss issues |  | 2007-02-23 | CLOSED | Carrie will check with Firestone to see if this is an open issue; Shams says there may be a conflict between ERCOT Protocols allowing DC Ties to provide AS and NERC not allowing. 2/24/2009: Based on the discussions at TPTF, Nodal Protocol will not be updated. The following decisions were made. - CLRs will be able to provide Ancillary Service. - Ancillary Service will not be provided from DC ties. This is added as an assumption in all MMS requirements documents.

## 07092007 CMM Punch Tab
This worksheet contains all of the modified spreadsheet items from the TPTF discussion of the updated CMM Requirements and CSD on July 9, 2007. These items were identified as follow-up items associated with the approving vote for the CMM Requirements v1.2 and the CMM CSD v1.2 as documented in the 070907 TPTF Meeting Minutes.
CMM Punch Tab: COMS Credit Monitoring and Management Conceptual System Design
Issuing Entity | Section | Description | Accepted /Rejected /Response | Reviewer | Comment
Reliant | n/a | Note that all assumptions for credit for CRRs hold for PCRRs as well. Under Protocols 7.1(2) PCRRs and MCFRIs are a subset of CRRs. Please confirm that the use of CRR in this document and other credit document includes the treatment of PCRRs and MCFRIs. A global statement to this effect should be made here and the systems should recognize and import/calculate with the PCRR/MCFRI data as well. | accepted, multiple occurrence | ERCOT | CMM gets the CRR owned by the CRR owner from the CRR system. If the CRR ownership should include PCRR as well as MCFRI, they will be defined so in the integration interfaces.
Reliant | 1.6, page 9 | they are time weighted averages | response | ERCOT | yes. Will be covered in the detailed design, including block or rolling.
Reliant | 2.19.5.1, page 47 | what will ERCOT credit do with the messages? Will action be taken? | response, will further address in operating procedures | ERCOT | These messages are informatioal to provide early warning so that ERCOT could analyze credit risks to the whole market or specific Counter-Parties. Please refer to Protocols 16.11.4.1 (3). Version 1.0 of the requirements was presented to CWG and approved by them. If there are any specific concerns, please specify them to be addressed.
CMM Punch Tab: COMS Credit Monitoring and Management Requirements Specification
Issuing Entity | Section | Description | Accepted /Rejected /Response | Reviewer | Comment
Reliant | 2.3.7 | [Reliant: if this state impacts a Market Participant’s ability to transact in ERCOT markets, the Participant should be notified AND consideration should be provided for how to accommodate their participation in the interim until ERCOT gets its systems working.] | response, will further address in operating procedures | ERCOT | This is part of a mostly manual business process to notify the impacted MP and obtain necessary info in a timely manner. Please refer to Alternative Scenario 2.
Reliant | 2.3.8 | [Reliant: what does this mean? Adjusted to account for specific conditions? If so, such conditions should be described.] | response, will further address in operating procedures | ERCOT | The unsecured credit limits are reviewed and modified if needed as per ERCOT creditworthiness standards.
Reliant | 2.4.14 | [Reliant: same comment as above. What is the equation for calculating this?] | response, will further address in operating procedures | ERCOT | This will be addressed in detailed design.
Reliant | 2.4.15 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.15 | [Reliant: What would determine the need? Is this a work around for system failure or does it mean ‘adjustment as analyst sees fit?’ This not allowed for under the Protocols 16.11.4.3.] | pending operatiing procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation, if needed. Please refer to Protocols section 16.11.4.1.(3)
Reliant | 2.4.16 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] The Credit Anlayst may adjust the RTL component as needed to reflect business conditions | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.17 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.18 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.23 | [Reliant: what does this mean? Adjustment up or down on what basis? Details require documentation.] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.23 | [Reliant: what is envisioned here? Say that there is a price that exceeds a defined parameter. What would be done that isn’t captured in the credit processes already? Would you run calculations earlier? Look at certain counterparties? Where will these business processes be defined? Recommend that they be discussed with CWG.] | response, will further address in operating procedures | ERCOT | These messages are informational to provide early warning so that ERCOT could analyze credit risks to the whole market or specific Counter-Parties. Please refer to Protocols 16.11.4.1 (3). Version 1.0 of the requirments was presented to CWG and approved by them. If there are any specific concerns, please specify them to be addressed.
Reliant | 2.4.4 | [Reliant: what does this mean? Adjustment up or down on what basis?] | response, will further address in operating procedures | ERCOT | Adjustments are intended for correcting errors or to entered based on manual calculation if needed.
Reliant | 2.4.5 | [is interface anticipated in either or both of these systems?] | response, will further address in operating procedures | ERCOT | Programmatic interfaces with both of these systems will be deployed.
Reliant | 2.4.5 | [Reliant: Would be useful to discuss how the ‘appropriate’ Hub prices will be determined.] | Response, Nodal needs to clarify this further | ERCOT | This will be addressed in detailed design.
Reliant | 2.4.6 | [Reliant: Would be useful to discuss how the ‘appropriate’ Hub prices will be determined.] | Response, Nodal needs to clarify this further | ERCOT | This will be addressed in detailed design.