## Market Design
Attachment A
Detailed List of Issues
Market Design (MD)
February 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other REF No. | Action Date
MD | 1 | Ancillary Services Cost Allocations applicable to Wind | TAC | Near Term |  | The ERCOT Board requested TAC provide more detail related to their recommendation to not do any special Ancillary Services cost allocations applicable to Wind. |  | TAC to make recommendation to BOD in January
MD | 2 | Ancillary Services Procurement Optimization for 2009 | QMWG | Near Term |  | Concept has been endorsed by TAC; written procedure to be developed by ERCOT Operations for approval
MD | 3 | Non-Spin requirements | PERTF | Near Term |  | Under discussion at PERTF
MD | 4 | Consideration of new ancillary service products in order to support reliability needs | ROS | Long Term |  | Eric Goff had developed a list of questions to be discussed at the Feb. 20 RTWG meeting |  | Circulated prior to Feb meeting
MD | 5 | Storage technologies benefits (e.g., flywheels) to the integration of wind and provision of necessary ancillary services (regulation, responsive reserves) | RTWG | Long Term |  | Steve Isser will bring white paper to RTWG; |  | Presented at Jan 29 meeting
MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF | Complete | ERCOT Procedure | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 7 | Investigate whether any Nodal Protocol changes are necessary to allow wind resources to provide ancillary services | ROS | Undetermined | PRR | Walter Reid will develop list of questions to be developed into a white paper. |  | Circulated prior to Jan 29 meeting
MD | 8 | Review of current Protocol to ensure requirements are applicable to all technologies re: reactive and voltage requirements | WOTF | Near Term | PRR | Docket 36482 open at PUCT. Future actions will be determined by the results of the proceeding. | WOTF 1a
MD | 9 | Review Nodal Protocols for proper treatment of wind generation re: dispatch response | TPTF | Near Term | NPRR | List of questions has been developed and a white paper with options will be prepared for TPTF. | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 10 | Review Nodal Protocols for proper treatment of wind generation re: performance metrics with negative pricing | TPTF | Near Term | NPRR | White paper with options will presented to TPTF | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 11 | Review Nodal Protocols for proper treatment of wind generation re: base point deviaton charges as applicable to wind generation | TPTF | Near Term | NPRR | White paper with options will presented to TPTF | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 12 | WGR LSL as % of HSL | QMWG | Complete | PRR 773 | COMPLETE | WOTF 2a
MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans | N/A | Complete | PRR 763 | COMPLETE | WOTF 3b

## System Ops
Attachment A
Detailed List of Issues
System Operations (SO)
February 2009
Issue Category | System Ops Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information | WOTF | Near Term | ERCOT Forms | Assigned to WOTF Modeling Subgroup. Currently being reviewed | WOTF 1d
SO | 2 | Identifying nodal tools to more effectively integrate wind into the grid | RTWG | Undetermined |  | Reviewed at January 29 RTWG meeting through Floyd Trefny's presentation; next steps pending.
SO | 3 | Response to down balancing instructions (QMWG); SCE issues, clarity on expected following instructions, requirements | QMWG | Near Term |  | Being worked on currently by QMWG
SO | 4 | Smart grid implications on market design and integration of renewable resources | RTWG | Long Term |  | Eric Goff and Steve Isser will develop a white paper
SO | 5 | Operational studies re: Wind (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Walter Reid to develop a white paper to be presented to RTWG in March
SO | 6 | Qualification testing of reactive capability for wind generation | ERCOT Operations | Near Term | OGRR | ERCOT Operations is drafting OGRR because the current procedure is inadequate
SO | 7 | High frequency: Develop alternate solutions | WOTF | Near Term |  | WOTF currently reviewing 4 possible solutions. Walter Reid will submit white paper. | WOTF 5
SO | 8 | System intertia capability of wind generators | PDCWG | Long Term |  | Mark Garrett to ask ROS for status update | WOTF 1e
SO | 9 | Better defined SCADA control of generation breakers | OGRR TF | Near Term | OGRR | Draft OGRR will be discussed at OGRTF | WOTF 1b
SO | 10 | ERCOT/TSP/Generator voltage management practices | WOTF | Near Term |  | Revisit this issue at the next WOTF meeting. | WOTF 1c
SO | 11 | Protocols, Operating Guides, Interconnection Procedure and the Interconnection Agreement need to be updated to make requirements less ambiguous and more generic to include all types of generation | ROS | Near Term | PRR, OGRR, ERCOT Procedures and Agreements | Currently focusing on reactive issues; a draft of a reactive requirements concept paper has been prepared and distributed to a small group for review
SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs | N/A | Complete | OGRR 208 | COMPLETE
SO | 13 | Performance metrics for wind | QMWG | Near Term | PRR 793 (Urgent) | PRR793 approved by TAC at the February TAC meeting. Add'l PRRs to be developed QMWG.
SO | 14 | What can we do to identify upcoming transmission outages and what can we do to minimize outage times and impact to wind power production? | CMWG | Long Term |  | PRR 795 was approved by TAC at the February TAC meeting. Nodal market software will better address this issue. | WOTF 3e
SO | 15 | 24/7 communication must be available for TSP to reach wind generators. | WOTF | Near Term | OGRR | Draft OGRR will be discussed at OGRTF | WOTF 2a
SO | 16 | Wind generation ramp rate limitations | ROS | Complete | PRR 771, PRR 788 | PRR 771 is APPROVED and PRR 788 approved by TAC | WOTF 3a
SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | Complete | ERCOT Procedures | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3b
SO | 19 | Run multiple CSC limit studies | WOTF | Complete | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3f
SO | 20 | Dynamic line ratings | WOTF | Complete | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3g
SO | 21 | Reexamine EECP Steps | OWG | Complete | PRR 769 NPRR 142 | COMPLETE: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting | WOTF 3h
SO | 23 | Integrating advanced meters and other demand response into the existing and Nodal Ancillary Service markets | DSWG | Long Term |  | RTWG recommends that this be a 2009 Goal for WMS
SO | 24 | Long term solutions for advanced meter settlement; incuding, impact of plug-in hybrid vehicles on storage and use of renewable resources. | AMIT | Long Term |  | Complete work suggested by EDS B&V study
SO | 25 | Governor Generator Response of wind generators | WOTF | Undetermined |  | Under active discussion at WOTF; a draft PRR will be prepared | WOTF 1e
SO | 26 | Operational studies: Solar (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Steve Isser to develop a white paper to be presented to RTWG in April
SO | 27 | ERCOT Operations is currently analyzing and deploying all wind generation local curtailment manually - what, if any, problems is this causing? | CMWG | Near Term |  | COMPLETE: ERCOT Operations discussed this issue extensively at February CMWG; no reasonable, timely or cost-effective solution is available in the existing zonal market, issue is resolved by the Nodal market design.
SO | 28 | Resources tripping due to Base Case (N-0) SPS | CMWG | Near Term |  | John Dumas is planning to prepare an OGRR to address this issue
SO | 29 | Transmission outage planning related to CREZ line construction outages | RPG | Near Term |  | The issue will be discussed at the next RPG meeting (CREZ-related).
SO | 30 | Use of wind generation output forecast for the purposes of the Projected Assessment of System Adequacy (PASA) | ERCOT Operations | Near Term |  | To be discussed at March RTWG meeting

## System Planning
Attachment A
Detailed List of Issues
System Planning (SP)
February 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref. No.
SP | 1 | Verify technical data (installed technology) | ERCOT Operations | Near Term | ERCOT Survey | COMPLETE: ERCOT to report on status at January 30 WOTF meeting
SP | 2 | Verify computer models for wind generation | ERCOT Planning | Near Term |  | Included in ERCOT's LVRT Study
SP | 3 | Fault Tolerance Studies (OGRR208) | ERCOT Planning | Near Term | OGRR | Included in ERCOT's LVRT Study
SP | 4 | Updated Voltage Transient and Small Signal Stability Study (West to North Transfer Study) | ERCOT Operations | Near Term |  | Limit study is underway; the design study is still under discussion at RPG
SP | 5 | Inertia Study | ERCOT Planning | Long Term |  | Will be undertaken following completion of LVRT study
SP | 6 | Use of VFTs to solve stability problems | RTWG | Long Term |  | Walter Reid/Paul Hassink to develop white paper
SP | 7 | Voltage Swing Management (Voltage Control Process) | ERCOT Planning | Long Term |  | Issue to be discussed at February RPG meeting (CREZ-design coordination issue)
SP | 8 | Low Voltage Ride Through Study | ERCOT Planning | Near Term |  | All study results due to ROS no later than June 2010

## WT
Attachment A
Detailed List of Issues
Workshop/Training Opportunities (WT)
February 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Status | Other Ref. No.
WT | 1 | WGR QSE Resource Plan and Energy Schedule Update Process | RTWG/ERCOT Operations | Undetermined | Included with Workshop III
WT | 2 | ERCOT Wind Workshop III - Spring 2009 | RTWG/ERCOT Operations | Near Term | ERCOT Operations to develop draft outline
WT | 3 | WGR Operator Training | RTWG/ERCOT Operations | Long Term | Ask ERCOT training to discuss with RTWG
WT | 4 | Wind in the Nodal Market | RTWG/ERCOT Operations | Near Term | Include in Wind Workshop III