|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for February 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 261 active generation interconnection requests totaling over 101,000 MW. This includes almost 50,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $772 Million - Transmission Projects approved in 2009 total $ 41 Million - All projects (in engineering, routing, licensing and construction) totals approximately $4.1 Billion - Transmission Projects energized in 2008 total about $453 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements       	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4	Potential Future Generation Interconnections	2

1.5	Potential Future Generation Projects Undergoing Full Interconnection Studies	5

1.6	Wind Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Other Notable Activities	8

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations  - none for February 2009

## New Generation Interconnection Agreements

## Senate Wind (08INR0011)  - 150 MW in Jack County

## Pearsall Expansion (09INR0079) -  200 MW in Frio County  (NOIE, Public Letter in lieu of SGIA)

## Lenorah Wind (08INR0040) - 251 MW in Martin County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 261 active generation interconnection or change requests |  |  |  |  |
| As of February 28, 2009 | North | South | West | Total |
| Security Screening Study | 5 | 9 | 9 | 24 |
| SSS Completed | 3 | 11 | 35 | 49 |
| Full Interconnect Study | 33 | 36 | 79 | 148 |
| FIS Completed | 2 | 10 | 1 | 13 |
| Interconnect Agreement Completed | 8 | 9 | 10 | 27 |
| Capacity under Interconnection Agreements | 5,458 | 2,778 | 1,513 | 9,749 |
| Capacity for Grid, MW | 23,931 | 36,653 | 40,539 | 101,123 |
| Wind Capacity, MW | 2,450 | 9,780 | 37,526 | 49,756 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC | - | - | 5,229 | 5,229 |
| Gas-CT | - | - | 705 | 705 |
| Total Gas | 3,083 | 18,170 | 5,934 | 27,187 |
| Nuclear | 0 | 3,200 | 9,186 | 12,386 |
| Coal | 2,050 | 1,945 | 4,131 | 8,126 |
| Wind | 13,611 | 29,051 | 7,094 | 49,756 |
| Solar | 1,043 | 0 | 0 | 1,043 |
| Biomass | 0 | 50 | 145 | 195 |
| Other | 950 | 1,480 |  | 2,430 |
| Grand Total | 20,737 | 53,896 | 26,490 | 101,123 |

## 1.4  Potential Future Generation Interconnections

The table below summarizes the publicly known potential future generation projects for the ERCOT region.  (IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Future Generation Interconnections as of February 28, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 07INR0027 | S Houston Green Power Exp | IA | Galveston | South | Apr-09 | Gas-CC | 244 |  |
| 07INR0028b | Goat Wind - phase 2 | IA | Sterling | West | Apr-09 | Wind | 70 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-09 | Wind | 225 |  |
| 08INR0003 | Sandow 5 | IA | Milam | North | Apr-09 | Coal | 581 | date |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 | new |
| 08INR0012 | Papalote Creek Wind Farm | IA | San Patricio | South | May-09 | Wind | 180 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Oct-09 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 | date |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 08INR0035 | Cedar Bayou 4 | IA | Chambers | South | Jun-09 | Gas-CC | 539 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 | date/mw |
| 08INR0046 | Bosque Expansion | IA | Bosque | North | Mar-09 | Gas-CC | 255 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-09 | Wind | 465 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Jul-09 | Coal | 855 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | Jan-10 | Coal | 855 |  |
| 09INR0007 | Nacogdoches Project | PL | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0026 | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 300 | date |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 | date |
| 09INR0027 | Winchester Power Park | IA | Fayette | South | Jun-09 | Gas-CT | 178 | date |
| 09INR0028 | V H Braunig 6 | PL | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 327 |  |
| 09INR0045 | Sand Hill Peakers | PL | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Dec-09 | Wind | 251 |  |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | May-09 | Wind | 141 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Apr-09 | Gas-CT | 48 |  |
| 09INR0079 | Pearsall Expansion | IA | Frio | South | Aug-09 | Gas-CT | 200 | new |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0025 | Mont Belvieu | IA | Chambers | South | Apr-09 | Gas-CT | 0 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
|  |  |  |  |  |  |  | 26,490 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Potential Future Generation Projects Undergoing Full Interconnection Studies

| Project | County | Capacity (MW) | COD | Fuel |  | Project | County | Capacity (MW) | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0009 | Jack | 150 | TBD | Wind |  | 08INR0044 | Concho | 200 | TBD | Wind |
| 08INR0062 | Archer | 249 | TBD | Wind |  | 08INR0061 | Hardeman | 200 | TBD | Wind |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 08INR0020 | Eastland | 200 | TBD | Wind |
| 06INR0022c | Kenedy | 200 | TBD | Wind |  | 09INR0064 | Borden | 41 | TBD | Wind |
| 08INR0042 | Coke | 200 | TBD | Wind |  | 08INR0041 | Coke | 200 | TBD | Wind |
| 09INR0063 | Nueces | 289 | Apr-09 | Gas |  | 08INR0060 | Hidalgo | 279 | Apr-09 | Gas |
| 09INR0005 | Calhoun | 280 | Apr-09 | Other |  | 09INR0059 | Freestone | 20 | May-09 | Coal |
| 08INR0014 | Webb | 183 | May-09 | Wind |  | 07INR0026 | Baylor | 400 | May-09 | Wind |
| 08INR0005 | Wise | 400 | Jun-09 | Gas |  | 09INR0025 | Concho | 180 | Jun-09 | Wind |
| 09INR0044 | Coke | 60 | Sep-09 | Wind |  | 10INR0027 | Nueces | 35 | Oct-09 | Wind |
| 10INR0026 | Tom Green | 186 | Oct-09 | Wind |  | 09INR0075 | Kinney | 248 | Oct-09 | Wind |
| 09INR0055 | McCulloch | 299 | Oct-09 | Wind |  | 09INR0041 | Mitchell | 300 | Oct-09 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-09 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-09 | Wind |
| 09INR0048 | Jack | 150 | Oct-09 | Wind |  | 08INR0054 | Comanche | 401 | Oct-09 | Wind |
| 11INR0015 | Concho | 249 | Nov-09 | Wind |  | 09INR0073 | Scurry | 200 | Nov-09 | Wind |
| 08INR0031 | Childress | 100 | Nov-09 | Wind |  | 09INR0029 | Calhoun | 263 | Dec-09 | Coal |
| 11INR0013 | Mills | 150 | Dec-09 | Wind |  | 11INR0012 | Duval | 400 | Dec-09 | Wind |
| 09INR0082 | Webb | 300 | Dec-09 | Wind |  | 09INR0065 | Webb | 150 | Dec-09 | Wind |
| 09INR0061 | Kent | 258 | Dec-09 | Wind |  | 09INR0058 | Howard | 250 | Dec-09 | Wind |
| 09INR0054 | Stonewall | 149 | Dec-09 | Wind |  | 09INR0051 | Borden | 249 | Dec-09 | Wind |
| 08INR0056 | Nolan | 149 | Dec-09 | Wind |  | 08INR0039 | Hamilton | 90 | Dec-09 | Wind |
| 08INR0023 | Floyd | 100 | Dec-09 | Wind |  | 08INR0022 | Floyd | 100 | Dec-09 | Wind |
| 07INR0008 | Howard | 35 | Dec-09 | Wind |  | 10INR0011 | Johnson | 275 | Jan-10 | Gas |
| 11INR0036a | Matagorda | 200 | Jan-10 | Wind |  | 11INR0033a | Cameron | 200 | Jan-10 | Wind |
| 10INR0048 | Hardeman | 1,000 | Jan-10 | Wind |  | 10INR0047 | Kendall | 1,000 | Jan-10 | Wind |
| 11INR0014 | Harris | 50 | Feb-10 | Gas |  | 10INR0022 | Harris | 3,500 | Mar-10 | Gas |
| 10INR0018 | Madison | 550 | Mar-10 | Gas |  | 09INR0062 | Brown | 140 | Mar-10 | Wind |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |  | 10INR0045 | Webb | 734 | Apr-10 | Wind |
| 10INR0017 | Chambers | 685 | May-10 | Gas |  | 10INR0079 | Nolan | 60 | May-10 | Wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 10INR0023 | Haskell | 386 | May-10 | Wind |
| 10INR0016 | Childress | 150 | May-10 | Wind |  | 09INR0070 | Reagan | 42 | May-10 | Wind |
| 09INR0069 | Reagan | 36 | May-10 | Wind |  | 09INR0035 | Concho | 750 | May-10 | Wind |
| 09INR0018 | Concho | 249 | May-10 | Wind |  | 07INR0032 | Tom Green | 249 | May-10 | Wind |
| 10INR0069 | Rusk | 818 | May-10 | Coal |  | 10INR0076 | Webb | 225 | May-10 | Wind |
| 09INR0081 | Rusk | 818 | Jun-10 | Coal |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0052a | Knox | 21 | Jul-10 | Wind |  | 10INR0013 | Upton | 400 | Jul-10 | Wind |
| 10INR0038 | Glasscock | 350 | Aug-10 | Wind |  | 10INR0071 | Matagorda | 88 | Sep-10 | Wind |
| 10INR0015 | Mitchell | 350 | Oct-10 | Wind |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 10INR0070 | Hunt | 50 | Nov-10 | Gas |  | 10INR0039 | Dickens | 200 | Nov-10 | Wind |
| 10INR0032 | Navarro | 800 | Dec-10 | Gas |  | 09INR0031 | Ector | 275 | Dec-10 | Gas |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0060 | Willacy | 401 | Dec-10 | Wind |
| 10INR0059 | Zapata | 251 | Dec-10 | Wind |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0049 | Pecos | 200 | Dec-10 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 10INR0033 | Armstrong | 420 | Dec-10 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 07INR0017 | Erath | 210 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 11INR0036b | Matagorda | 200 | Jan-11 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 11INR0037 | Smith | 55 | May-11 | Biomass |  | 11INR0046 | Brazoria | 300 | May-11 | Gas |
| 11INR0028 | Grimes | 1,280 | May-11 | Gas |  | 10INR0009 | Castro | 200 | May-11 | Wind |
| 11INR0009 | Navarro | 1,200 | Jun-11 | Gas |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 11INR0022 | Tom Green | 200 | Jun-11 | Wind |  | 11INR0021 | Tom Green | 200 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 06INR0041 | Newton | 1,160 | Jul-11 | Gas |  | 11INR0040 | freestone | 749 | Aug-11 | Gas |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0008a | Roberts | 1,000 | Sep-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 09INR0016 | Yoakum | 680 | Nov-11 | Gas |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 06INR0022d | Kenedy | 200 | Dec-11 | Wind |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 12INR0020 | Wharton | 660 | Jun-12 | Gas |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 12INR0016 | Nueces | 1,200 | Nov-12 | Other |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 08INR0019b | Gray | 250 | Nov-12 | Wind |
| 08INR0019a | Gray | 250 | Nov-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 11INR0023 | King | 400 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 06INR0022b | Kenedy | 200 | Dec-12 | Wind |  | 12INR0009 | Nueces | 875 | May-13 | Gas |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 15INR0003 | Matagorda | 3,200 | Jan-15 | Nuclear |

## Wind Generation

Wind Capacity Installed by Year					County Location of Installed Capacity and Interconnection Requests

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  This project is in ERCOT Independent Review.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. This project is in ERCOT Independent Review.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Oncor submitted a project to add a 138/69 kV autotransformer at Stanton East into the Spraberry to Big Spring 69 kV line and rebuild the 138 kV line from Stanton East to Big Spring Switch.  This project will cost $15 M with an estimated completion date no earlier than summer 2011.  The review of this project is complete and a RPG Acceptance Letter is being prepared.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

- Austin Energy submitted a project to relocate the Decker to Techridge circuit to new ROW so that the existing structures can be utilized for the new Gilleland to Techridge circuit.  The estimated completion date of this project is November 2010 and estimated cost is $ 4.3 M.   This project is in study period.

# The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to construct a new 6.2 mile transmission line from Highway 123 to Cushman substation.  The estimated completion date of this project is June 2014 and estimated cost is $ 11.6 M.   This project is in the comment period.

# The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to upgrade and convert a 27.7 mile Flatonia-Moulton-Henkhaus-Shiner-Yoakum Gartner Road 69 kV transmission line to 138 kV.  The estimated completion date of this project is June 2011 and estimated cost is $ 18.6 M.   This project is in the comment period.

# The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to construct a new 7.8 mile transmission line between the existing GPI and Parkway substations.  The estimated completion date of this project is June 2013 and estimated cost is $ 12.9 M.   This project is in the comment period

# Other Notable Activities

- All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT Regional Planning has begun work on the 2009 Five-Year Transmission Plan utilizing the latest SSWG base cases.  This work is in the conditioning phase where projects in the base cases requiring RPG review that have not undergone that review are removed.  These projects have been identified and submitted to Transmission Owners for their review and creation of IDEV’s to remove the projects from the base cases.  Responses have been received from most transmission owner but a couple is still outstanding.

- Completed initial RMR determination on Luminant Notice of Suspension of Operations (NSO) submission and released 12 units.  Conducting further study before making final determination on three other units.  Studies are also underway for initial determination on three units for which NSO was received from CPS Energy

- The Annual Load Data Request (ALDR) training was held on January 21, 2009.

- ERCOT TPIT report for 2009 first quarter was posted on March 2, 2009. A new column to identify the Planning Charter Tier has been added to TPIT. This column also identifies CREZ and CREZ modified projects.