## Slide 1: TPTF Final Report To TAC
Randy Jones on Behalf of the Transition Plan Task Force (TPTF)
February 24, 2009

## Slide 2: Introduction
As requested by the TAC the Transition Plan Task Force (TPTF) prepared a final report on the status of those tasks and responsibilities previously assigned by TAC to the TPTF in the:
  TPTF Charter, and
  TAC approved ERCOT Nodal Transition Plan
The TPTF report
  covers the period from the TPTF first meeting on November 30, 2005 through the February 24, 2009,
  identifies the current status of those TPTF tasks and activities that remain as on-going or scheduled, and that should be completed between now and the Texas Nodal Market Implementation Date (TNMID)
  provides TPTF recommendations for the continuation and final disposition of these tasks and activities by the TAC, or its designee
  was approved by the TPTF by roll call vote on February 24, 2009

## Slide 3: TPTF Report Structure
Table A addresses the duties and responsibilities that are assigned to TPTF in the TPTF Charter or the ERCOT Nodal Transition Plan
  For each activity or responsibility in the Charter or the Transition Plan, the final report provides:
    description of the assigned task
    TPTF’s view of the remaining work to support the Nodal Schedule Go-Live date, and
    its recommendations to TAC

## Slide 4: TPTF Report Structure
Table B lists those TPTF punch list items that remain open
  14 Open punch list items are identified
  For each item the current status is listed and a recommended disposition for closure
Table C lists those issues that TPTF referred to its Quick Response Working Group (QRWG) for off-line discussion and consensus building
  2 remaining Open QRWG issues are identified
  for each issue the current status of discussions and consensus building is outlined and recommended disposition

## Slide 5: Executive Summary - Recommendations
TPTF recommends that TAC continue to track and complete the Table A, B and C tasks and activities
The ERCOT Nodal Project Team and the TPTF have jointly identified and worked to resolve issues in meeting the Protocol requirements consistent with the capabilities of the vendor’s and ERCOT’s systems
  TPTF suggests that the need to address design issues will be ongoing throughout the remainder of this project and recommends TAC consider an organizational structure that is sufficiently robust to respond in a timely and knowledgeable manner
ERCOT and Market Participants must be prepared to act in accordance with the ERCOT Nodal Project Schedule
TPTF reaffirms its previous recommendations to TAC on February 5, 2009, provided in its suggested reconfiguration of Stakeholder participation

## Slide 6: Appendix – Support Documents
Link to the TPTF Charter
Link to the Nodal Market Transition Plan
Link to the TPTF punch list
http://www.ercot.com/content/committees/board/tac/tptf/keydocs/2009/tptf_charter_approved_tac_090607.doc
http://www.ercot.com/content/committees/board/tac/tptf/keydocs/2009/ERCOT_Nodal_Transition_Plan_062807.doc
http://www.ercot.com/content/committees/board/tac/tptf/keydocs/2009/TPTF_Punchlist.xls