## Slide 1: Texas Nodal Program Implementation: Program Update
Trip Doggett

## Slide 2: Agenda
Program Highlights
Utilicast – Audit Points to Address
Detailed Risk Status
Budget – Cost Management
Notes: <number>
<footer>
<header>
<date/time>
<number>

## Slide 3: Program Highlights – 1
The Nodal schedule and budget were approved by the Board, as submitted, on Feb. 17
  Schedule: go live in December 2010
  Budget: not to exceed $658.7 million
Since the schedule was replanned June 1, 2008, all tasks on the program critical path are currently on schedule
  Of 16 scheduled tasks on the critical path (to date), the program has hit 16
  Of 2,913 total scheduled tasks (to date), the program has hit 2,598
The integration and testing projects are undergoing a change in leadership and approach to address concerns raise by Utilicast in Report #8. More details on subsequent slide

## Slide 4: Program Highlights – 2
Core projects and associated releases
NMMS | Conducting functional acceptance test (FAT) for NMMS 6; scheduled to complete by Apr. 7
EMS | Completed FAT on release 6.2.x (release to address several SIG issues and NPRRs) on Feb. 9 and completed FAT on release 6.4.x (CIM Importer additions based on synchronized model (v1.21 schema) and additional SIGs) on Feb. 20 Scheduled to start FAT on release 6.5.x (regression test and SPR Patch 2 Release) on Mar. 9
MMS | Completed FAT testing for MMS4 Patch7 (CIM importer additions based on synchronized model (v1.21 schema) and bug fixes) on Feb. 20 Scheduled to start FAT on MMS5 (last scheduled release of functionality) on Apr. 16
COMS | Scheduled to start FAT on CSI7.0 (COMS integration refactoring with MMS 5) on Mar. 03

## Slide 5: Audit Points to Address from Utilicast Report 8 – 1
ID | Description | Action Plan | Responsible Manager | Target Date
UTI08-01 | The individual project budgets should be challenged in the following areas: a. Vendor contracts b. Contract staff c. Internal staff | Long –term vendor contracts will be negotiated with the assistance of a 3rd party negotiator, to address budget matters as well as others. 3rd parties are being interviewed at this time b, c. Plans for use of contract staff, as well as the orderly transition to ERCOT teams are being examined, as we refine the schedule and plan for the remainder of the schedule | J. Ply | 2/27/09: contract in process for 3rd party negotiator; 6/30/09 for contracts to be renegotiated for top 5 vendors Integrated schedule is being re-planned incrementally, with full re-plan to be complete in March, 2009
UTI08-02 | Given the high risks of the integration phase of the Nodal Program, this area should be reviewed in detail and be the subject of Nodal Oversight Report 9. | This item is closed. The integration phase of the Nodal Program was made the subject of Nodal Oversight Report Number 9. | J. Ply | Complete and verified; 2/2/09
UTI08-03 | Scope for the December 2010 release of the Nodal Program should be locked down with any proposed changes subject to a strict change control process. | This item is closed. There is now a clear policy supported by the Board of Directors that any change that affects Nodal schedule and budget must by approved by the ERCOT CEO and Board of Directors. | T. Doggett | Complete and verified; 2/17/09

## Slide 6: Audit Points to Address from Utilicast Report 8 – 2
ID | Description | Action Plan | Responsible Manager | Target Date
UTI08-04 | No enhancements should be considered for zonal market applications or processes unless assessed as business critical. | This item is closed. The ERCOT PMO is carefully monitoring Zonal project work, with guidelines in place to avoid use of Nodal resources. As of 1/30/09, there are no known requirements for use of Nodal resources in the work for 2009. | T. Doggett | Complete and verified; 1/30/09
UTI08-05 | There should be immediate investment in new data center capacity to allow for expansion of IT infrastructure to support the Nodal Program. | A project has been initiated to expand the data center in Taylor (PR-80047). The planned occupancy date is September 2009. The plan to add or move hardware is under development. Additional data center space is planned as part of the Met Center disposition project (PR-80001). Those data centers should be online in early 2011. Plans are under development to provide capacity prior to those new data centers becoming available. | J. Floyd | Early 2011
UTI08-06 | Given the risks of market readiness and Market Participants potentially delaying "Go-live" due to ambiguous EDS exit criteria, this area should be subject to a detail review. | This item is closed. The Special Nodal Program Committee decided the topic for Utilicast Report #10 will be "Infrastructure and Integration Readiness." | J. Ply | Complete and verified; 2/26/09

## Slide 7: Audit Points to Address from Utilicast Report 9 – 1
ID | Recommendation | Action Plan Status | Responsible Manager | Target Date
UTIL09-01 | The application project teams should own and be accountable for developing and testing their application interfaces. | The ownership has been reassigned and was communicated to the teams on 2/18/09 | L. Clarke | Complete; to be verified
UTIL09-02 | The scope of system integration testing (end-to-end testing) should be limited to confirming that the individual applications can operate as a single enterprise solution. | Communication to leaders was done on 2/18/09, and they carried the information to their teams that week. 2/26/09 End to End scenario criteria are under development... | L. Clarke | 3/31/09
UTIL09-03 | Clearly define and communicate the scope, objectives and expected deliverables of the core system integration components | 2/23/09 The approach has been communicated. Project Managers are in the re-planning process. | L. Clarke | 3/31/09
UTIL09-04 | Assign a qualified integration project lead. | This item is closed. Linda Clarke has been assigned. | J. Ply | Complete and verified; 2/13/09

## Slide 8: Audit Points to Address from Utilicast Report 9 – 2
ID | Recommendation | Action Plan Status | Responsible Manager | Target Date
UTIL09-05 | Appoint qualified leaders with clear ownership of clearly defined deliverables to the key system integration roles. | 2/26/09 – ERCOT has provided offers to potential candidates for 4 of 5 positions. We have commitments for the following positions: Technical Solution Lead, Market Trials Lead, End-to-End Business Scenario Testing Lead. On target to complete offers by mid-March. | L. Clarke | 3/31/09
UTIL09-06 | Update project plans and budgets based on revised integration scope, objectives, roles and responsibilities. | 2/27/09 Work is in progress | Nodal Project Managers and J. Ply | 3/31/09
UTIL09-07 | Define and implement (in conjunction with the Market Participants) the specification for the volume and content of information transmitted over external web services. | 2/20/09 Action items were assigned to the EIP Project Manager to establish a plan and a specification for content by 3/12/09, in preparation for the next Board of Directors meeting. | B. Brandaw | 3/17/09
UTIL09-08 | Build and configure a dedicated integration test environment. | 2/27/09 Data has been gathered and a plan is under development for the tasks required to complete. | K. Meinen | 3/31/09
UTIL09-09 | Review access policies and IT controls for non-production environments. | 2/20/09 Among the plans in the integration test environment preparation is a description of the procedures for handling access and IT controls. | K. Meinen | 3/31/09

## Slide 9: Nodal Program Risk: Integration Testing Strategy Needs Updating
Risk: Integration Testing Strategy Needs Updating |  |  |  | The existing integration testing strategy (e.g. planning approach, team structure, methodology) may not be adequate to successfully perform integration. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Identify leader for the entire Enterprise Verification effort (interface and end-to-end testing, market trials and system cutover) |  |  |  | J. Ply | 1/13/09 | Complete; Linda Clarke named as the Nodal Enterprise Verification Lead
2. Develop high level approach for Enterprise Verification. |  |  |  | L. Clarke | 2/18/09 | Complete Approach for interface testing rolled-out to PMs, who are updating schedules and moving forward with implementation
3. Review and refine the leadership and staffing levels for Nodal Enterprise Verification. |  |  |  | L. Clarke | Previous date 2/27/09; updated to 3/15/09 | 2/26/09 – ERCOT has provided offers to potential candidates for 4 of 5 positions. We have commitments for the following positions: Technical Solution Lead, Market Trials Lead, End-to-End Business Scenario Testing Lead. On target to complete offers by mid-March.
Notes: <number>
Identify the risk with a label that can be used in conversing about the risk
Indicate where we are in handling this risk - highlight one block in blue
Define – identifying and analyzing the impact of the risk
Plan – establishing the details for mitigating the risk
Manage – executing the mitigation plans and monitoring progress
Watch – we have the risk in control, using our mitigation plans, or there is no plan and we are just keeping an eye on this
Mitigation plans identify the work being done, with current status as of the reporting date
<number>

## Slide 10: Nodal Program Risk: Nodal Integration Test (iTest) and EDS Environments
Risk: Nodal Integration Test (iTest) and EDS Environments |  |  |  | Because the current iTest environment is set up in the EDS (passive) environment, and because it lacks all of the required platform software and permissions, the Nodal program cannot effectively conduct integration testing. Delays in integration testing threaten program delivery. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Review current iTest environment and strategy. |  |  |  | K. Meinen | 2/6/09 | Complete
2. Establish a detailed plan and project schedule for key activities and milestones to establish and maintain the iTest environment. Include elements such as: Ensure all technical architecture documents are current Deploy all needed HW Install all Nodal systems, with required components Establish release procedures with appropriate controls Ensure iTest environments match needs of integrated testing strategy |  |  |  | K. Meinen | Previous date 2/20/09; updated to 2/27/09 | 2/6/09 Identified elements for initial iTest environment, to be complete 3/20/09 2/20/09 Established initial milestones for completion of analysis and iTest build. Working on plan for iTest readiness for testing.

## Slide 11: Nodal Program Risk: Information Transmitted Over External Web Services
Risk: Information Transmitted Over External Web Services |  |  |  | If the volume and content of the information transmitted over Nodal external web services is not defined in detail, then market participant applications may attempt to transmit information in forms and of sizes that the Nodal applications are unable to process. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Identify an approach to handle appropriate sizes of files. |  |  |  | B. Brandaw | 3/12/09 | 2/20/09 An initial meeting was held to explain the actions required, so that a strategy can be explained at the next Board of Directors meeting on 3/17/09.
2. Establish a specification of the format of the information content to be transmitted by market participants. |  |  |  | B. Brandaw | 3/12/09 | 2/20/09 An initial meeting was held to explain the actions required, so that a strategy can be explained at the next Board of Directors meeting on 3/17/09. 2/27/09 Team has contacted technical rep from large MP – no need to chunk files; contacted Structure, PSI, and PJM for recommendations

## Slide 12: ERCOT-Wide Risk: Zonal Resource Constraints for Nodal Program
Risk: Zonal Resource Constraints for Nodal Program |  |  |  | Because the Nodal go-live date has been delayed, there are a number of Zonal projects, PRRs, and IMM suggestions for Zonal improvements that may result in resource constraints for the Nodal Program. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Manage list of PRRs and SCRs to a resource plan that uses a strategy to avoid impacting Nodal personnel resources when delivering additional Zonal enhancements. |  |  |  | D. Troxtell T. Anderson | Ongoing | 1/30/09 – Completed review with PRS and WMS on the current list of reconsidered and new PRRs and SCRs. No expected impact to Nodal. Updates will be provided to Nodal PMO as the list evolves. March/09 – To review the list with TAC
2. Manage Project Priority List (PPL) with clear view of resources needed for any projects in flight or about to be launched, with a strategy to avoid impact on Nodal personnel resources. |  |  |  | D. Troxtell | Ongoing | 1/28/09 – Current PPL shows no threat to Nodal personnel resource; updates to be provided to Nodal PMO as the PPL evolves; sent the list to Nodal PMO.
Notes: <number>
Identify the risk with a label that can be used in conversing about the risk
Indicate where we are in handling this risk - highlight one block in blue
Define – identifying and analyzing the impact of the risk
Plan – establishing the details for mitigating the risk
Manage – executing the mitigation plans and monitoring progress
Watch – we have the risk in control, using our mitigation plans, or there is no plan and we are just keeping an eye on this
Mitigation plans identify the work being done, with current status as of the reporting date
<number>

## Slide 13: ERCOT-Wide Risk: Data Center Space Concerns
Risk: Data Center Space Concerns |  |  |  | Data center capacity, space, and power may be inadequate for Nodal Program go-live, unless plans for expansion are adequate. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Establish an Information Lifecycle Management approach, to manage the life cycle of data being managed. |  |  |  | R. Hinsley | Roadmap by March 6 Implementation ongoing | ERCOT project PR 90006_01 Commercial Systems Information Lifecycle Management: Project SAIC to be Project Manager SAIC is engaged to complete a roadmap for a strategy by March 6.
2. Expand current data center space, and build out new data center, to increase ERCOT data center capacity. |  |  |  | R. Hinsley | TCC1 build out complete by 9/09 South DC in production Feb 2011 TCC3 in production May 2011 | ERCOT project PR_80047 TCC1 equipment to be purchased May 2009. ERCOT project PR_80001 South DC will run parallel Oct 2010 – Feb 2011 to test and avoid disruption to Nodal
3. Validate and monitor Nodal data capacity assumptions |  |  |  | R. Hinsley | May 2009 | Study underway to validate current assumptions
Notes: <number>
<number>
<number>

## Slide 14: Budget – Cost Management
The program’s monthly budget actuals have been under the forecast over the last several months
  Currently scrubbing the Nodal budgets on a project-by-project basis to ensure appropriate staffing levels, mix of internal and external labor, and estimates based on current information
Introducing new financial processes
  Generating a “Current Month-End Spend Projection” that is a combination of expenses and liabilities incurred during the first half of a month combined with a projection of expenses and liabilities during the second half of a month
  The program, at a project level beginning in February, will update forecasted spend for a minimum of the subsequent three months and further out if known
  Monthly financial work session will be scheduled the last week of each month with each project for the purpose of reviewing the prior month budget to actual performance in order to explain all variances and impacts to schedule or forecasted expense and to review forecast changes for approval
  Monthly project reviews will be revised include both budget and schedule together, as well as other key controls of the program

## Slide 15
Questions?