## TABLE 1 FOR ATTACHMENT 4
[5 empty] | TABLE 1 FOR ATTACHMENT 4 | [7 empty] | LEGEND: | (details are below-initiating on line 22, cell A)
[5 empty] | IMPLEMENTATION CHART FOR BAL-001 | [8 empty] | Begin Work (BW)
|  | Compliance Schedule for Requirements R1- R11 for BAL-001-TRE-01 | [11 empty] | Compliant (C)
|  |  | Compliance Schedule for Requirements R1- R11 for BAL-001-TRE-01 | [10 empty] | Substantially Compliant (SC)
Auditably Compliant (AC)
|  | End of Q2 2010 |  | End of Q4 2010 |  | End of Q2 2011 |  | End of Q4 2011 |  | End of Q2 2012 |  | End of Q4 2012 |  | Measurement definition for responsible party:
REQUIREMENT | Responsible Party | BA / System Control Center | Other Facilities (GO, GOP, etc) | BA / System Control Center | Other Facilities (GO, GOP, etc) | BA / System Control Center | Other Facilities (GO, GOP, etc) | BA / System Control Center | Other Facilities (GO, GOP, etc) | BA / System Control Center | Other Facilities (GO, GOP, etc) | BA / System Control Center | Other Facilities (GO, GOP, etc)
R1 | BA | BW |  |  |  | SC |  | C |  |  |  | AC |  | M1. The BA shall have a procedure in place for identifying Measurable Events.
R2 | BA | BW |  |  |  | SC |  |  |  | C |  | AC |  | M2. BA shall make available for inspection evidence that the data as specified in R2 was submitted to the Compliance Enforcement Authority for evaluation.
R3 | BA | BW |  | SC |  |  |  | C |  |  |  | AC |  | M3. The BA shall have available for inspection evidence that the analysis of the IMFR was performed as specified in R3.
R4 | BA | BW |  |  |  | SC |  |  |  | C |  | AC |  | M4. The BA shall have evidence it calculated the twelve-month rolling average frequency response performance of the Interconnection of all Measurable Events.
R5 | BA | BW |  | SC |  |  |  | C |  |  |  | AC |  | M5. For each Measurable Event, the BA shall have evidence it reported the performance of each interconnected Generation Resource/Frequency Responsive Resource to the Compliance Enforcement Authority.
R6 | BA | BW |  |  |  | SC |  | C |  |  |  | AC |  | M6. For each Measurable Event, the BA shall have evidence it reported the twelve- month rolling average performance of each Generation Resource/Frequency Responsive Resource to the Compliance Enforcement Authority.
R7 | GO |  | BW |  | SC |  |  |  | C |  |  |  | AC | M7. The GOP shall have evidence it reported to the BA, each Generation Resource/Frequency Responsive Resource’s governor operating range and expected frequency response performance for the full output range of each Generation Resource/Frequency Responsive Resource.
R8 | GO |  | BW |  | SC | [5 empty] | C |  | AC | M8. The GO shall have evidence its frequency response Generation Resource/Frequency Responsive Resource’s governor droop is set in accordance with the settings in Attachment 3.
R9 | GO |  | BW |  |  |  | SC |  |  |  | C |  | AC | M9. The GO shall have evidence its frequency response Generation Resource/Frequency Responsive Resource’s governor deadband is set in accordance to the limits in Attachment 3.
R10 | GO/GOP |  | BW |  |  |  | SC |  | C |  |  |  | AC | M10. Within the Measurable Event report, evidence of premature frequency response withdrawal by the Generation Resource/Frequency Responsive Resource was not visually observed.
R11 | GO/GOP |  | BW |  |  |  | SC |  | C |  |  |  | AC | M11. Within the Measurable Event report, the twelve-month rolling average frequency response (p.u.) performance of each Generation Resource/Frequency Responsive Resource met the minimum performance as stated in Attachment 3.
Begin Work means a Responsible Entity has developed and approved a plan to address the requirements of a standard,
has begun to identify and plan for necessary resources, and has begun implementing the requirements.
Substantially Compliant means an entity is well along in its implementation to becoming compliant with a requirement,
but is not yet fully compliant.
Compliant means the entity meets the full intent of the requirements and is beginning to maintain required
“data,” “documents,” “documentation,” “logs,” and “records.”
Auditably Compliant means the entity meets the full intent of the requirement and can demonstrate compliance to an auditor,
including 12-calendar-months of auditable “data,” “documents,” “documentation,” “logs,” and “records.”
Per the standards, each subsequent compliance-monitoring period will require the previous full calendar year of such material.

## REQUIREMENTS DETAILS
REQUIREMENTS DETAILS (BAL-001-TRE-1 REAL POWER BALANCING CONTROL PERFORMANCE:
R1. | The Balancing Authority for the ERCOT Interconnection shall identify Measurable Events (as defined in this regional standard) for primary governing frequency response measurement of Generation Resources, Frequency Responsive Resources, and firm load.
R2. | Within 30 days of a Measurable Event, the Balancing Authority for the ERCOT Interconnection shall submit to the Compliance Enforcement Authority scan rate data necessary to analyze each Measurable Event identified in R1. This data shall include:
(1) Interconnection Frequency;
(2) Interconnection scheduled frequency used in the ACE equation;
(3) Regulation Service deployed;
(4) Responsive Reserve Service deployed;
(5) Available Responsive Reserve Service (Nodal only);
(6) Generation Resource/Frequency Responsive Resource MW value;
(7) Control Error (Schedule CE in Zonal, Generation Resource/Frequency Responsive Resource CE in Nodal);
(8) Generation Resource/Frequency Responsive Resource Expected Frequency Response;
(9) Resource Regulation Service Allocation (Nodal only);
(10) Resource Economic Base Point (Nodal only);
(11) Resource High Operating Limit;
(12) Resource Low Operating Limit;
(13) Load Acting As Resource MW;
(14) Load Acting As Resource deployed;
R3. | The BA shall analyze frequency and frequency movements and calculate the Interconnection Minimum Frequency Response (IMFR) (MW/0.1Hz) by January 1 of each year.
R4. | The BA shall attain a twelve-month rolling average Interconnection Frequency Response, as measured in Attachment 2, greater than or equal to the Interconnection Minimum Frequency Response.
R5. | For each Measurable Event, the frequency response performance of each interconnected Generation Resource/Frequency Responsive Resource shall be compiled by the BA as measured in Attachment 3.
R6. | The BA shall calculate the twelve-month rolling average frequency response performance of each Generation Resource/Frequency Responsive Resource and report it to the Compliance Enforcement Authority.
Generation Resources less than 10 MW each, who at a single point of interconnection sum to an aggregate greater than 10 MW, shall be treated as a single Generation Resource.
R7. | The GO shall report to ERCOT the operating range, performance level, and any parameter limiting the frequency response of each Generation Resource/Frequency Responsive Resource.
See Attachment 3 for these parameters.
R8. | The GO shall ensure that combustion turbines in a combined cycle configuration have a governor droop characteristic of 4%, steam turbines have a governor droop characteristic of 5%,
and that all other Generation Resources/Frequency Responsive Resources have a governor droop characteristic of 5% or less. See Attachment 3 for these characteristics.
R9. | Each GO shall limit governor dead bands, intentional and unintentional, of turbine governors to those stated in Attachment 3.
R10. | Except for protection of equipment or safety, the GO and GOP will sustain its governor response to all frequency deviations that exceed the dead bands stated in Attachment 3.
R11. | The GO and GOP will meet a minimum twelve-month rolling average frequency response performance on each Generation Resource/Frequency Responsive Resource as stated in Attachment 3.
See chart of Figure 4: Expected Resource Performance and associated spreadsheet.