## Slide 1: Nodal COMS Update Commercial Operations Subcommittee March 10, 2009 Hope Parrish ERCOT - Market Operations Division Projects Organization

## Slide 2: COMS Project: S&B and Data Aggregation
http://nodal.ercot.com <number>
S&B and Data Aggregation
  Development
      All Lodestar core development and FAT testing complete. Integration testing to begin after the ITEST refresh in April.
      Lodestar Outstanding code (to date): Ongoing ad hoc optimization including memory enhancements, additional error handling and performance tuning will continue through integration testing
      CSI Outstanding code (to date): CSI 7.0 includes Long Day/Short Day, remaining BDs
  Testing
    Perform execution of integration testing
  Major issues
    iTEST refresh scheduled for March - will add some time to the validation of CSI 7.0. Continue to work towards synchronized data sets required for end to end testing.

## Slide 3: COMS Project: Registration and Disputes
http://nodal.ercot.com <number>
Registration and Disputes
  Development
    Registration complete – any bug fixes will be worked into SIR releases between now and go-live
    Disputes complete
  Testing
    FAT testing complete
    Integration testing starting 03/26/2009 thru 05/01/2009
  Major issues
    None

## Slide 4: COMS Project: Credit Monitoring and Mgmt
http://nodal.ercot.com <number>
Development
  CMM Scheduled weekly code drops to promote progress
    CMM 4.1 - Received Build for Credit Scoring, Mergent Feeds, and Bilateral Trade
      (Outstanding development to date) External Reports and Custom GUI Management
    CMM 4.2 – Internal Reports / Bug fixes
    CMM 4.3 - Refactoring
Testing
  CMM 4.1 FAT in progress. Plan to run all remaining releases in parallel with Integration testing without impact
    CMM 4.1 FAT target Completion = 05/07/2009
    CMM 4.2 FAT target Completion = 06/18/2009
    CMM 4.3 FAT target Completion = 07/08/2009
Major Issues
  Vendor and ERCOT Turnover resulted in delays to finalization of detailed analysis and designs of the remaining releases. Additional resources have been added from TPT and procuring additional test resources to bring schedule back in.

## Slide 5: Readiness Center Reports, DDLs, and XSDs
http://nodal.ercot.com <number>
Posted 03/03/2009
Nodal Data Services Master List version 8.01 – the re-baseline posting has gone through a thorough reconciliation using current Zonal and Nodal protocols. This list includes all data that must be posted/made available by ERCOT. It can be found at http://nodal.ercot.com/readiness/reports/index.html.
EDW – Draft Settlements user Guide v0.01 – this is the initial draft posting of the user guide for shadow settlement extracts (use of Settlements DDL and PRDE DDL). It can be found at http://nodal.ercot.com/readiness/reports/index.html.
EDW – Settlements Draft DDL v0.09 – this draft of the DDL includes the field comments. It can be found at http://nodal.ercot.com/readiness/reports/DDL/index.html.
EDW – PRDE Draft DDL v0.08 – this draft of the DDL includes the field comments. It can be found at http://nodal.ercot.com/readiness/reports/DDL/index.html.
EDW – PRDE Decode Tables – this is a posting for the MPs to be able to have a baseline of the decoding tables as we have them setup in our ITEST environment to decode some of the Lodestar data in the Settlements extract. It can be found at http://nodal.ercot.com/readiness/reports/index.html.
EDW – DRAFT Settlement DDL Join Mappings – this is a posting for the MPs to be able to see how the fields between the Settlements DDL and PRDE DDL are joined together to decode data. It can be found at http://nodal.ercot.com/readiness/reports/index.html.
If you have any questions about the documents feel free to email us at NodalReportReadiness@ercot.com.

## Slide 6: Readiness Center Standard & Mock Statements and Invoices
http://nodal.ercot.com <number>
Mock CARD Invoice and Extracts | http://nodal.ercot.com/readiness/reports/si/kd/card_invoices_and_extracts.zip
Mock CRR Balancing Account Invoice | http://nodal.ercot.com/readiness/reports/si/kd/mock_crr_balancing_account_invoice_examples.zip
Mock DAM Late Fee Invoices | http://nodal.ercot.com/readiness/reports/si/kd/dam_late_fee_invoices.zip
Draft Invoices | http://nodal.ercot.com/readiness/reports/si/kd/Draft%20Invoices.zip
Draft Settlement Statements | http://nodal.ercot.com/readiness/reports/si/kd/draft_settlement_statements.zip
Mock DAM Settlement Examples | http://nodal.ercot.com/readiness/reports/si/kd/mock_dam_settlement_examples.zip
Release 8 Settlement Postings (Statements, Invoices, Extracts, Reports, Notices) | (http://nodal.ercot.com/readiness/eds4/documents/index.html)

## Slide 7
http://nodal.ercot.com <number>
Questions?