## Slide 1: MARS Taskforce
RMS Update March 11, 2009
Notes: <number>

## Slide 2: MARS Taskforce March 9, 2009 Meeting
ERCOT Project Status Report for Planning Phase
  Planning Complete 02/20/2009 Completed
Taskforce reviewed the Market Testing and Execution Phase milestones and critical tasks for Project 80027 Advanced Metering Interim Settlement Solution.
Notes: <number>

## Slide 3: Execution Phase Testing Requirements
Scope of Market Testing:
  TDSP submits Advanced Metering LSE interval data file submission and ERCOT returns a file-level acknowledgement
Target Dates for Market Testing:
  October 19 – November 6, 2009
Next Steps:
    As the project progresses through development activities and the detailed ERCOT testing schedule is refined, coordination activities will be scheduled with the TDSPs.
Notes: <number>

## Slide 4: Execution Phase Schedule Milestones and Critical Tasks
Execution Milestones | Baseline Date
Technical Architecture Complete | 05/15/2009
Development Complete | 07/24/2009
Detailed Designs Complete | 08/11/2009
pTest Complete | 08/11/2009
iTest Complete | 11/06/2009
Market Test Complete | 11/06/2009
GO LIVE | 11/14/2009 (off-cycle)
Go Live (Contingency Date) | 12/12/2009
Stabilization Complete | 03/19/2010
Project Complete | 05/21/2010
Notes: <number>

## Slide 5: March 9, 2009 Meeting
MARS Taskforce reviewed initial draft of new Retail Market Guide Section 7.15 “Advanced Meter Interval Data File Format and Submission”, which includes
  File layout and data requirements for ERCOT Specified File Format for both ERCOT and TDSP’s FTP sites
  Process for TDSPs to post files to FTP site for CR downloads or transmit files via NAESB to ERCOT
  File Naming Convention
  Documented file size limitations for files sent to ERCOT will contain no more than 50,000 transactions
Notes: <number>

## Slide 6: Questions Answered
Clarified that a transaction is comprised of a single day of interval data reads – 96 reads (92 or 100 reads if changing to or from Daylight Savings Time (DST).
What extracts and web services will be available to market participants at project go-live?
      Changes impacting 727?
      When effective?
      Others?
Notes: <number>

## Slide 7: Questions Discussed
When ERCOT is ready to start receiving 814_20 Load Profile changes for AMS would the TDSP need to provide an 814_20 Load Profile update for the AMS profile on a meter read date?
  If yes, how will the volume be managed for each TDSP?
Notes: <number>

## Slide 8: ERCOT’s Response
Considerations:
  The effective date of the profile change (814_20) can not be future dated. Therefore, the profile changes will need to be submitted after project go-live (11/14/09).
  The load profile annual validation will be occurring approximately the same time frame or within a month of go-live and early stabilization.
Notes: <number>

## Slide 9: Annual Validation Questions
What about Annual Validation being performed around this time?
  814_20 Volume for all TDSPs involved.
  Resources needed to manage this effort and scheduling impacts to complete
  Time needed for issue resolution
  Value?
Notes: <number>

## Slide 10: Next Steps for MARS
Complete the review and finalize new section Retail Market Guide Section 7.15 “Advanced Meter Interval Data File Format and Submission” by mid-April
Continue to update RMS and COPS on the progress of Project 80027 Execution Plan
Revisit the 814_20 AMS Profile change volume question in July 09 to determine the best solution for the market
Continue to complete and resolve action items by providing timely feedback
Notes: <number>

## Slide 11: Questions?
Notes: <number>