## Slide 1: Update on Advanced Metering Projects
Heather Day
Project Manager, MO DPO
Retail Market Subcommittee
March 11, 2009

## Slide 2: Agenda
Advanced Metering Projects – Recap
PR80027_01 Advanced Metering Interim
  Current Status
  Estimated Project Costs
  Timeline
  Risks
Questions

## Slide 3: 2009 PPL – Advanced Metering Projects

## Slide 4: PR80027_01 Project Status – Execution Phase
Project Phases
Initiation – Completed
Planning – Completed
Execution – Pending Board Approval 03/17/2009
Closing – 03/19/2010
Recent Accomplishments
Requirements, Conceptual Designs, Security Assessment, and defined testing strategy and timeline.
Next Steps
Obtain Board Approval – 03/17/2009
Technical Architecture Complete – 05/15/2009
Development Complete – 07/24/2009
Detail Designs (done in parallel to development) – 08/11/2009 (as built)

## Slide 5: PR80027_01 Estimated Project Costs
Project Forecasted Budget
Actual Spend to Date: ~$204K
Remaining Forecast: ~$1.34M (includes a 25% contingency)
More closely aligns with the PRR Cost Estimates from the CBAs.
  PRR766 – $750k cost estimate
  PRR756 - $750k cost estimate
Contributing factors to increase in forecasted budget:
  Additional resources to ensure delivery by 2009 delivery date.
  Data Aggregation Rewrite must be reworked into Zonal code due to Nodal Delay (was originally planned to deliver with original Nodal schedule and provides performance enhancements for higher volumes)
  ERCOT Executive request for 25% Contingency

## Slide 6: PR80027_01 High-Level Schedule
Execution Phase Milestones | Baseline Date
Technical Architecture Complete | 05/15/2009
Detailed Designs Final | 07/10/2009
Development Complete | 07/24/2009
UAT and Performance Test Complete | 11/06/2009
Market Test Complete | 11/06/2009
Go Live | 11/14/2009
Go Live (Contingency Date) | 12/12/2009
Stabilization Complete | 03/19/2010
Project Complete | 05/21/2010

## Slide 7: PR80027_01 Project Risks
  Known risks in executing the project:
    Possible schedule delays should key contract or ERCOT resources be pulled from the project.
      Mitigation: All required contractors identified and engaged. Resource efforts are continually monitored and any issues are addressed immediately with the resource manager. Increased contingency to allow for additional resources as needed.
    Possible schedule delays if adequate storage, power and space is not available by go-live to support increased data volumes.
      Mitigation: Working closely and continually with infrastructure team to ensure necessary storage, power and space if available to support project throughout development, at go-live and on-going. Increased contingency to allow for additional resources as needed.
    Possible schedule delays due to competing with Nodal integration testing for limited iTest environments
      Mitigation: Detailed coordination steps are being identified and refined to ensure that all parties are aware of competing activities, etc. Increased contingency to allow for additional resources as needed.

## Slide 8
Questions?