## Sheet1
ERCOT
Renewable Technology Working Group (RTWG)
List of Issues (abridged)
March 2009
No. | Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status
4 | MD | 4 | Consideration of new ancillary service products in order to support reliability needs | ROS | Long Term | 0 | Eric Goff had developed a list of questions to be discussed at the Feb. 20 RTWG meeting; Eric will bring a whitepaper in May
7 | MD | 7 | Investigate whether any Nodal Protocol changes are necessary to allow wind resources to provide ancillary services | ROS | Undetermined | PRR | Walter Reid will develop list of questions to be presented to RTWG in May.
8 | MD | 8 | Review of current Protocol to ensure requirements are applicable to all technologies re: reactive and voltage requirements | WOTF | Near Term | PRR | Docket 36482 has been abated. ERCOT staff is preparing a draft PRR that should be out in March.
14 | SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information | WOTF | Near Term | ERCOT Forms | Assigned to WOTF Modeling Subgroup. Currently being reviewed
19 | SO | 6 | Qualification testing of reactive capability for wind generation | ERCOT Operations | Near Term | OGRR | ERCOT Operations is drafting OGRR because the current procedure is inadequate
20 | SO | 7 | High frequency: Develop alternate solutions | WOTF | Near Term | 0 | WOTF currently reviewing a whitepaper on governor response; a draft PRR will be developed.
21 | SO | 8 | System intertia capability of wind generators | PDCWG | Long Term | 0 | Mark Garrett to ask ROS for status update
22 | SO | 9 | Better defined SCADA control of generation breakers | OGRR TF | Near Term | OGRR | Draft OGRR is being discussed at OGRTF
24 | SO | 11 | Protocols, Operating Guides, Interconnection Procedure and the Interconnection Agreement need to be updated to make requirements less ambiguous and more generic to include all types of generation | ROS | Near Term | PRR, OGRR, ERCOT Procedures and Agreements | ERCOT developing a technology-specific procedure for wind; RTWG is considering technology-specific procedures for other renewable technologies
36 | SO | 25 | Governor Generator Response of wind generators | WOTF | Undetermined | 0 | Under active discussion at WOTF; a draft PRR will be prepared
MD = Market Design
SO = System Operations
SP = System Planning
WT = Workshop/Training