TPIT information draft						March 11, 2009

Yellow highlights are from Dec 15, 2008 meeting.

Blue highlights address comments received after Dec 15, 2008 meeting.

Except as noted in this document or in the column heading of the TPIT workbook, each column should be filled in for each project.

Transmission Project Information Tracking (TPIT) and Steady-State Base Case updates are performed quarterly.  TPIT updates are due to ERCOT on the 1st of the month or the next following business day. The case updates are due to ERCOT one week after the TPIT updates.

Additional data items will only be added to TPIT with approval of the TSPs who submit TPIT.

Each quarter all TSPs will be e-mailed a base workbook of its projects from the previous quarter’s final TPIT workbook. Each TSP will edit its workbook, make notations when new projects are added to the workbook, and e-mail it back to ERCOT. ERCOT will combine them into one TPIT workbook.

For the projects that require Regional Planning Group (RPG) review, the ERCOT regional planning department will update the three columns labeled: “Date Submitted to ERCOT for RPG Review”, “Date RPG Review Completed”, and “Date ERCOT BOD Review Completed”. If a project does not require RPG review, these columns will be left blank.

The following types of transmission projects which have a “material impact on the grid’s ability to deliver generation and control voltage” are to be included in TPIT:
1. Transmission Line (60 kV and above, New/ Rebuild/ Upgrade) 
2. Reactive Device Installation (Capacitor Bank, Reactor Bank, FACTS device, etc.) 
3. Autotransformer (New/ Upgrade) 
4. Substation Upgrade (If upgrade affects transmission line or autotransformer rating.)

5. Multi-terminal Transmission Substation (60 kV and above, New/Rebuild/Upgrade)

Examples of projects that may not have a “material impact” and may be excluded from TPIT:

1. Minor physical change to a transmission line such as moving a set of structures to accommodate road construction.

2. Impedance change that can be reasonably attributed to round off error.

3. Load serving substations.

Cancelled projects will be moved to the “Cancelled” tab, and will be removed during the next quarter’s update.

Completed projects will be moved to the “Completed” tab.

ERCOT will assign the TPIT project numbers to new projects. The TSP will include a notation that new projects were added to the workbook in the e-mail used to transmit the workbook back to ERCOT.

The TSPs will coordinate with other TSPs on combined projects.  Combined projects should only be included one time. Some projects that have multiple distinct phases with multiple TSPs constructing separate phases may be submitted as multiple projects. Notes of the related TPIT projects should be made in the ‘Other’ column.

There should be no duplicate projects in the TPIT.

TSPs provide as much technical data and cost estimates as possible.  TSPs will include preliminary cost estimates for all projects.  If cost estimates are part of another project the TSPs will include these estimates in the ‘Other’ column and not in the “Cost Estimate” column.  The most up-to-date estimated project cost for completed projects will be provided. For projects in the completed tab the Total Project Estimated Cost is not required to be updated with final actual costs .

Only numbers should be in the columns with numerical data. Do not enter units such as MVA, kV, miles, etc… These are included in the headers.  All numerical data should be entered as numbers not text.

The ‘SERVICE LEVEL KV’ column for autotransformers should be the high voltage side of the autotransformer.

Distribution transformer capacity should not be included in the ‘Autotransformer Capacity (MVA)’ column.

The two ‘Transmission Circuit Miles’ (new and rebuilt) columns should indicate the circuit miles of transmission wire and NOT the tower miles or transmission Right of Way.

The ‘Actual In-Service Date’ column should be blank in the Future tab, but filled in on the Completed tab.

Column R ‘County Location of Ending point for a Line’ should be blank for substation projects.

The ‘SSWG Base Case Related Bus Numbers’ column may be blank if the project does not materially affect the model of the transmission system in the base cases. Example: some projects do not require a change to the SSWG cases. Because SSWG models are Bus-Branch models they do not reflect detailed substation design. Some projects only make substation improvements that increase reliability of the transmission system, but do not change impedance or ratings in a Bus-Branch model.  Bus numbers will be filled in when they are applicable.

The ‘Requested Additional Information’ and ‘Other’ columns are optional.