## CBA_Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | SCR 754 |  |  | Estimator's Name: |  | Dave Maggio/Gokal Raina
Project Title: | Zonal AWS Wind Generation Forecasts for QSEs |  |  | Sponsor's Name: |  | John Adams
|  |  |  | Estimate Date: |  | 2009-02-25
Project Description: | PRR 763 requires QSEs representing Wind-powered Generation Resources (WGRs) to use an ERCOT provided Wind Generation Resource Power Production (WGRPP) forecast in their WGR Resource Plans during Replacement Reserve Service (RPRS) procurements. The project will replace the emailed forecast by utilizing the existing zonal infrastructure and processes as follows: Fully redundant configuration of zonal platform including site failover capability Existing data retrieval processes from other vendor forecast services Existing MOS MUI services to deliver data to QSEs on query
Benefits and Impacts
1 - Replace emailed wind generation forecasts sent to QSEs with Wind Generation Resources (WGRs) to increase reliability of receiving the forecasts.
2 - Forecast will be provided by utilizing fault tolerant zonal platforms.
3 - QSEs with WGRs can utilize existing MOS MUI services to retrive data through data queries. QSE's need to add the new query to their existing systems.
4 - The emailed forecasts will not be discontinued until all QSE's are able pull the report through the MUI
Feasibility
1 - The project will utilize the development components of a prototype that was built to validate the solution.
2 - The QSE data queries will utilize the similar services as currently provided in MOS MUI XML transfer document.
3 - Standard replication tools will be used to support Cognos reporting by the ERCOT business user.
Alternatives
Assumptions
1 - The forecast file sent to ERCOT by the wind forecast vendor will continue to be received at approximately 10 minutes after the hour, every hour.
2 - The QSEs representing WGRs will not attempt to retrieve a WGRs’ forecast more than 10 times in a given hour.
3 - The QSEs will have set up their systems to automatically retrieve the forecasts as provided by ERCOT.
4 - Individual QSEs will be ready to partcipate in MOTE testing over a 2 week period.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 75000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 75000
| ERCOT Ongoing Cost | 0
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 0
[5 empty] | 75000 |  | Total Cost
Project Benefit | ERCOT Benefit | 0
| Market Benefit | 0
[5 empty] | 0 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | -80000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## CBA_Data_Entry
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | SCR 754 | Zonal AWS Wind Generation Forecasts for QSEs
Sponsor: | John Adams | Estimate Date: | 2009-02-25 | Estimator: | Dave Maggio/Gokal Raina
Project Description: | PRR 763 requires QSEs representing Wind-powered Generation Resources (WGRs) to use an ERCOT provided Wind Generation Resource Power Production (WGRPP) forecast in their WGR Resource Plans during Replacement Reserve Service (RPRS) procurements. The project will replace the emailed forecast by utilizing the existing zonal infrastructure and processes as follows: Fully redundant configuration of zonal platform including site failover capability Existing data retrieval processes from other vendor forecast services Existing MOS MUI services to deliver data to QSEs on query
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1 | Replace emailed wind generation forecasts sent to QSEs with Wind Generation Resources (WGRs) to increase reliability of receiving the forecasts.
2 | Forecast will be provided by utilizing fault tolerant zonal platforms.
3 | QSEs with WGRs can utilize existing MOS MUI services to retrive data through data queries. QSE's need to add the new query to their existing systems.
4 | The emailed forecasts will not be discontinued until all QSE's are able pull the report through the MUI
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies | The project will utilize the development components of a prototype that was built to validate the solution.
Other 1 | The QSE data queries will utilize the similar services as currently provided in MOS MUI XML transfer document.
Other 2 | Leverage Zonal Market User Interface (MUI) currently being used by QSE’s
Other 3 | Standard replication tools will be used to support Cognos reporting by the ERCOT business user.
Alternatives
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1
2
Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The forecast file sent to ERCOT by the wind forecast vendor will continue to be received at approximately 10 minutes after the hour, every hour.
2 | The QSEs representing WGRs will not attempt to retrieve a WGRs’ forecast more than 10 times in a given hour.
3 | The QSEs will have set up their systems to automatically retrieve the forecasts as provided by ERCOT.
4 | Individual QSEs will be ready to partcipate in MOTE testing over a 2 week period.
ERCOT Cost and Benefit Detail | [7 empty] | OPTIONAL WORKSHEET FOR CALCULATING COSTS - STAFFING
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3 |  |  | Task / Item | FTE Cost ($/hour) | Expected Cost in FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Cost = Total FTE Hours * FTE Cost | Workdays Per Year
Implementation Cost | Project | 75000 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
[9 empty] | 0 | 0 | 0 | 0 | 240
Ongoing Cost (O&M) | Software | 0 |  |  |  | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Present Value of Internal ERCOT Cost: | 75000 | [8 empty] | Total | 0
OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - STAFFING
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3 |  |  | Task / Item | FTE Cost ($/hour) | Expected Reduction in FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Benefit = Total FTE Hours * FTE Cost | Workdays Per Year
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | NPV = | 0 | No direct cost savings to ERCOT | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  | Total | 0
Productivity Increases | Select type… | 0 | 0 | 0 | 0 | NPV = | 0 | OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - OTHER
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  |  | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  |  | 0
| Present Value of Internal ERCOT Benefit: | 0 | [8 empty] | Total | 0
Market Cost and Benefit Detail | [7 empty] | OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - STAFFING
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3 |  |  | Task / Item | FTE Cost ($/hour) | Expected Reduction in FTE Hours Per Workday | Total FTE Hours Per Year | Estimated Cost Savings = Total FTE Hours * FTE Cost | Workdays Per Year
Implementation Cost |  | 0 | 0 | 0 | 0 | NPV = | 0 | Minimal impact to Market, need to add the new query. | 0 | 0 | 0 | 0 | 240
[9 empty] | 0 | 0 | 0 | 0 | 240
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  | 0 | 0 | 0 | 0 | 240
| Present Value of Market Cost: | 0 | [8 empty] | Total | 0
OPTIONAL WORKSHEET FOR CALCULATING BENEFITS - OTHER
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3 |  |  | Item | Comment |  |  | Amount
Benefits for Market | Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  |  | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  |  | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  |  | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0 |  |  |  |  | 0
| Total Present Value of Market Benefit: | 0 | [8 empty] | Total | 0
Total Cost | 75000 |  | Net (Cost) - Benefit ($) |  | -80000
Total Benefit | 0 |  | Cost Benefit Ratio |  | 0
Summary values are rounded to 2 significant digits.
Senate Bill 7 Requirements
Indicate percentage that this project supports Senate Bill 7 requirements:
Pct
| Access to transmission and distribution systems |  |  | 0%
| Reliability and adequacy of electrical network |  |  | 100%
| Customer choice of REP |  |  | 0%
| Accounting accuracy |  |  | 0%
|  | Total (Must equal 100%) |  | 100%
ERCOT Corporate Goals
Indicate percentage that this project supports each ERCOT corporate goal:
Pct
| 1 - Reliability and Congestion Management |  |  | 100%
| 2 - Retail Transaction Processing Success |  |  | 0%
| 3 - Wholesale Access, Settlement and Billing |  |  | 0%
| 4 - Management Systems and Business Practices |  |  | 0%
| 5 - Financial Management and Cost Effectiveness |  |  | 0%
| 6 - External and Stakeholder Affairs |  |  | 0%
| 7 - Organizational Readiness |  |  | 0%
|  | Total (Must equal 100%) |  | 100%
Measurement Strategy
Enter methods for measuring post-project costs and benefits here…
| Metric to be Measured |  | Who to Contact | When to Make Contact | Additional Measurement Notes
ERCOT Cost | Total cost of the project after it has been fully implemented. |  | Cagle Lowe | End of Execution
Timeliness | 3 Month Project Timeline |  | Cagle Lowe | End of Execution
Select type…
Select type…
Select type…
Additional Comments
Enter any additional comments here…
1
2
3
4
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?

## Instructions
Cost / Benefit Analysis Worksheet Instructions
IMPORTANT: This page will be revised after the Summary and Data Entry tabs are complete.
General Information
Fields highlighted in yellow are to be entered by the person completing the CBA
Fields highlighted in turquoise are section headings or important subtotals
All data entry takes place on the "CBA_Dtl" tab
"CBA_Sum" provides a 2 page summary of the 5 page detail section
"CBA_Dtl" contains several optional worksheets to the right of the main CBA sections
These optional worksheets are not included in the default print range
CBA_Dtl Tabl
Project Information
|  | PRR / SCR / PR / "New" |  | Enter the source document number for this project - if none exists,
enter "New"
|  | Project Title |  | Name of project
|  | Sponsor's Title |  | Project sponsor
|  | Estimator |  | Person completing the CBA
|  | Estimate Date |  | Date the CBA is completed
| Senate Bill 7 Requirements |  |  | Enter percent of each SB7 requirement the project supports
Total should not exceed 100%
| ERCOT Corporate Goals |  |  | Enter percent of each ERCOT corporate goal the project supports
Total should not exceed 100%
Assumptions
|  | Assumptions |  | Document assumptions that are made in the evaluation of the project
| ERCOT Internal Cost |  |  | Note that Year 0 benefit is likely to be zero. Most likely scenario is that project costs will be incurred in first year, and deployment and benefit will be at end of first year or in following year. Years are fiscal years, January to December.
Implementation Cost
|  |  | Cost to Implement | For a project requested by ERCOT this number comes from the Time and Cost Estimate worksheet
For a project requested by the market, this number is the mid-point of the Impact Analysis cost range
All project costs are to be included in this value
Ongoing Cost (O&M)
|  |  | Staffing | ERCOT staffing increases due to the implementation of this project
|  |  | Hardware | Hardware additions required after project implementation
|  |  | Software | Software costs required after implementation (ex: yearly licensing)
|  |  | Infrastructure | Other costs relating to the physical or computing infrastructure
|  |  | Other | Use these 2 fields to capture other cost categories
|  |  | Other | Change the "Other" headings to the name of the new cost categories
ERCOT Internal Benefit
Direct Cost Savings
|  |  | Staffing | ERCOT staffing savings due to project
|  |  | Hardware | Hardware savings due to project
|  |  | Software | Software savings due to project
|  |  | Infrastructure | Infrastructure savings due to project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Productivity Increases
|  |  | Time Savings | Value of hours saved due to project deliverables
|  |  | Other Increased Efficiencies | Value of hours saved due to project deliverables
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Other Benefits
|  |  | Cost Avoidance | Costs avoided due to implementation of project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
| Market Cost |  |  | Note that Year 0 benefit is likely to be zero. Most likely scenario is that project costs will be incurred in first year, and deployment and benefit will be at end of first year or in following year. Years are fiscal years, January to December.
|  | Implementation Cost |  | Market implementation cost is derived from ERCOT implementation cost
|  |  | Estimated Market Cost | Calculated by multiplying ERCOT implementation cost by the selected market impact percentage (from the Parameters section) and the number of impacted market participants (from the Parameters section)
|  |  | Impacted Market Segments | These fields allow the requester to customize the cost/benefit calculations by declaring the number of market participants are impacted by segment - this is used in both the Market Cost and Market Benefit sections. Work with PRR/SCR sponsors and ERCOT Client Services on a case by case basis to refine the Impacted Numbers by Market Segment where ever possible in order to avoid unintentional inflation of market benefit.
|  |  | Market Implementation Complexity | "High/Medium/Low/No Impact" - indicates the impact percentage for a market segment
|  | Ongoing Cost |  | Ongoing costs required of market participants upon implementation of project (totals by market segment)
Market Benefit
Benefits by Participant
|  |  | Direct Cost Savings | Direct savings per market participant in each market segment
|  |  | Elimination of Manual Effort | Elimination of manual effort per market participant in each market segment
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Benefits for Market
|  |  | Reduced Congestion Cost | Expected congestion cost savings in market
|  |  | Consumer Savings | Expected savings that are likely to benefit consumers - be sure not to double count savings to market participants that are likely to pass through to consumers
|  |  | Transaction Cost | Expected reductions in transaction costs due to project
|  |  | Other | Use these 2 fields to capture other savings categories
|  |  | Other | Change the "Other" headings to the name of the savings categories
Project Objectives Detail
|  | Implementation Requirement |  | Project score indicating implementation timing requirements and/or governing body requirements (PUCT, market committee, etc.)
|  | Reliability |  | Project score indicating impact on overall ERCOT system reliability (all systems to be considered)
|  | Security |  | Project score indicating impact on physical or cyber security
|  | Data Management |  | Project score indicating the impact on data accuracy, timeliness and/or transparency
|  | Efficiency |  | Project score indicating efficiency gains that would be realized
|  | Requirements |  | Project score indicating the completeness of the requirements and the likelihood that delivery risk can be reduced by breaking the project into smaller deliverables
|  | Investment or Baseline |  | Project score indicating whether the project provides additional functionality (investment) or supports the existing system architecture
|  | Risk Reduction |  | Project score indicating overall risk reduction that can be achieved at implementation
Intangible Benefits
|  | Area / Comments |  | Document benefits here that cannot be quantified but should be considered in the overall prioritization of the project
Risk Reduction
|  | Risk Description |  | Description of risk item
|  | Mitigation Percentage |  | Percent of the risk that the project would eliminate if implemented
|  | Probability of Risk Occurring |  | Probably of the risk occurring in a given year
|  | Approximate Cost of Risk |  | Estimated cost if the risk occurred
|  | Expected Risk Cost/Year |  | Risk probability * Approximate Cost of Risk * Mitigation Percentage
Alternatives
|  | Alternatives |  | Document alternatives that were considered or are available
Ex: comments about manual workarounds (amount of effort and cost) or other implementation options that were considered
CBA_Sum Tab
| Cost / Benefit Summary |  |  | Summary from CBA_Dtl tab
| Objectives Summary |  |  | Summary from CBA_Dtl tab
| Intangible Benefit Summary |  |  | Summary from CBA_Dtl tab
| Risk Reduction Summary |  |  | Summary from CBA_Dtl tab
| Assumptions Summary |  |  | Summary from CBA_Dtl tab
Calculation Parameters
Market Cost
|  |  | Impacted # of QSEs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of CRs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of TDSPs | Source for this data is in the Market Cost section of CBA_Dtl
|  |  | Impacted # of Resources | Source for this data is in the Market Cost section of CBA_Dtl
|  | Present Value Interest Rate |  | Percentage used to value future cash flows in the CBA
This value was suggested by the ERCOT Accounting Dept.; it should not be changed