## Slide 1: Texas Nodal Program Implementation: Program Update
April 9, 2009
Technical Advisory Committee Meeting
Mike Cleary
Sr. VP and Chief Technology Officer
Notes: <number>

## Slide 2: Agenda
Nodal Program Update
April 9, 2009
Program Highlights
  Core Project Releases
  Key Market Participant Dates
  Recent Accomplishments
Utilicast – Audit Points to Address
Detailed Risk Status
Notes: <number>
<number>

## Slide 3: Program Highlights – 1
Nodal Program Update
April 9, 2009
Core Project Releases
NMMS | Conducting functional acceptance test (FAT) for NMMS 6; scheduled to complete by Apr 7 Final release, NMMS 7, scheduled to start FAT on Apr 24 and complete by May 21
EMS | All major software releases delivered; two patch releases remain EMS 6.5.x (regression test and SPR Patch 2 release) is scheduled to start FAT on Apr 27 and complete by May 8 EMS 6.6.x (SPR Patch 3 release) is scheduled to start FAT on May 19 and complete by Jun 2
MMS | Last scheduled release, MMS 5, delivered by vendor and currently undergoing pre-FAT; scheduled to start FAT on Apr 16 and complete by Aug 21
CRR | All major software releases delivered; maintenance release scheduled to start FAT on Jun 15 and complete by Aug 31
COMS | Conducting FAT on CMM 4.1 (external reports/Bilateral Trade); scheduled to complete by May 7; two CMM releases remain with final FAT complete by Jul 8 Started FAT on CSI 7.0 (COMS integration) on Apr 1; scheduled to complete by Apr 26
Notes: <number>

## Slide 4: Program Highlights – 2
Nodal Program Update
April 9, 2009
Key Market Participant Dates
  Please refer to attached document, Nodal Timeline 0410.pdf
Notes: <number>

## Slide 5: Program Highlights – 3
Nodal Program Update
April 9, 2009
Recent Accomplishments
  Utilicast Report #9, recommendation to change the approach for adapter, interface, and end-to-end business scenario testing – COMPLETE.
  Installation of an integration test (iTest) environment with all required hardware and nodal applications – COMPLETE. Final environment access and permission work is underway.
  Activities to refresh the test environment databases – COMPLETE.
  External web services information (approach to handle appropriate sizes of files, specification of the format of the information content) – finalized and communicated to Market Participants on Mar 20.
Notes: <number>

## Slide 6: External Audit Status Summary
Nodal Program Update
April 9, 2009
Audit | Audit Points Identified | Audit Points in Execution | # Closed Audit Points
IBM Report 6 | 4 | 1 | 3
IBM Report 7 | 4 | 1 | 3
Utilicast Report 8 | 6 | 2 | 4
Utilicast Report 9 | 9 | 4 complete - to be verified; 3 in execution | 2
Notes: <number>

## Slide 7: Audit Points to Address from Utilicast Report 8
Nodal Program Update
April 9, 2009
ID | Recommendation | Action Plan Status | Responsible Manager | Target Date
UTI08-01 | The individual project budgets should be challenged in the following areas: a. Vendor contracts b. Contract staff c. Internal staff | Long –term vendor contracts will be negotiated with the assistance of a 3rd party negotiator, to address budget matters as well as others. b, c. Plans for use of contract staff, as well as the orderly transition to ERCOT teams are being examined, as we refine the schedule and plan for the remainder of the schedule | Janet Ply | Target: 6/30/09 for contracts to be renegotiated for 5 top vendors 3/31/09 Third party has been engaged to conduct a contract assessment as an initial effort, completed 3/31 3/3/09 Have completed review of our key contracts by an outside firm 3/30/09 resourcing of remaining effort shows growth in size of ERCOT teams and reduction of contract staff as testing effort is re-planned incrementally ; Program has engaged a resource manager to review all staffing.
UTI08-05 | There should be immediate investment in new data center capacity to allow for expansion of IT infrastructure to support the Nodal Program. | A project has been initiated to expand the data center in Taylor (PR-80047). Planned occupancy date is September 2009, with plan to add or move hardware under development. Additional data center space planned as part of the Met Center disposition project (PR-80001). Those data centers should be online in early 2011. Plans are under development to provide capacity prior to those new data centers becoming available. | Jeff Floyd | Early 2011
Notes: <number>

## Slide 8: Audit Points to Address from Utilicast Report 9 - 1
Nodal Program Update
April 9, 2009
ID | Recommendation | Action Plan Status | Responsible Manager | Target Date
UTIL09-02 | The scope of system integration testing (end-to-end testing) should be limited to confirming that the individual applications can operate as a single enterprise solution. | Communication to leaders was done on 2/18/09, and they carried the information to their teams that week. 2/26/09 End to End scenario criteria are under development. | L. Clarke | 3/31/09 Complete; to be verified by Utilicast
UTIL09-03 | Clearly define and communicate the scope, objectives and expected deliverables of the core system integration components | 2/23/09 The approach has been communicated. Project Managers are in the re-planning process. | L. Clarke | 3/31/09 Complete; to be verified by Utilicast
UTIL09-05 | Appoint qualified leaders with clear ownership of clearly defined deliverables to the key system integration roles. | 3/23/09 – People are now on-site working with the program for 4 of 5 positions: Person for Data Management position to be on-site 4/6/09. | L. Clarke | 3/31/09 Complete; to be verified by Utilicast
UTIL09-07 | Define and implement (in conjunction with the Market Participants) the specification for the volume and content of information transmitted over external web services. | 3/20/09 Language was drafted for inclusion in the External Interface Specification and software changes were identified. Formal communication of these changes was made on 3/20 during an EDS call. | B. Brandaw | 3/17/09; Complete; to be verified by Utilicast
Notes: <number>

## Slide 9: Audit Points to Address from Utilicast Report 9 - 2
Nodal Program Update
April 9, 2009
ID | Recommendation | Action Plan Status | Responsible Manager | Target Date
UTIL09-06 | Update project plans and budgets based on revised integration scope, objectives, roles and responsibilities. | 4/1/09 – Re-baselined integrated scheduled to include adapter/interface changes. 3/30/09 – The integrated project schedule is being updated with detailed plans and budget for connector testing as well as the general approach for end to end testing; resources are being reviewed against the plans. | Nodal Project Managers and J. Ply | 3/31/09; revised to 4/30/09
UTIL09-08 | Build and configure a dedicated integration test environment. | 4/1/09 – Minor issues being resolved that do not impact interface testing. 3/30/09 – Environment has been configured and regression testing is underway. Most Project Managers have signed off. | K. Meinen | 3/23/09; revised to 4/3/09
UTIL09-09 | Review access policies and IT controls for non-production environments. | 4/1/09 – Distributed to PMs for final review. 3/30/09 – Release Management and Infrastructure Change Management processes are in final review with Nodal Program leaders and IT. | K. Meinen | 3/31/09; revised to 4/30/09
Notes: <number>

## Slide 10: Nodal Program Risk: Resource Conflict for Advanced Metering and Nodal Program
Nodal Program Update
April 9, 2009
Nodal Program Update
April 2, 2009
Risk: Advanced Metering Resources |  |  |  | Advanced Metering is a high priority project for 2009. There are now potential conflicts in 2009 over resources and testing environments needed at the same time by the nodal program and Advanced Metering project. [note: this is an instance of resource conflicts being monitored and managed with the ERCOT PMO] |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Establish a testing approach to use different environments for the Lodestar testing. Limit shared testing to just the single shared ISM environment during testing in Q4 2009. |  |  |  | H. Parrish S. Jirasek | 7/24/09 | 4/2/09 Test strategy is complete for Advanced Metering. It will be incorporated into the nodal test plan for end-to-end testing during the April planning.
2. Arrange resource assignments for Lodestar and EDW to ensure coverage by development teams and business team resources to allow for parallel nodal program work and Advanced Metering work, to support the Advanced Metering mandate of January 2010 and nodal go-live date of December 2010. |  |  |  | H. Parrish S. Jirasek | 7/24/09 | 4/2/09 Resource planning is underway, with current expectations that coverage will be sufficient. Plans will be incorporated into the nodal test plan for end-to-end testing during the April planning.
3. Monitor resource assignments and availability. |  |  |  | H. Parrish S. Jirasek | November, 2009 | 
Notes: <number>
<number>
Identify the risk with a label that can be used in conversing about the risk
Indicate where we are in handling this risk - highlight one block in blue
Define – identifying and analyzing the impact of the risk
Plan – establishing the details for mitigating the risk
Manage – executing the mitigation plans and monitoring progress
Watch – we have the risk in control, using our mitigation plans, or there is no plan and we are just keeping an eye on this
Mitigation plans identify the work being done, with current status as of the reporting date
<number>

## Slide 11: ERCOT-Wide Risk: Data Center Space Concerns
Nodal Program Update
April 9, 2009
Risk: Data Center Space Concerns |  |  |  | Data center capacity, space, and power may be inadequate for Nodal Program go-live, unless plans for expansion are adequate. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Establish an Information Lifecycle Management approach, to manage the life cycle of data being managed. |  |  |  | D. Forfia | Implementation ongoing | 3/31/09 ILM Roadmap has been completed by SAIC, and next planning activities underway ERCOT project PR 90006_01 Commercial Systems Information Lifecycle Management Project SAIC to be Project Manager, to complete roadmap by 3/6/09
2. Expand current data center space, and build out new data center, to increase ERCOT data center capacity. |  |  |  | D. Forfia | TCC1 build out complete by 9/09 South DC in production Feb 2011 TCC3 in production May 2011 | 3/30/09 Work underway to expand current TCC1 data center ERCOT project PR_80047 TCC1 equipment to be purchased May 2009. ERCOT project PR_80001 South DC will run parallel Oct 2010 – Feb 2011 to test and avoid disruption to Nodal
3. Validate and monitor Nodal data capacity assumptions |  |  |  | D. Forfia | May 2009 | Study underway to validate current assumptions
Notes: <number>
<number>
<number>
<number>

## Slide 12: ERCOT-Wide Risk: Zonal Resource Constraints for Nodal Program
Nodal Program Update
April 9, 2009
Risk: Zonal Resource Constraints for Nodal Program |  |  |  | Because the Nodal go-live date has been delayed, there are a number of Zonal projects, PRRs, and IMM suggestions for Zonal improvements that may result in resource constraints for the Nodal Program. |  | 
Risk Life Cycle State |  |  |  |  |  | 
Define | Plan | Manage | Watch |  |  | 
Mitigation Plans |  |  |  | Who | Target Date | Current Status
1. Manage list of PRRs and SCRs to a resource plan that uses a strategy to avoid impacting Nodal personnel resources when delivering additional Zonal enhancements. |  |  |  | D. Troxtell T. Anderson | Ongoing | 1/30/09 – Completed review with PRS and WMS on the current list of reconsidered and new PRRs and SCRs. No expected impact to Nodal. Updates will be provided to Nodal PMO as the list evolves. April 09 – To review the list with TAC
2. Manage Project Priority List (PPL) with clear view of resources needed for any projects in flight or about to be launched, with a strategy to avoid impact on Nodal personnel resources. |  |  |  | D. Troxtell | Ongoing 4/17/09 – complete an “on request” analysis with nodal resources as identified during recent nodal re-forecast activity | 4/2/09 ERCOT PMO will continue regular review of resource plans for projects on the PPL to detect any potential impact to resources also allocated to nodal work, as well as “on request” comparison of nodal resource allocations against those loaded for the PPL. Frequency of these reviews will increase to monthly instead of quarterly. 3/27/09 Potential conflict is under review for resources needed to work on Advanced Metering project.
Notes: <number>
<number>
Identify the risk with a label that can be used in conversing about the risk
Indicate where we are in handling this risk - highlight one block in blue
Define – identifying and analyzing the impact of the risk
Plan – establishing the details for mitigating the risk
Manage – executing the mitigation plans and monitoring progress
Watch – we have the risk in control, using our mitigation plans, or there is no plan and we are just keeping an eye on this
Mitigation plans identify the work being done, with current status as of the reporting date
<number>

## Slide 13
<number>
Nodal Program Update
April 9, 2009
Questions?
Notes: <number>