## Slide 1: Nodal Update for: Single Entry Model (SEM) Go-Live Transition
http://nodal.ercot.com <number>
ROS
April 16, 2009
Matt Mereness

## Slide 2: SEM Go-Live Transition Update
http://nodal.ercot.com <number>
General review of SEM Transition
Communications with stakeholders
SEM Go-Live Criteria
Model Submissions during June-Aug’09 transition

## Slide 3: General Review of SEM Transition
http://nodal.ercot.com <number>
Single Entry Model (SEM) Go-Live is the switchover on Aug 31, 2009 for TSP submissions of network operations model change requests
  from “Service Request” submissions via TML
  to “NOMCR” submissions via the NMMS
TSP
Current Activity
Submit Modeling
Change via Service Request
ERCOT Uploads
Svc Request
into Zonal
Genesys Model
ERCOT Copies/Converts
Zonal Model “seed”
Into Nodal
NMMS Model
TSP
Aug 31, 2009
Submit Modeling Change via
NOMCR/NMMS Tool
ERCOT Incrementally
Converts NOMCR
Into Svc Req
Uploads into Zonal
Genesys Model
ERCOT uploads
NOMCR
Into Nodal
NMMS Model
Data Consistency Checks are run to
ensure model synchronization/fidelity
Data Consistency Checks are run to
ensure model synchronization/fidelity

## Slide 4: General Review of SEM Transition (cont’d)
http://nodal.ercot.com <number>
The processes and approvals leading up to this activity were outlined in the SEM Go-Live Procedure approved by TPTF and TAC in Aug/Sep 2008
  http://nodal.ercot.com/readiness/golive/index.html
In the coming months ERCOT will continue to provide updates to NDSWG on details of the implementation and switchover activities.
All nodal presentations to NDSWG continue to be consolidated and posted on Nodal Readiness Center:
  http://nodal.ercot.com/readiness/eds2/documents/index.html

## Slide 5: General Review of SEM Transition (cont’d)
http://nodal.ercot.com <number>
ERCOT is utilizing NDSWG forum to update and communicate TSP activities for Single Entry Model (SEM) Go-Live

## Slide 6: Communications with Stakeholders
http://nodal.ercot.com <number>

## Slide 7: Communications with Stakeholders (cont’d)
http://nodal.ercot.com <number>

## Slide 8: SEM Go-Live Criteria
http://nodal.ercot.com <number>
SEM Go-Live Criteria defined in the SEM Go-Live Procedure http://nodal.ercot.com/readiness/golive/index.html
Section 4- The following entry criteria shall be met for SEM Go-Live
  TSPs & ERCOT complete EDS 2 Release 4 activities (next page)
  Nodal network model validated and approved as baseline for SEM Go-Live by ERCOT System Ops and Market Ops Directors
  ERCOT publishes CIM model to be used for SEM Go-Live
  ERCOT sufficiently staffed for maintenance of nodal & zonal systems
  Nodal EMS is capable of consuming NMMS CIM files through the EMS CIM importer for use in the Nodal EMS application suite
  SEM Go-Live readiness approved by TPTF, TAC and ERCOT BOD
    presume ROS approval in place of TPTF
  ERCOT publishes the following documents for TSPs
    ERCOT Network Operations Model validation whitepaper
    ERCOT Network Operations Model validation results
    NMMS Modeling Guidelines / Validation Rules document
    Latest CIM data dictionary and schema

## Slide 9: SEM Go-Live Criteria (cont’d)
http://nodal.ercot.com <number>
  All TSPs complete EDS 2 Release 4 activities
    MPs have enrolled and can access the ERCOT MIS portal
    MPs have been trained on the NOMCR process
    TSPs can electronically submit data changes utilizing the NOMCR user interface and CIM compliant format for data exchange or via the manual MIS NOMCR process
    QSEs can submit data changes utilizing the registration submission and subsequent ERCOT NOMCR process
    MPs can receive NOMCR acknowledgement of submittals, verifications, and confirmation of data posting
  ERCOT completes EDS 2 Release 4 activities
    ERCOT is ready to fully utilize the NOMCR process for all TSP/QSE data change requests
    TSP MPs can successfully submit data changes via the CIM compliant electronic NOMCR process.
    QSE can successfully submit data changes through registration submissions (and updated in the Network Operations Model via the NOMCR process)
    ERCOT has processes in place to use a “single entry point” to maintain both Nodal and Zonal network model databases when MPs submit changes via the NOMCR process
    NMMS is the database of record for the Network Operations Model including the ICCP modeling point database and operatorship / ownership information
    NMMS database is under full change control by ERCOT Network Model Group
    ERCOT discontinues the use of Service Requests for data changes and change control
    ERCOT begins the use of the NOMCR process for data changes and change control

## Slide 10: Model Submissions during June-Aug’09 transition
http://nodal.ercot.com <number>
Model Submissions for network operations model
  Currently no limits on submissions
    Market Notice clarification sent March 5 to all MPs
    “… to clarify that there are no restrictions or “freezes” currently in place limiting network model change submissions via the service request process.”
  Draft concepts for transition period:
    June 1- Aug 31, 2009
      Objective to minimize Service Requests during this period
      Submit changes as far in advance as possible
      No equipment name changes (defer until after 8/31/09)
    Aug 15-31, 2009
      Objective during period is to complete transition and implementation
      Two weeks no submissions, except for emergency changes
    Discuss more at April NDSWG

## Slide 11: Questions
http://nodal.ercot.com <number>
Questions or comments can be submitted to:
  eds2@ercot.com
  mmereness@ercot.com