## Slide 1: Single Entry Model (SEM) Go-Live
http://nodal.ercot.com <number>
TAC Update
May 7, 2009

## Slide 2: SEM Go-Live
http://nodal.ercot.com <number>
What is SEM Go-Live?
Market Engagement/Communications
Training Update
SEM Go-Live Criteria
Transition summary during June – August 2009
Next steps

## Slide 3: What is SEM Go-Live?
http://nodal.ercot.com <number>
Single Entry Model (SEM) Go-Live is the switchover on Aug 31, 2009 for TSP submissions of network operations model change requests
  from “Service Request” submissions via TML
  to “NOMCR” submissions via the NMMS
  System of record for Model remains Zonal/Genesys system until Dec 2010
TSP
Current Activity
Submit Modeling
Change via Service Request
ERCOT Uploads
Svc Request
into Zonal
Genesys Model
ERCOT Copies/Converts
Zonal Model “seed”
Into Nodal
NMMS Model
TSP
Aug 31, 2009
Submit Modeling Change via
NOMCR/NMMS Tool
(includes ICCP)
ERCOT Incrementally
Converts NOMCR
Into Svc Req
Uploads into Zonal
Genesys Model
ERCOT uploads
NOMCR
Into Nodal
NMMS Model to
support nodal testing
Data Consistency Checks are run to
ensure model synchronization/fidelity
Periodic checks are run to
ensure model synchronization/fidelity
Full
Copy
Incr.
NOMCR

## Slide 4: Market Engagement / Communications
http://nodal.ercot.com <number>
The processes and approvals leading up to this activity were outlined in the SEM Go-Live Procedure approved by TPTF and TAC in Aug/Sep 2008
  http://nodal.ercot.com/readiness/golive/index.html
ERCOT has engaged and presented updates to the following groups, and will do so monthly moving forward:
  NDSWG- Jan, Feb, Mar, April
    Market SMEs review artifacts and training agenda
  ROS- Feb, April
    High level reports of schedule, metrics, and criteria status
Metrics-
  MP13 – MP Completes Nodal Operations Training
    Measure of training attendance for MPs
  MP14-B EDS2-Rel4 Trials Participation
    Measure of testing participation- target 95% of aTSPs

## Slide 5: Market Engagement / Communications
http://nodal.ercot.com <number>
Coming into critical window of final Zonal->Nodal model transformation, market training, application roll-out

## Slide 6: Training Update
http://nodal.ercot.com <number>
TSP Testing and Training environments will be the same
Testing system access
  Available June 8 – Aug 10
  NOMCR testing system will be on-line and available to all TSPs
  ERCOT will establish dedicated email and have staff available to support questions (nomcrhelp@ercot.com)
Instructor Led Training to be hosted in Taylor
  Pre-SEM classes June 22 – Aug 3
    Current plans for at least six 2-day sessions
    Planning for 12-18 seats for each class
    Large dedicated training room
  Post-SEM classes Sept 23- Oct 20
    Fewer sessions and smaller classes (tbd)
    Make-up classes, not just-in-time training for all staff after go-live

## Slide 7: SEM Go-Live Criteria
http://nodal.ercot.com <number>
SEM Go-Live Criteria defined in the SEM Go-Live Procedure http://nodal.ercot.com/readiness/golive/index.html
Section 4- The following entry criteria shall be met for SEM Go-Live
  TSPs & ERCOT complete EDS 2 Release 4 activities (next page)
  Nodal network model validated and approved as baseline for SEM Go-Live by ERCOT System Ops and Market Ops Directors
  ERCOT publishes CIM model to be used for SEM Go-Live
  ERCOT sufficiently staffed for maintenance of nodal & zonal systems
  Nodal EMS is capable of consuming NMMS CIM files through the EMS CIM importer for use in the Nodal EMS application suite
  SEM Go-Live readiness approved by TPTF, TAC and ERCOT BOD
    presume ROS approval in place of TPTF
  ERCOT publishes the following documents for TSPs
    ERCOT Network Operations Model validation whitepaper
    ERCOT Network Operations Model validation results
    NMMS Modeling Guidelines / Validation Rules document
    Latest CIM data dictionary and schema

## Slide 8: SEM Go-Live Criteria (cont’d)
http://nodal.ercot.com <number>
  All TSPs complete EDS 2 Release 4 activities
    MPs have enrolled and can access the ERCOT MIS portal
    MPs have been trained on the NOMCR process
    TSPs can electronically submit data changes utilizing the NOMCR user interface and CIM compliant format for data exchange or via the manual MIS NOMCR process
    QSEs can submit data changes utilizing the registration submission and subsequent ERCOT NOMCR process
    MPs can receive NOMCR acknowledgement of submittals, verifications, and confirmation of data posting
  ERCOT completes EDS 2 Release 4 activities
    ERCOT is ready to fully utilize the NOMCR process for all TSP/QSE data change requests
    TSP MPs can successfully submit data changes via the CIM compliant electronic NOMCR process.
    QSE can successfully submit data changes through registration submissions (and updated in the Network Operations Model via the NOMCR process)
    ERCOT has processes in place to use a “single entry point” to maintain both Nodal and Zonal network model databases when MPs submit changes via the NOMCR process
    NMMS is the database of record for the Network Operations Model including the ICCP modeling point database and operatorship / ownership information
    NMMS database is under full change control by ERCOT Network Model Group
    ERCOT discontinues the use of Service Requests for data changes and change control
    ERCOT begins the use of the NOMCR process for data changes and change control

## Slide 9: Transition summary during June-Aug’09
http://nodal.ercot.com <number>
  Currently no limits on submissions (Market Notice sent March 5)
    “… to clarify that there are no restrictions or “freezes” currently in place limiting network model change submissions via the service request process.”
  Transition periods:
    June 1- Aug 30, 2009 (objective to minimize SvcReq during this period)
      No equipment name changes (defer until after SEM Go-Live 8/31/09)
      Submit changes as far in advance as possible
    Aug 15-30, 2009
      Two weeks no submissions, except for emergency changes
    Aug 31, 2009 - Feb 2010 (NOMCRs for any/all network changes)
      Initially the NOMCR timeline will align with zonal timeline
        NOMCRs received and translated to zonal model change
        30-day lead-time, compliant with current zonal database schedule
        Status is tracked and communicated via system emails
      SRs that did not go into zonal production will be converted to NOMCRs for verification and submission by TSPs in Sept
      TSP gradually transitions to NodalProtocols(3.10) 90-day reqts

## Slide 10: Next steps
http://nodal.ercot.com <number>
  Objective today was to clarify SEM Go-Live and market activities
  Monthly TAC updates will be made on status of SEM Go-Live
  ERCOT asks TAC to consider approval sequence for Go-Live
    In absence of “TPTF Approval”
  Questions?