## Slide 1: Texas Nodal Program Implementation: Program Update
Mike Cleary
Sr. VP and Chief Technology Officer
May 7, 2009
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
May 7, 2009
Program Highlights
  Current Timeline
  Risks & Issues
Market Readiness
Notes: <number>
<number>

## Slide 3: Nodal Program Timeline
May 7, 2009
Technical Advisory Committee

## Slide 4: Risks & Issues to Achieving Nodal’s Major Milestones
Technical Advisory Committee
May 7, 2009
Single-Entry Model Go-Live (8-31-09)
  Issue: NMMS defect-resolution threatens SEM Go-Live (CLOSED)
Complete Integrated Systems (11-18-09)
  Risk: Resource conflict for Advanced Metering and Nodal Program
  Issue: Handling CMM delays for Nodal Program
  Issue: Zonal resource constraints for Nodal Program
  Issue: Resource conflict could delay development of NMMS processes and procedures
Integrated Market Trials (2-10)
  Risk: Reconciling Protocols, Systems and Market Expectations
Nodal Go-Live (12-1-10)
  Risk: Data Center capacity concerns

## Slide 5
People
Technical Advisory Committee
May 7, 2009
Program Director
Janet Ply
ERCOT & Market
Readiness Murray Nixon (Acting)
NMMS
Terry Nielson
EMS
Manuel Atanacio
EDW
Shawna Jirasek
Chief Technology
Officer
Mike Cleary
Market & Grid Operations
Murray Nixon
Nodal Program Budget Mgmt
Chris Howell
MMS
Jeff Robinson
OS & CRR Sankara Krishnaswamy
IMM
Janice Ayson
Commercial Systems Hope Parrish
S&B and CSI
Justin Rasberry
CMM
Cathy Cioffi
Financial Transfer
Phyllis Encinias
Reg/Disputes
Clay Katskee
Nodal Enterprise Verification
Linda Clarke
Integration Technical Solutions Operational Readiness
John McCall
E2E Business Scenario Testing
Andrea Shepherd
MP Readiness
TBD
Market Trials
Jason Iacobucci
System Cutover
TBD
*Protocol Alignment Project*
TBD
MIS
Adam Martinez
MIS Portal
Brett Economides
CDR
Naresh Chunduri
Chief Financial
Officer
Steve Byone
Chief Operations
Officer
Trip Doggett
Chief Executive
Officer
Bob Kahn
Executive Sponsors
Processes & Procedures
Chuck Hansen
Kevin Furlong
Transition
TBD
Engagement & Outreach
TBD
Market Training
Ted Hailu
ERCOT Training
Chuck Hansen
Readiness Assessment
TBD
Readiness Metrics
Brandon McElfresh
ERCOT
Board of Directors
Chief Information
Officer
Richard Morgan (Interim)
General Counsel
Mike Grable
Resource
Management
Andrew Rinaldi
IT
Infrastructure
David Forfia
Program Control & Review
TBD
Process &
Quality Assurance
Joyce Statz
Deputy Program
Director
TBD
Public Utility Commission
Of Texas
Schedule
Kirk Oswalt
Communications
Tom Kleckner
Chief Administration Officer
Nancy Capezzuti
Nodal Financial Mgmt Office
Mike Petterson
OTS/MOTE/SOTE
Gokal Raina
Notes: <number>
.

## Slide 6: Aligning Market Protocols, Apps & Business Procedures
Technical Advisory Committee
May 7, 2009
Review Protocols
  Identify standard ISO services
  Identify ERCOT-specific market designs
Trace to Design Applications Testing Results
Trace to Business Processes
Produce Results
  Confirm implementation of standard ISO, ERCOT-specific designs
  Identify gaps between standard ISO, ERCOT-specific designs
    NPRR799 process Go-Live vs. Post Go-Live

## Slide 7: ERCOT Participant Readiness Approach
May 7, 2009
Technical Advisory Committee
ERCOT Participant Readiness Approach

## Slide 8: Readiness Functional Areas
Technical Advisory Committee
May 7, 2009
Engagement & Outreach
  Manage and chair Nodal Market Implementation Working Group
  Collect and track issues and action items
  Conduct phone and conference call campaigns/surveys
Participant Training
  Develop/revise participant training curriculum
  Conduct participant training courses
Readiness Assessments
  Establish assessment criteria
  Determine participants to assess via market-segmentation analysis
  Conduct assessment workshops
  Conduct baseline and follow-on assessments to gauge readiness
  Document assessments and action items
Readiness Metrics
  Track/report readiness metrics
  Coordinate with internal readiness
  Update dashboards, if necessary

## Slide 9
Questions ?