## Slide 1: May 2009 MO Projects Financial Overview & 2010 PPL Prioritization Commercial Operations Subcommittee May 12, 2009 Hope Parrish Market Operations Division Projects Organization

## Slide 2: Agenda
<number>
Overview of project status on MO 2009 PPL
Current 2009 Financials
2010 PPL Prioritization
  Review Timeline
  Review draft 2010 PPL
  Prioritize and rank initial list

## Slide 3: 2009 Projects
<number>

## Slide 4: Financial Overview as of 03/01/2009
<number>
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $520k | Current approved RO funding allocation Designates where the capability line falls
Current Forecast Spend of projects above the Capability Line | ~$1.26M | Based on current expectations and run rates for active and not started projects above the capability line Current Forecast for 2009 on ILM is expected to be $1.2M.
Budget Variance | ~($740k) | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line Will obtain funding from other CARTs to support ILM efforts (IO CART, etc.) as this is a critical need project. This request will come at the Planning end date.

## Slide 5
2010 PPL Prioritization

## Slide 6: 2010 PPL Prioritization - Timeline
April 2009
  CARTs develop draft 2010 project lists
    Request and incorporate input from the market
    5 year project forecast referenced and updated
May 2009
  Initial review at Market Subcommittee meetings
    MO - COPS (May 12)
    RO - RMS (May 13)
    SO - ROS, WMS (May 14 / May 20)
June 2009
  Approval by market subcommittees
    MO - COPS (June 9)
    RO - RMS (June 10)
    SO - ROS, WMS (June 11 / June 17)
    CO, IO, MO, RO, SO – PRS (June 18)
July 2009
  Approval by TAC (July 9)
  Available for F&A and Board review (July 21)

## Slide 7: 2010 PPL Prioritization – COPS Goals
WebEx with COPS – Apr 30 10-11am (Complete)
Process Kick off at COPS – May 12
  Goal to prioritize and rank an Initial 2010 MO PPL
ERCOT Draft Project Charters, CBA and submit – May 08
ERCOT Draft TCE for projects – May 15
Review and finalize Draft Charter, CBA, and TCE week of May 29
Approve 2010 MO PPL – June 9 COPS Meeting

## Slide 8: 2010 PPL Prioritization – Project Cancel Discussion
PR40056_01: Demand Response for Settlement (PRR478 PRR385)
Description: This project was to implement a settlement solution for lag dynamic samples when a there is a lag between processing of a new profile. This project was deferred until PWG and AMIT (PUC34610) have reviewed and confirmed this is still necessary.
Discussion: With the direction of Advanced Metering, should this project be cancelled?

## Slide 9: 2010 PPL Prioritization
Review 2010 PPL Initial – go to 2010_Planning_PPL_MO_05122009.xls
-Review
-Add
-Rank
-Prioritize

## Slide 10: Questions / Contact
<number>
Hope Parrish
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com
Notes: <number>