## Slide 1: March 2009 RO Projects Financial Overview Retail Market Subcommittee May 13, 2009 Hope Parrish Market Operations Division Projects Organization

## Slide 2: 2009 Projects

## Slide 3: Projects in Execution
PR50061_01 – Gated to Execution Phase on May 1, 2009
PR80040_01 – Planned for migration to production on May 16, 2009
PR80028_01 – Execution complete, expected to move to closing May 22, 2009

## Slide 4: Projects in Planning
PR80031_01 – Gated to Planning Phase on April 17, 2009
Notes: <number>

## Slide 5: Projects in On Hold or Not Started
PR80030: Placed “On Hold”due to funding needs for higher priority projects.
PR90007: 2009 funds released to higher priority projects with the assumption that the long-term solution will not start until 2010. Remains above the capability line.

## Slide 6: Projects Closing, Closed or Cancelled
Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Revised Budget Range
Market | RMS | RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Closed | 0 - Previously Approved | <$100k
Market | RMS | RO | SCR748 | Website Enhancements for ERCOT Outages PhII | 70006_02 | Closed | 0 - Previously Approved | <$50k
Market | RMS | RO | SCR745 | ERCOT Outage Evaluation PhII | 60006_01 | Closing | 0 - Previously Approved | <$50k
ERCOT | RO | RO |  | Paperfree and NAESB Transition to ISM formerly (EDW EAI Transition Phase 1 (including PaperFree & NAESB)) | 50061_02 | Cancelled | 2 - High | $100k-$250k
PR70007 Closed

## Slide 7: Financial Overview as of 04/01/2009
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $3.39M | Current approved RO funding allocation Designates where the capability line falls Pending increase next month for PR50088-Data Research and reporting (approx. $300k for 2009). Requires Board Approval.
Current Forecast Spend of projects above the Capability Line | ~$3.22M | Based on current expectations and run rates for active and not started projects above the capability line
Budget Variance | ~$17k | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line.

## Slide 8
2010 PPL Prioritization

## Slide 9: 2010 PPL Prioritization - Timeline
April 2009
  CARTs develop draft 2010 project lists
    Request and incorporate input from the market
    5 year project forecast referenced and updated
May 2009
  Initial review at Market Subcommittee meetings
    MO - COPS (May 12)
    RO - RMS (May 13)
    SO - ROS, WMS (May 14 / May 20)
June 2009
  Approval by market subcommittees
    MO - COPS (June 9)
    RO - RMS (June 10)
    SO - ROS, WMS (June 11 / June 17)
    CO, IO, MO, RO, SO – PRS (June 18)
July 2009
  Approval by TAC (July 9)
  Available for F&A and Board review (July 21)

## Slide 10: 2010 PPL Prioritization – RMS Goals
WebEx with RMS – Apr 30 2-3pm (Complete)
Submit all 2010 Project Initiatives to hparrish@ercot.com – May 4 (Complete)
Process Kick off at RMS – May 13
  Goal for an Initial list with rank and priorities
ERCOT Draft Project Charters, CBA and review – May 08
ERCOT Draft TCE for projects – May 15
ALL - Review and finalize Draft Charter, CBA, and TCE week of May 29
Approve 2010 PPL at June RMS

## Slide 11: 2010 PPL Prioritization
Review 2010 PPL Initial – go to 2010_Planning_PPL_RO_05132009.xls
-Review
-Add
-Rank
-Prioritize

## Slide 12: Questions / Contact
Hope Parrish
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com
Notes: <number>