## RO
RO 2010 Planning PPL | [15 empty] | Documentation
RO 2010 Rank | 2010 Priority | Source | Committee | Program Area | Source Doc | Project Number | Project Name / Type | Status | 2009 Budget | 2010 budget | 2011 Budget | 2012 Budget | 2013 Budget | Total Budget | Summary Description | PR | TCE | CBA
Carry Over Projects
1 | 2-High | PUCT | RMS | RO | PRR 766; PUCT 34610 | 80027_01 | Advanced Metering – Interim Settlement Solution | Execution | 1369595 | <$50k | 0 | 0 | 0 | 1540063 | This project supports the interim settlement of up to provisioned Advanced Meters using actual 15 minute data as defined by PUCT Project 34610 (Interim Solution) (including small distributed renewable generators. ) Included in this effort is: | Yes | Yes | Yes
2 | 2-High | ERCOT | RO | RO |  | 50088_01 | Data Research and Reporting (formerly ETS Transition to EDW) | Planning | 350000 | $1M-$1.5M | $500k-$750k | 0 | 0 | 800000 | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse | Yes | Yes | Yes
3 | 2-High | ERCOT | RMS | RO |  | 90011_01 | Advanced Metering - Retail Market Interface | Not Started | 130000 | $100k-$250k | 0 | 0 | 0 | 500000 | Adding POLR Customer Class and AMS Meter Flag to the Database Query Function on the MIS | Yes | Yes | Yes
4 | 2-High | PUCT | PUCT | RO |  | 90007_01 | Advanced Metering – Long-Term Settlement Solution | Not Started | 0 | $1M-$2M | $1M-$2M | 0 | 0 | 5000000 | Necessary to comply with the requirements of PUCT Subst. R. §25.130. Advanced Metering, HB 2129 and HB 3693, relating to advanced metering. Accelerates the timeline for the market to take advantage of the benefits of advanced meters. | Yes | No | No
7 | 3-High/Medium | ERCOT | RO | RO |  | 80030_01 | MarkeTrak Phase 3 | Hold | 0 | $500-$1M | $100k-$250k | 0 | 0 | 200000 | MarkeTrak version upgrade and business enhancements requested by ERCOT and Market. | Yes | In progress | No
8 | 3-High/Medium | ERCOT | RO | RO |  | 80031_01 | Retail Application Upgrades | Planning | 463000 | $100k-$250k | 0 | 0 | 0 | 463000 | Carry Over - Analysis of all systems requiring upgrades over next 3 years (Siebel, TIBOC, Oracle, Paperfree) | Yes | Yes | Yes
2010 Requested Projects
5 |  | PUCT |  |  | PR35769 | New | POLR Process | Not Started |  | TBD | 0 | 0 | 0 |  | Implementation of PUCT 35769 – RULEMAKING TO RELATING TO ELECTRIC PROVIDERS OF LAST RESORT | No | No | No
6 |  | PUCT |  |  | PR356536 | New | Expedited Switch | Not Started |  | TBD | TBD | 0 | 0 |  | PUCT 36536 – RULEMAKING TO EXPEDITE CUSTOMER SWITCH TIMELINES - PUCT Substantive Rule §25.493 (e) states that ERCOT “shall develop procedures to facilitate the expeditious transfer of large numbers of customers from one rep to another.” | No | No | No
9 |  | ERCOT |  |  |  | New | Advanced Metering - Mid Term (ERCOT changes) | Not Started |  | $250k-$500k | $100-$250k | 0 | 0 |  | Mid term needs in preparation for the long term solution. Move 86703 report off ftp, modify 867 loading process to L*, splitting out interval data from LSChannelCutHeader Tables in L* if no impact to Nodal | In progress | In progress | In progress
10 |  | ERCOT |  |  |  | New | Retail Testing Website Enhancement | Not Started |  | $100k-$250k | 0 | 0 | 0 |  | ERCOT upgrade to transition to Enterprise Architecure approved infrastructure. No functional changes planned. | In progress | In progress | In progress
11 |  | ERCOT |  |  |  | New | Test Automation Tool Upgrade | Not Started |  | $100k-$250k | 0 | 0 | 0 |  | Automated testing tool - Winrunner is end of life 0508. Tool used by Market Ops teams to test - Retail, MarkeTrak, ERCOT.com | In progress | In progress | In progress
12 |  | ERCOT |  |  |  | 60033_01 | Retail Apps - Consolidated Calendar | Not Started |  | $100k-$250k | 0 | 0 | 0 |  | Develop single business calendar for use by all retail applications. (Does not include the Settlement calendar) | Yes | Yes | Yes
Others??
[7 empty] | Estimated Total |  |  | $3M-$5M
2011 projects from 5 year CART plans
|  | ERCOT | RO | RO |  |  | TML Transition to MIS |  | 0 | 0 | $250k-$500k | 0 | 0
|  | ERCOT |  |  |  |  | Siebel Upgrade |  |  | 0 | $500k-$1M | $100k-$250k | 0 |  | Siebel Application upgrade to 8.x and the data model changes for service account and esiid split
|  | ERCOT |  |  |  |  | EDI Transaction Enhancements |  |  | 0 | $250k-$500k | $100k-$250k | 0 |  | Execution on the analysis of PF replacement
|  | ERCOT |  |  |  |  | Retail Application Upgrades |  |  | 0 | $100k-$250k | $100k-$250k | $100k-250k |  | Application upgrades that require custom code changes (MarkeTrak, Paperfree, TIBCO)
|  | Market |  |  |  |  | TXSET XX |  |  | 0 | $500k-$1M | $100k-250k | 0 |  | TX SET Version Release as identified by TX SET and RMS

## Input (hidden)
CART | Source | Y/N | Priority
CO | Ercot | Yes | 1-Critical
MO | Market | No | 2-High
RO | Nodal | In progress | 3-High/Medium
IO | PUCT |  | 4-Medium
SO