|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for April 2009 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 243 active generation interconnection requests totaling almost 97,000 MW. This includes over 48,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total cost of $979.3 Million - Transmission Projects approved in 2009 total $ 105 Million - All projects (in engineering, routing, licensing and construction) totals approximately $4.1 Billion - Transmission Projects energized in 2008 total about $453 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	1

1.5	Generation Projects Undergoing Full Interconnection Studies	1

1.6	Wind Generation	1

2.	Regional Planning Group Project Reviews	1

3.	Other Notable Activities	1

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations

## Bosque Expansion (08INR0046) - 255 MW Combined Cycle in Bosque County

## South Houston Green Power Expansion (07INR0027) - 244 MW Combined Cycle in Galveston County

## Winchester Power Park (09INR0027) - 178 MW Combustion Turbine in Fayette County

## Sandow 5 (08INR0003) - 581 MW Coal in Milam County

## Goat Wind Phase 2 (07INR0028b) - 70 MW Wind in Sterling County

## The total installed wind capacity is now 8,135 MW, of which 7,477 (92%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements

## Nacogdoches Project (09INR0007) - 100 MW Biomass in Nacogdoches County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 243 active generation interconnection or change requests |  |  |  |  |
| As of April 30, 2009 | North | South | West | Total |
| Security Screening Study | 3 | 6 | 9 | 18 |
| SSS Completed | 2 | 9 | 23 | 34 |
| Full Interconnect Study | 29 | 36 | 81 | 146 |
| FIS Completed | 6 | 7 | 4 | 17 |
| Interconnect Agreement Completed | 7 | 9 | 12 | 28 |
| Capacity under Interconnection Agreements | 4,722 | 2,146 | 2,093 | 8,961 |
| Capacity for Grid, MW | 23,255 | 33,416 | 40,152 | 96,833 |
| Wind Capacity, MW | 2,610 | 9,522 | 36,545 | 48,677 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC | - | - | 4,241 | 22,276 |
| Gas-CT | - | - | 527 | 1,677 |
| Total Gas | 5,518 | 13,667 | 4,768 | 23,953 |
| Nuclear | - | 3,200 | 9,186 | 12,386 |
| Coal | 1,463 | 2,532 | 3,550 | 7,545 |
| Wind | 10,667 | 30,636 | 7,374 | 48,677 |
| Solar | 1,268 | 369 | - | 1,637 |
| Biomass |  | 50 | 145 | 195 |
| Other | 950 | 1,480 | - | 2,430 |
| Grand Total | 19,866 | 51,934 | 25,023 | 96,823 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of April 30, 2009 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 10INR0025 | Mont Belvieu | IA | Chambers | South | May-09 | Gas-CT | 0 | Date |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Jul-09 | Gas-CC | 327 |  |
| 09INR0079 | Pearsall Expansion | IA | Frio | South | Aug-09 | Gas-CT | 200 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Aug-09 | Gas-CT | 48 | Date |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 09INR0028 | V H Braunig 6 | IA | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 08INR0012a | Papalote Creek Wind Farm | IA | San Patricio | South | Oct-09 | Wind | 180 | Date |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 11INR0015 | Panther Creek 3 | IA | Sterling | West | Nov-09 | Wind | 200 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Nov-09 | Coal | 855 | Date |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Dec-09 | Wind | 251 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 10INR0026 | Langford Wind Power | IA | Tom Green | West | Dec-09 | Wind | 150 |  |
| 06INR0029 | Jackson Mountain | IA | Nolan | West | Jan-10 | Wind | 90 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | May-10 | Coal | 855 | Date |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 09INR0045 | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-10 | Wind | 150 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-11 | Wind | 225 | Date |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1092 |  |
| 10INR0010 | Jack County 2 | PL | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | Nov-11 | Wind | 141 | Date |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 |  |
| 09INR0026 | Sterling Energy Center | IA | Sterling | West | Jun-12 | Wind | 300 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1001 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1792 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2700 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3200 |  |
|  |  |  |  |  |  |  | 25,023 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0044 | Concho | 200 | TBD | Wind |  | 06INR0022c | Kenedy | 200 | TBD | Wind |
| 09INR0064 | Borden | 41 | TBD | Wind |  | 08INR0042 | Coke | 200 | TBD | Wind |
| 08INR0041 | Coke | 200 | TBD | Wind |  | 09INR0005 | Calhoun | 280 | TBD | Other |
| 09INR0059 | Freestone | 20 | TBD | Coal |  | 09INR0025 | Concho | 180 | Jun-09 | Wind |
| 09INR0044 | Coke | 60 | Sep-09 | Wind |  | 10INR0027 | Nueces | 35 | Oct-09 | Wind |
| 09INR0075 | Kinney | 248 | Oct-09 | Wind |  | 09INR0055 | McCulloch | 299 | Oct-09 | Wind |
| 09INR0041 | Mitchell | 300 | Oct-09 | Wind |  | 07INR0014b | Wilbarger | 70 | Oct-09 | Wind |
| 07INR0014a | Wilbarger | 140 | Oct-09 | Wind |  | 09INR0048 | Jack | 150 | Oct-09 | Wind |
| 08INR0054 | Comanche | 401 | Oct-09 | Wind |  | 09INR0073 | Scurry | 200 | Nov-09 | Wind |
| 08INR0031 | Childress | 100 | Nov-09 | Wind |  | 11INR0013 | Mills | 150 | Dec-09 | Wind |
| 08INR0039 | Hamilton | 90 | Dec-09 | Wind |  | 11INR0012 | Duval | 400 | Dec-09 | Wind |
| 09INR0082 | Webb | 300 | Dec-09 | Wind |  | 09INR0065 | Webb | 150 | Dec-09 | Wind |
| 09INR0077 | Reagan | 500 | Dec-09 | Wind |  | 09INR0061 | Kent | 258 | Dec-09 | Wind |
| 09INR0058 | Howard | 250 | Dec-09 | Wind |  | 09INR0054 | Stonewall | 148.5 | Dec-09 | Wind |
| 09INR0051 | Borden | 249 | Dec-09 | Wind |  | 08INR0056 | Nolan | 149 | Dec-09 | Wind |
| 08INR0023 | Floyd | 100 | Dec-09 | Wind |  | 08INR0022 | Floyd | 100 | Dec-09 | Wind |
| 10INR0011 | Johnson | 275 | Jan-10 | Gas |  | 11INR0036a | Matagorda | 200 | Jan-10 | Wind |
| 11INR0033a | Cameron | 200 | Jan-10 | Wind |  | 10INR0047 | Kendall | 1000 | Jan-10 | wind |
| 10INR0048 | Hardeman | 1000 | Jan-10 | wind |  | 10INR0024 | Briscoe | 3000 | Jan-10 | Wind |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | wind |  | 10INR0045 | Webb | 734 | Apr-10 | wind |
| 10INR0054 | Palo Pinto | 36 | May-10 | Wind |  | 10INR0079 | Nolan | 60 | May-10 | Wind |
| 10INR0023 | Haskell | 386 | May-10 | Wind |  | 10INR0016 | Childress | 150 | May-10 | Wind |
| 09INR0070 | Reagan | 42 | May-10 | Wind |  | 09INR0069 | Reagan | 36 | May-10 | Wind |
| 09INR0035 | Concho | 750 | May-10 | Wind |  | 09INR0018 | Concho | 249 | May-10 | Wind |
| 07INR0032 | Tom Green | 249 | May-10 | Wind |  | 10INR0069 | Rusk | 818 | May-10 | Coal |
| 10INR0076 | Webb | 225 | May-10 | Wind |  | 10INR0029 | Hood | 810 | Jun-10 | Gas |
| 09INR0081 | Rusk | 818 | Jun-10 | Coal |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 10INR0052a | Knox | 21 | Jul-10 | Wind |  | 10INR0013 | Upton | 400 | Jul-10 | Wind |
| 10INR0038 | Glasscock | 350 | Aug-10 | Wind |  | 10INR0071 | Matagorda | 88 | Sep-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 09INR0074 | Motley | 70 | Oct-10 | Wind |  | 10INR0070 | Hunt | 50 | Nov-10 | Gas |
| 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |  | 10INR0039 | Dickens | 200 | Nov-10 | Wind |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 10INR0032 | Navarro | 800 | Dec-10 | Gas |
| 10INR0060 | Willacy | 400.5 | Dec-10 | Wind |  | 10INR0059 | Zapata | 250.7 | Dec-10 | Wind |
| 09INR0076 | Jackson | 300 | Dec-10 | Wind |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0049 | Pecos | 200 | Dec-10 | Wind |  | 10INR0033 | Armstrong | 420 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 09INR0031 | Ector | 275 | Dec-10 | Gas |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 07INR0026 | Baylor | 400 | Dec-10 | Wind |  | 07INR0017 | Erath | 210 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 11INR0036b | Matagorda | 200 | Jan-11 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0037 | Smith | 55 | May-11 | Biomass |
| 11INR0028 | Grimes | 1280 | May-11 | Gas |  | 11INR0046 | Brazoria | 300 | May-11 | Gas |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 10INR0009 | Castro | 200 | May-11 | Wind |  | 11INR0009 | Navarro | 1200 | Jun-11 | Gas |
| 09INR0050 | Fannin | 1200 | Jun-11 | Gas |  | 11INR0057 | Cameron | 144 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 11INR0040 | freestone | 749 | Aug-11 | Gas |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0008a | Roberts | 1000 | Sep-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 12INR0006 | Limestone | 875 | Jun-12 | Coal |
| 10INR0022 | Harris | 3500 | Jun-12 | Gas |  | 12INR0002 | Briscoe | 750 | Jul-12 | Wind |
| 12INR0016 | Nueces | 1200 | Nov-12 | Other |  | 08INR0019c | Gray | 250 | Nov-12 | Wind |
| 08INR0019b | Gray | 250 | Nov-12 | Wind |  | 08INR0019a | Gray | 250 | Nov-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 06INR0022b | Kenedy | 200 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1100 | Dec-12 | Wind |
| 11INR0023 | King | 400 | Dec-12 | Wind |  | 12INR0009 | Nueces | 875 | May-13 | Gas |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0006 | Gray | 750 | Oct-13 | Wind |
| 06INR0022e | Kenedy | 200 | Dec-13 | Wind |  | 14INR0002 | Goliad | 756 | Feb-14 | Coal |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 15INR0003 | Matagorda | 3200 | Jan-15 | Nuclear |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year					County Location of Installed Capacity and Interconnection Requests

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  The review of this project is complete and an ERCOT Recommendation Letter is in process.

# Luminant submitted a set of projects to reduce North to South Congestion.  It consists of several 138 kV line upgrades and series reactor installations.  The total cost for all projects is approximately $31 M. The review of this project is complete and a RPG Recommendation Letter has been completed and posted.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

- Austin Energy submitted a project to relocate the Decker to Techridge circuit to new ROW so that the existing structures can be utilized for the new Gilleland to Techridge circuit.  The estimated completion date of this project is November 2010 and estimated cost is $ 4.3 M.   This project is in ERCOT Independent Review.

# The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to construct a new 6.2 mile transmission line from Highway 123 to Cushman substation.  The estimated completion date of this project is June 2014 and estimated cost is $ 11.6 M.   This project is in ERCOT Independent Review.

# The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to construct a new 7.8 mile transmission line between the existing GPI and Parkway substations.  The estimated completion date of this project is June 2013 and estimated cost is $ 12.9 M.   This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to expand the Zenith substation, add one 800 MVA autotransformer, connect Zenith to existing circuits near the Gertie substation and upgrade/reconfigure nearby 138 kV circuits.  The estimated completion date of this project is summer 2012 and estimated cost is $ 26.6 M.   This project is in ERCOT Independent Review.

# American Electric Power Service Corporation submitted a project to construct several improvements in the Corpus Christi area.  The estimated completion date of this project is June 2012 and estimated cost is $ 214 M.   This project is in Study Mode.

# Other Notable Activities

- All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- ERCOT Regional Planning has begun work on the 2009 Five-Year Transmission Plan utilizing the latest SSWG base cases.  The conditioning phase is complete and the reliability phase has begun.

- Completed final RMR determination on Luminant Notice of Suspension of Operations (NSO) submission and recommended Permian Basin 5 and 6 for RMR.  Continued analysis of RMR need using cases with 300 and 414MW of western ERCOT wind generation.

- Base Case creation for the Voltage Ride-Through study has begun using standard SSWG base cases.  These base cases will be modified with a security constrained dispatch for two scenarios; high wind/high load and high wind/low load.

- Completed stability runs for DWG’s study of LaaR capability at 2300 MW of the responsive reserve service.

- The Annual Load Data Request (ALDR) training was held on January 21, 2009.

- TPIT05012009 individual worksheets were sent to TO’s for their updates and changes.  All data changes are due back to ERCOT by May 2, 2009.