## 814
EDI Completed? | Transaction | N | Original Guide Example # | Description | Detail | File Name | Comments | Assigned To | Reviewed?
Complete | 814_01 | Y | 1 | Enrollment Request – New CR to ERCOT | CR submits Enrollment Request to ERCOT Includes Request for Historical Summarized Usage CR Provides Customer Notification Name and Address for Enrollment Notification NOT a special Read date | 814_01_Example1 | Recommended using the DBA and the address overflow in the new examples (does not have to be on all but at least one from each group) - also recommended using 36 digits for the ESI ID to show max | Johnny | Yes
Complete | 814_01 | Y | 3 | Enrollment Request – New CR to ERCOT | CR submits Enrollment Request to ERCOT Includes a Waiver of Notification Includes a request for Historical Interval Usage Includes a request for a Special Meter Read for an early switch | 814_01_Example2 |  | Johnny
Complete | 814_01 | Y | 4 | Enrollment Request – New CR to ERCOT – FOR MUNI/CO-OP MARKET ONLY | CR submits Enrollment Request to ERCOT Includes Request for Historical Summarized Usage CR Provides Customer Notification Name, Customer Billing Information and Service Address for Enrollment Notification | 814_01_Example3 |  | Johnny | Yes
Complete | 814_02 | Y | 1 | Enrollment Reject Response – ERCOT to New CR | Enrollment request rejected Example shows multiple reject reasons | 814_02_Example1 |  | Johnny | Yes
Complete | 814_03 | Y | 2 | Switch CR Notification Request –ERCOT to TDSP -- see comments | ERCOT Enrollment Request Information to TDSP Off Cycle Switch Request Valid | 814_03_Example1 |  | Kathy
| 814_03 | Y | 3 | Switch CR Notification Request –ERCOT to TDSP– FOR MUNI/CO-OP MARKET ONLY -- see comments | ERCOT Enrollment Request Information to TDSP Off Cycle Switch Request Valid | 814_03_Example2
Complete | 814_03 | Y | 4 | Mass Transition Request from ERCOT - ERCOT to TDSP– FOR USE In ‘IOU’ MARKET ONLY -- see comments | ERCOT Enrollment Request Information to TDSP Off Cycle Switch Request for Mass Transition Valid | 814_03_Example3 |  | Kathy | Yes
Complete | 814_03 | Y | 5 | Mass Transition Request from ERCOT –ERCOT to TDSP– FOR USE IN ‘MUNI/CO-OP’ MARKET ONLY-- see comments | ERCOT Enrollment Request Information to MUNI/CO-OP TDSP Off Cycle Switch Request for Mass Transition Valid | 814_03_Example4 |  | Dave
| 814_04 | Y | 4 | Mass Transition Switch (Special Read for Switch Accepted) Accept Response –IOU TDSP to ERCOT (SEE COMMENTS) | IOU TDSP responds to Mass Transition Switch initiated by ERCOT with Premise Information Early Switch Request Accepted Example shows a single meter that measures Off Peak and Totalized Usage | 814_04_Example1
Complete | 814_04 | Y | 5 | Mass Transition Switch (Special Read for Switch Accepted) Accept Response –MUNI-CO-OP to ERCOT (SEE COMMENTS) | MOU/EC responds to Mass Transition Switch initiated by ERCOT with Premise Information Early Switch Request Accepted Example shows a single meter that measures Off Peak and Totalized Usage | 814_04_Example2 | Need assistance. We have not had a Mass Transition for a MOU/EC. Is it ok to create this transaction? - OK TO USE SAME OR CREATE | Dave
Complete | 814_05 | Y | 2 | Premise Information and Enrollment Accept Response – ERCOT to New CR (switch) | ERCOT forwards Premise Information and Start Date to New CR This example shows a response for Unmetered Services | 814_05_Example1 |  | Jonathan
| 814_05 | Y | 3 | Switch CR Notification Reject Response –ERCOT to New CR | TDSP rejects switch notification, ERCOT forwards rejection to new CR who submitted 814_01 or 814_16 | 814_05_Example2
Complete | 814_05 | Y |  | Premise Information and Enrollment Accept Response – ERCOT to New CR (MVI) |  | 814_05_Example3 |  | Jennifer | Yes
Complete | 814_05 | Y |  | Switch CR Notification Reject Response –ERCOT to New CR (MVI) |  | 814_05_Example4 |  | Jonathan
| 814_06 | Y | 1 | Drop Due to Switch Request – ERCOT to Current CR | ERCOT notifies the CR that customer has chosen another CR | 814_06_Example1
Complete | 814_07 | Y | 1 | Drop Due to Switch Accept Response – Current CR to ERCOT | Current CR Accepts Drop | 814_07_Example1 |  | Jennifer | Yes
Complete | 814_08 | Y | 1 | Cancel Switch Request – ERCOT to Current CR | ERCOT Notifies Current CR that the Switch to a New CR was Canceled Reinstating the customer with the Current CR | 814_08_Example1 |  | Jennifer
| 814_08 | Y | 2 | Cancel Switch Request – ERCOT to TDSP | ERCOT Notifies TDSP that the Switch to a New CR was Canceled Reinstating the customer with the Current CR | 814_08_Example2
Complete | 814_08 | Y | 4 | Cancel Switch Request – Current CR to ERCOT - Customer Initiated Move-Out Cancel | Current CR sends Cancel Switch Request to ERCOT Reinstating the customer with the Current CR ERCOT Restores Normal Read Cycles and Cancel Special Read Request | 814_08_Example3 |  | Johnny | Yes
Complete | 814_09 | Y | 3 | Cancel Switch Accept Response – TDSP to ERCOT | TDSP Accepts the Cancel Switch Notification | 814_09_Example1 |  | Kathy
| 814_09 | Y | 8 | Cancel Switch Reject Response – ERCOT to Current CR | ERCOT to Current CR Rejects the Cancel Switch Notification | 814_09_Example2
| 814_10 |  |  | No 814_10 Examples were accepted by TX SET
Complete | 814_11 | Y | 4 | Drop Accept Response – ERCOT to Current CR – Mass Transition | ERCOT Accepts Drop to AREP Request. TDSP accepts 814_03 and ERCOT forwards 814_14 to AREP and 814_11 to Current CR | 814_11_Example1 |  | Jennifer | Yes | Take out
Complete | 814_11 | Y |  | Drop Reject Response – ERCOT to Current CR – Mass Transition | ERCOT Rejects Drop to AREP Request. TDSP rejects 814_03 and ERCOT forwards original reject reason code to the Current CR in the 814_11. | 814_11_Example2 |  | Jennifer | Yes | Take out
Complete | 814_11 |  | 2 | Drop to AREP Reject Response – ERCOT to Current CR | ERCOT rejects Drop request from CR | 814_11_Example3 |  |  |  | Take out
| 814_12 | Y | 1 | Customer Changes Move-in Date Request – New CR to ERCOT | The customer makes a request to the New CR for a date change to the original move in request. The New CR sends the 814_12 to ERCOT requesting a change to the original move-in date. | 814_12_Example1
Complete | 814_13 | Y | 2 | Customer Changes Move-in Date Reject Response – ERCOT to New CR | ERCOT sends an 814_13 to the New CR to acknowledge the original move-in date change requested on the 814_12. | 814_13_Example1 |  | Jonathan | Yes
Complete | 814_13 | Y | 5 | Move-in Date Change Accept Response – TDSP to ERCOT | The TDSP sends an 814_13 Accept Response back to ERCOT in order to acknowledge the requested change to the service start date resulting from the request for change to the original move-in date by the customer | 814_13_Example2 |  | Jennifer
| 814_14 | Y | 4 | Drop Enrollment Request – ERCOT to POLR or Designated CR | ERCOT sends an 814_14 Notice of Pending Customer Enrollment Information to the Provider of Last Resort (or designated CR) as part of a Mass Transition event. In this example, ERCOT has included the optional RL code and DTM 376 indicating that the new CR shall immediately submit a Move-Out for this ESI ID for the requested move-out date indicated in the DTM 376. | 814_14_Example1
Complete | 814_14 | Y | 5 | Drop Enrollment Request – ERCOT to POLR or Designated CR – USE IN ‘MUNI/CO-OP’ MARKET ONLY | ERCOT sends an 814_14 Notice of Pending Customer Enrollment Information to the Provider of Last Resort (or designated CR) as part of a Mass Transition event. ESI ID is for MOU/EC Market therefore Membership ID is required. | 814_14_Example2 | Accepted | N/A
Complete | 814_15 | Y | 3 | Drop Enrollment Accept Response – POLR (or designated CR) to ERCOT | The POLR (or designated CR) sends back an 814_15 Accept response to the 814_14 Drop Enrollment Request for a Mass Transition event. | 814_15_Example1 |  | Jonathan
| 814_16 | Y | 3 | Move-in (With Request for Historical Detail Interval Usage) Request – New CR to ERCOT | CR Submits Move In Request Historical Interval Usage Requested | 814_16_Example1
| 814_16 | N | 4 | Move-in (No Request for Historical Usage) Request – New CR to ERCOT FOR MUNI/CO-OP MARKET ONLY | CR Submits Move In Request No Historical Usage Requested | 814_16_Example2 | ERCOT can only find an 814_16 with Historical Usage (example above) do we want to keep this and just create it or remove it from the list? NOT NEEDED
Complete | 814_17 | Y | 3 | Move-in (With Request for Historical Detail Interval Usage) Reject Response – ERCOT to New CR | This scenario, from ERCOT to the New CR, is used to reject the 814_16 (Move In with Detail Historical Interval Usage Request) when the transaction does not pass validation. | 814_17_Example1 |  | Monica
| 814_18 | Y | 1 | Establish CSA CR Request – New CSA CR to ERCOT | This scenario, from the New CSA CR to ERCOT, is used to establish the owner/controller’s New CSA CR in ERCOT’s database. | 814_18_Example1
Complete | 814_18 | Y | 2 | Delete CSA CR Request – Current CSA CR to ERCOT | This scenario, from the Current CSA CR to ERCOT, is used to remove an existing CSA CR from ERCOT’s database. Owner/controller no longer wants CSA agreement with the CR. | 814_18_Example2 |  | Jennifer | Yes
Complete | 814_18 | Y | 4 | Establish CSA CR Request –ERCOT to MCTDSP | This scenario, from ERCOT to the MCTDSP, is used to request the acceptance of a new CSA. | 814_18_Example3 |  | Dave
| 814_19 | Y | 1 | Establish CSA CR Accept Response – ERCOT to New CSA CR | This scenario, from ERCOT to the New CSA CR, is used to provide response to the 814_18 (Establish/Delete CSA CR Request), enrolling the New CSA CR in ERCOT’s database. | 814_19_Example1
Complete | 814_19 | Y | 5 | Establish CSA CR Accept Response – MCTDSP to ERCOT | This scenario, from the MCTDSP to ERCOT is used to reject the 814_18 (Establish/Delete CSA CR Request) when the transaction does not pass validation in the TDSPs system. | 814_19_Example2 |  | Eloise
Complete | 814_20 | Y | 1 | Create ESI ID Request – TDSP to ERCOT | TDSP submits Create ESI ID Request to ERCOT | 814_20_Example1 |  | Kathy
| 814_20 | Y | 2 | Maintain ESI ID Notification Request – ERCOT to Current CR | ERCOT forwards meter exchange data the Current CR Example includes a change in Load Profile as a result of the Meter Exchange ERCOT stores the Load Profile change and forwards the all information to CR | 814_20_Example2
Complete | 814_20 | Y | 3 | Retire ESI ID Request – TDSP to ERCOT | TDSP to ERCOT Retire an ESI ID | 814_20_Example3 |  | Cary | Yes
Complete | 814_20 | Y | 4 | Maintain ESI ID Request – TDSP to ERCOT | TDSP to ERCOT Change ESI ID information – Read Cycle | 814_20_Example4 |  | Kathy
| 814_20 | Y | 5 | Maintain ESI ID Notification Request – ERCOT to Current CR | ERCOT to Current CR Change ESI ID information – Notification of a Change in Read Cycle ERCOT Forwards Change in Read Cycle to Current CR | 814_20_Example5
Complete | 814_20 | Y | 6 | Maintain ESI ID Request – TDSP to ERCOT | TDSP to ERCOT Change ESI ID information – Special Needs Indicator | 814_20_Example6 |  | Cary | Yes
Discuss | 814_20 | Y | 9 | Maintain ESI ID Notification Request – ERCOT to Current CR | ERCOT forwards meter update data to Current CR Example includes a change in meter type in addition to Load Profile Change ERCOT stores only the Load Profile information and will still forward all of the information to CR | 814_20_Example7 | Kathy will find example for Kathryn of TDSP to ERCOT and change it to look like the ERCOT to CR
| 814_20 | Y | 10 | Maintain ESI ID Request – TDSP to ERCOT | TDSP to ERCOT Change ESI ID information – Load Profile: No Meter Set | 814_20_Example8
Complete | 814_21 | Y | 1 | Create ESI ID Accept Response – ERCOT to TDSP | ERCOT to TDSP Create ESI ID Request is Accepted | 814_21_Example1 |  | Cary | Yes
Complete | 814_21 | Y | 3 | Maintain ESI ID Notification Accept Response – Current CR to ERCOT | CR to Current ERCOT Change ESI ID information – Notification of a Change in Read Cycle CR Accepts Change in Read Cycle forwarded from ERCOT | 814_21_Example2 |  | Kim
| 814_22 | Y | 1 | Tenant Move Out – Revert to CSA CR Request – ERCOT to CSA CR | ERCOT to CSA CR Tenant Initiated Customer Move Out Used to start service of the ESI ID with the CSA CR | 814_22_Example1
Complete | 814_23 | Y | 1 | CSA CR Move In Accept Response – CSA CR to ERCOT | CSA CR to ERCOT Accept Response for CSA CR Move In | 814_23_Example1 |  | Jonathan | Yes
Complete | 814_24 | Y | 1 | Move Out Request – CR to ERCOT | CR submits Move Out Request to ERCOT Used for notification of a customer’s move-out request | 814_24_Example1 |  | Johnny
| 814_24 | Y | 2 | Move Out Request – ERCOT to TDSP | ERCOT forwards Move Out Request to TDSP Used for notification of a customer’s move-out request Essentially a pass through of the customer’s move-out request | 814_24_Example2
Complete | 814_24 | Y | 4 | Move Out Request – ERCOT to MC- TDSP | ERCOT forwards Move Out Request to MC-TDSP Used for notification of a customer’s move-out request Essentially a pass through of the customer’s move-out request | 814_24_Example3 |  | Dave
Complete | 814_25 | Y | 1 | Move Out Accept Response – ERCOT to CR | ERCOT submit accept response to CR Used to acknowledge receipt of the 814_24 Move-out Request | 814_25_Example1 |  | Johnny
| 814_25 | Y | 3 | Move Out Accept Response – TDSP to ERCOT | TDSP submit accept response to ERCOT Used to acknowledge receipt of the 814_24 Move-out Request | 814_25_Example2
Complete | 814_25 | Y | 5 | Move Out Reject Response – ERCOT to CR (Forwarded from TDSP) | ERCOT forwards TDSP’s reject response to CR Used to reject receipt of the 814_24 Move-out Request | 814_25_Example3 |  | Kathy | Yes
Complete | 814_26 | Y | 1 | Ad-Hoc Historical Usage Request – CR to ERCOT | CR submits Ad-Hoc request for 12-monhts of Historical Usage to ERCOT Used to request Historical Summarized Usage (HU) on an ESI ID (interval summary or unmetered services or non-interval detail) | 814_26_Example1 |  | Jennifer
| 814_26 | Y | 3 | Ad-Hoc Historical Usage Request – ERCOT to TDSP | ERCOT forwards Ad-Hoc request for 12-monhts of Historical Usage to TDSP Essentially a pass through form the ERCOT of the CR’s Request Used to request Historical Summarized Usage (HU) on an ESI ID (interval summary or unmetered services or non-interval detail) | 814_26_Example2
Complete | 814_27 | Y | 2 | Ad-Hoc Historical Usage Accept Response – ERCOT to CR | ERCOT submits Accept Response to Ad-Hoc request for 12-months of Historical Usage to CR Essentially as pass through of the TDSP’s response to the CR Historical Summarized Usage (HU) on an ESI ID | 814_27_Example1 |  | Jennifer | Yes
Complete | 814_27 | Y | 4 | Ad-Hoc Historical Usage Accept Response – TDSP to ERCOT | TDSP submits Accept Response to Ad-Hoc request for 12-months of Historical Usage to ERCOT Essentially as pass through of the TDSP’s response to the CR Historical Summarized Usage (HU) on an ESI ID | 814_27_Example2 |  | Jennifer
| 814_28 | Y | 1 | Permit Required – TDSP to ERCOT | TDSP notifies ERCOT that Move-In Request is suspended due to Permit Required. | 814_28_Example1
Complete | 814_28 | Y | 2 | Completed Unexecutable– TDSP to ERCOT | TDSP notifies ERCOT that Move-In Request is Completed Unexecutable | 814_28_Example2 |  | Kathy | Yes
Complete | 814_29 | Y | 2 | Accept Response Permit Required or Completed Unexecutable – Current CR to ERCOT | Current CR notifies ERCOT of an Accept Response on a Move-Out. | 814_29_Example1 |  | Jennifer
| 814_PC | Y | 1 | Maintain Customer Information Request – CR to TDSP | CR submits Maintain Customer Information Request to the TDSP Residential Example with all potential contact information populated | 814_PC_Example1
Complete | 814_PC | Y | 2 | Maintain Customer Information Request – CR to TDSP | CR submits Maintain Customer Information Request to the TDSP Commercial Example | 814_PC_Example2 |  | Jennifer | Yes
Complete | 814_PC | Y | 4 | Maintain Customer Information Request – CR to MC TDSP | CR submits Maintain Customer Information Request to the MC TDSP Residential Example with all potential contact information populated and a change to billing type. | 814_PC_Example3 |  | Dave
| 814_PC | Y | 5 | Maintain Customer Information Request –MCTDSP to CR | MCTDSP submits Maintain Customer Information Request to the CR Residential Example with all potential contact information populated and a change to billing type. | 814_PC_Example4
Complete | 814_PD | Y | 1 | Maintain Customer Information Accept Response – TDSP to CR | TDSP Accept Response | 814_PD_Example1 |  | Kathy | Yes

## 810
EDI Completed? | Transaction | N | Original Guide Example # | Description | File Name | Comments | Assigned To | Reviewed?
Complete | 810_02 | Y | 1 | Invoice, including Service Order charges, Interest Charge and Interest Credit, stated at a RATE level - New examples need to COMBINE RATE AND ACCOUNT LOOP EXAMPLES | 810_02_Example1 |  | Kathy | Yes
| 810_02 | Y | 2 | Invoice, including Service Order charges, stated at an ACCOUNT level - New examples need to COMBINE INTO ONE EXAMPLE SHOWING ACCOUNT AND RATE LEVEL CHARGES. | 810_02_Example2
Complete | 810_02 | Y | 4 | Late Payment Charge Invoice including late payment charges for several unpaid invoices Outstanding Discretionary Charge | 810_02_Example3 |  | Kathy
| 810_02 | Y |  | 810 - Billing Example of Lights (Prorated) - Correct example to look like all other 810 examples | 810_02_Example4
Complete | 810_02 | Y | 6 | Billing for Usage Invoice Correction | 810_02_Example7_Step1_Original 810_02_Example7_Step2_Cancel 810_02_Example7_Step3_Replace |  | Kathy | Yes
Complete | 810_02 | Y | 7 | Invoice Correction | 810_02_Example6_Step1_Original 810_02_Example6_Step2_Cancel 810_02_Example6_Step3_Replace |  | Monica
Complete | 810_03 | Y | 1 | Invoice, including Energy Charge with Service Order Charge | 810_03_Example1 |  | Eloise
Complete | 810_03 | Y | 2 | Cancel Delivery Invoice - MCTDSP | 810_03_Example2 |  | Eloise
Complete | 810_03 | Y | 3 | Delivery: Prior Balance / Late Payment Charge - MCTDSP | 810_03_Example3 |  | Dave
Per MCTDSP this is not a valid example | 810_03 | N | 4 | Pro-ration of Outdoor Lighting | 810_03_Example4 | Not valid in MOU/EC

## 820
EDI Completed? | Transaction | N | Original Guide Example # | Description | File Name | Comments | Assigned To | Reviewed?
Complete | 820_02 | Y | 1 | TDSP sends invoice, then cancels the invoice and sends a re-bill invoice that is less than the original invoice amount after the due date of the original invoice. | 820_02_Example1_Step1 820_02_Example1_Step2 |  | Kathy | Yes
Complete | 820_02 | Y | 3 | TDSP sends invoice, then cancels the invoice and sends a re-bill invoice that is more than the original invoice. | 820_02_Example2_Step1 820_02_Example2_Step2 |  | Kathy
| 820_02 | Y | 4 | CR takes credit for a Late Payment charge that has already been paid and then cancelled by the TDSP. | 820_02_Example3
Complete | 820_02 | Y | 6 | CR Partially pays a Late Payment Invoice. | 820_02_Example4 |  | Kathy | Yes
Complete | 820_03 | Y | 1 | Remittance Detail –MCTDSP to CR | 820_03_Example1 |  | Dave

## 650
EDI Completed? | Transaction | N | Original Guide Example # | Description | Detail | File Name | Comments | Assigned To | Reviewed?
Complete | 650_01 | Y | 3 | Disconnect for Non-Pay Request - CR to TDSP | CR submits Disconnect for Non-Pay request Includes Premium Disconnect Location | 650_01_Example1 | includes MTR instead of PDL | Jennifer | Yes
Complete | 650_01 | Y | 6 | Reconnect when CR did not initiate the Disconnect - CR to TDSP | CR request the TDSP to reconnect service when CR did not initiate the Disconnect service transaction | 650_01_Example2 |  | Jennifer | Yes
| 650_01 | Y | 7 | Reconnect for Non-Pay | CR submits a reconnect for Non-Pay After the Disconnect for Non-Pay has been sent to the TDSP | 650_01_Example3
Complete | 650_02 | Y | 3 | Disconnect for Non-Pay Completion Response - TDSP to CR | TDSP submits Disconnect for Non-Pay Completion Response | 650_02_Example1 |  | Ed
Complete | 650_02 | Y | 7 | Disconnect for Non-Pay Complete Unexecutable Response - TDSP to CR | TDSP submits Complete Unexecutable Response | 650_02_Example3 |  | Ed
Complete | 650_02 | Y | 9 | Reconnect for Non-Pay Complete Unexecutable Response - TDSP to CR | TDSP receives Reconnect for Non-Pay prior to completing Disconnect for Non-Pay No one dispatched, no fee associated. | 650_02_Example2 |  | Kathy
Complete | 650_02 | Y |  | WILL ALSO NEED AN EXAMPLE OF A COMPLETE RECONNECT RESPONSE |  | 650_02_Example7 |  | Ed
Complete | 650_04 | Y | 1 | Suspension of Delivery Services - TDSP to CR | TDSP submits Suspension of Delivery Services | 650_04_Example1 |  | Jonathan
| 650_04 | Y | 4 | Permanent Suspension of Services - TDSP to CR | TDSP submits Permanent Suspension | 650_04_Example2
Complete | 650_04 | Y | 5 | Suspension of Delivery Services - MCTDSP to CR | MCTDSP submits Suspension of Delivery Services (Permanent disconnect – CR must submit 814_24 MVO for ESI ID) | 650_04_Example3 |  | Dave
Complete | 650_04 | Y | 6 | Disconnect for Non-pay - MCTDSP to CR | MCTDSP submits Disconnect for Non-payment | 650_04_Example4 |  | Dave
| 650_04 | Y | 7 | Reconnect for Non-pay - MCTDSP to CR | MCTDSP reconnects ESI ID previously Disconnected for Non-payment | 650_04_Example5
complete | 650_05 | Y |  | Example was not accepted by TX SET |  | 650_05_Example1 |  | Kathy | Yes

## 824
EDI Completed? | Transaction | N | Original Guide Example # | Description | Detail | File Name | Comments | Assigned TO | Reviewed?
Complete | 824 | Y | 1 | Application Advice – CR to TDSP | CR submits 824 Application Advice to TDSP Rejection of 810 Invoice | 824_Example1 | Example has ABO not CRI as reject reason | Jennifer | Yes
Complete | 824 | Y | 2 | Application Advice –ERCOT to TDSP | ERCOT submits 824 Application Advice to TDSP Rejection of 867 Monthly Usage | 824_Example2 | Example provided by Market has DDM not A76 as reject reason | Steve
| 824 | Y | 3 | Application Advice – CR to ERCOT | CR submits 824 Application Advice to ERCOT Rejection of 867 Monthly Usage Multiple Rejection Reasons | 824_Example3

## 867
EDI Completed? | Transaction | N | Original Guide Example # | Description | Detail | File Name | Comments | Assigned to | Reviewed?
Complete | 867_02 | Y | 1 | Historical Usage NON-INTERVAL METERS | ERCOT to CR Summarized Historical Usage for Non-Interval Metered Services Months of July and August | 867_02_Example1 |  | Kathy | Yes
Complete | 867_02 | Y |  | Historical Usage UNMETERED SERVICES | ERCOT to CR Summarized Historical Usage for two Un-Metered Services Values for multiple months July and August | 867_02_Example2 |  | Jonathan
| 867_02 | Y |  | Historical Usage INTERVAL METERS | ERCOT to CR Detail Historical Usage for Interval Reporting for a Meter by Interval Values for the months July and August | 867_02_Example3
| 867_02 | N |  | NON-INTERVAL METERS, METER CHANGE OUT – MIXED VALUES | ERCOT to CR Historical Usage for (one month) a Partial Month of Non-Interval Metered Services Meter Exchange to an Interval Meter and the remainder of the Month Reporting Interval Usage | 867_02_Example4 | Need Assistance in Finding NOT NEEDED
Complete (with assistance of CNP) Is there value since this is requesting months of July and August? | 867_02 | Y |  | Historical Usage INTERVAL METERS, MULTIPLE CHANNELS | ERCOT to CR Detail Historical Usage for Interval Reporting for a Meter with Multiple Channels by Interval Values for the months July and August | 867_02_Example5 | NOT NEEDED | Johnny
| 867_03 | Y | 1 | Monthly Usage NON-INTERVAL – ORIGINAL | TDSP to ERCOT Original Monthly Detailed and Summarized Usage | 867_03_Example1
Complete | 867_03 |  |  | Need to included examples of Power Factor 867_03 transactions |  | 867_03_Example2 |  | Ed
Complete | 867_03 | Y | 2 | Monthly Usage NON-INTERVAL – CANCELLATION | TDSP to ERCOT Cancellation of Monthly Usage for Non-Interval Detail and Summarized Usage | 867_03_Example3 |  | Steve
Complete | 867_03 | Y |  | Need to include example providing the Ingore Flag for REF~Meter Role example for distributed generation ns |  | 867_03_Example4 |  | Kim
Complete | 867_03 | Y | 3 | Monthly Usage NON-INTERVAL – ORIGINAL, FINAL BILL | TDSP to ERCOT Original Final Usage for Non-Interval Detail and Summarized Usage | 867_03_Example5 |  | Ed
Complete | 867_03 | Y | 4 | Monthly Usage UN-METERED SERVICES – ORIGINAL | TDSP to ERCOT Original Un-Metered Services Usage Detail and Summerized Usage Report One Unmetered Device Type on a ESI-ID one Mercury Vapor | 867_03_Example6 | SODIUM NOT MERCURY VAPOR - TX SET SAYS OK | Cary
Complete | 867_03 | Y | 6 | Monthly Usage INTERVAL – ORIGINAL | ERCOT to CR Interval Summary, Detail, and Summary Across Meters Monthly Usage Report | 867_03_Example7 | Need Assistance in Finding USE EXAMPLE THAT IS THERE NOW | Johnny
Complete | 867_03 | Y | 7 | Monthly Usage NON-INTERVAL – ORIGINAL-TIME OF USE METERS | TDSP to ERCOT Original Monthly Detailed and Summarized Usage Non-Interval Meter that ismeasuring Time Of Use Meters Power Factor not measured | 867_03_Example8 |  | Ed
Per description TDSPs to look at and determine if still correct | 867_03 | Y | 8 | Monthly Usage NON-INTERVAL – MULTIPLE METERS – METERS- CONSUMPTION TO ERCOT CONTAINS ADJUSTMENT -- TDSPs need to relook at this example to determine if it is still valid, if so, is the example correct? | TDSP to ERCOT Original Monthly Detailed and Summarized Usage Non-Interval Meter with Three Meters Power Factor not measured | 867_03_Example9 |  | See if Cary or Ed has example of this
| 867_03 | N | 9 | Monthly Usage INTERVAL – ORIGINAL-ERCOT POLLED – SEPTEMBER-DAILY EXAMPLE | ERCOT to CR Interval Usage Summary Across Meters Daily Usage Report Summary Across Meters is for the load associated with Generation Meters Note: ERCOT Will send this same transaction to the TDSP | 867_03_Example10 | Need Assistance in Finding NOT NEEDED
Complete | 867_03 | Y | 10 | Monthly Usage NON-INTERVAL – MASTER METER – INCLUDING MASTER METER/SUBTRACTIVE METERING WHEN THE MASTER METER IS ON A DIFFERENT ESI ID THAN THE SUBTRACT METER- - CONSUMPTION TO ERCOT CONTAINS NET USAGE -- | TDSP to ERCOT Original Monthly Detailed and Summarized Usage Non-Interval Meter that is measured at the Master meter and includes the subtractive meters (totalized across all subtract meters (1-##)) | 867_03_Example11 |  | Ed
sent to TDSP (CNP does not have example) | 867_03 | Y | 11 | Monthly Usage INTERVAL – MASTER METER – INCLUDING MASTER/SUBTRACTIVE METERING WHEN THE MASTER METER IS ON A DIFFERENT ESI ID THAN THE SUBTRACT METER- - CONSUMPTION TO ERCOT CONTAINS ADJUSTMENT -- | TDSP to ERCOT Original Monthly Detailed and Summarized Usage Interval Meter that is measured at the Master meter and includes the subtractive meters (totalized across all subtract meters (1-##)) | 867_03_Example12 | Kathryn will ask Ed and Cary if they have examples
| 867_03 | Y | 12 | Monthly Usage NON-INTERVAL –METER – INCLUDING METERING CONSUMPTION ADJUSTMENT - CONSUMPTION TO ERCOT CONTAINS ADJUSTMENT | TDSP to ERCOT Original Monthly Detailed and Summarized Usage Non-Interval Meter where the meter did not register kWh’s due to diversion above the meter. The meter is fine and it is determined/estimated that 1000 kWh’s should be added due to electricity being used that did not pass through the meter. | 867_03_Example13
| 867_03 | Y | 13 | Note: This example starts at the PTD level. Scenario 1 (Lights are prorated) | Note-- need to show the complete 867_03 under the unmetered example for a streetlight service/premise. | 867_03_Example14
Complete | 867_03 | Y | 14 | METER EXCHANGE NON-INTERVAL to NON-INTERVAL – ORIGINAL | TDSP to ERCOT The TDSP completes a meter exchange for a Residential Premise during the month. This exchange replaces a non-interval Residential meter with a non-interval Residential meter. The TDSP sends the Original Monthly Detailed and Summarized Usage containing the meter exchange to ERCOT. | 867_03_Example15 |  | Cary
| 867_03 | Y | 15 | METER EXCHANGE kWh INTERVAL to kWh INTERVAL– ORIGINAL | ERCOT to CR The TDSP completed a meter exchange for a large commercial customer during the month. The TDSP replaced an IDR meter with and an IDR meter. ERCOT forwards to the CR the Interval Summary, Detail, and Summary Across Meters Monthly Usage Report This example shows kWh only. | 867_03_Example16
Complete | 867_03 | Y | 16 | METER EXCHANGE kWh and kVARH INTERVAL to kWh and kVARH INTERVAL– ORIGINAL | ERCOT to CR The TDSP completed a meter exchange for a large commercial customer during the month. The TDSP replaced an IDR meter with an IDR meter. ERCOT forwards to the CR the Interval Summary, Detail, and Summary Across Meters Monthly Usage Report This example shows kWh and kVARH. | 867_03_Example17 |  | Kathy | Yes
Complete | 867_03 | Y | 17 | Monthly Usage NON-INTERVAL – ORIGINAL with First Month that Denial of Access Occurred | TDSP to ERCOT Original Monthly Detailed and Summarized Usage; includes Denial of Access Estimated Meter Read | 867_03_Example18 |  | Jennifer
Complete | 867_03 | Y | 18 | Monthly Usage NON-INTERVAL – ORIGINAL with Denial of Access Occurred and TDSP Estimation Occurrences | TDSP to ERCOT Original Monthly Detailed and Summarized Usage; includes Second Month that Denial of Access Occurred and TDSP Estimation Occurred One Month in Between the Two Denial of Access Occurrences | 867_03_Example19 |  | Jennifer
Complete | 867_03 | Y | 19 | Monthly Usage NON-INTERVAL – Replacement | TDSP to ERCOT Replacement Monthly and Summary Usage Sent After Cancel | 867_03_Example20 |  | Cary
Complete | 867_04 | Y | 1 | Initial Meter Read Notification METERED SERVICES | TDSP to ERCOT Used to send the initial/start read and date upon completion of a Cycle or Off-Cycle Switch or Move-In Essentially a pass through from the TDSP to the CR | 867_04_Example1 |  | Steve
| 867_04 | Y | 2 | Initial Meter Read Notification METERED SERVICES – 3 METERS (INCLUDING A TIME-OF-USE, ALL REGISTER READINGS) – Off –Cycle Switch | TDSP to ERCOT Used to send the initial/start read and date upon completion of a Cycle or Off-Cycle Switch or Move-In Essentially a pass through from the TDSP to the CR | 867_04_Example2
Complete | 867_04 | Y | 4 | Initial Meter Read Notification UNMETERED SERVICES | TDSP to ERCOT Used to send the initial/start read and date upon completion of a Cycle or Off-Cycle Switch or Move-In Essentially a pass through from the TDSP to the CR | 867_04_Example3 |  | Cary | Yes
| 867_04 | Y | 5 | Initial Meter Read Notification METERED SERVICES – INTERVAL METER- CYCLE SWITCH | TDSP to ERCOT Used to send the initial/start read and date upon completion of a Cycle or Off-Cycle Switch or Move-In Essentially a pass through from the TDSP to the CR | 867_04_Example4