## Slide 1: Single Entry Model (SEM) Go-Live Update
http://nodal.ercot.com <number>
TAC Update
June 4, 2009

## Slide 2: SEM Go-Live
http://nodal.ercot.com <number>
Summary of current SEM Activities
Consider changes to SEM Go-Live Procedure:
  Address posting of Network Operations Model
  Address approval of SEM Go-Live without TPTF
  Possible Vote on SEM Go-Live Procedure changes
Appendix
  What is SEM Go-Live?
  Market Engagement/Communications
  Training Update
  SEM Go-Live Criteria
  Transition summary during June – August 2009
  Next steps

## Slide 3: Summary of current SEM Activities
http://nodal.ercot.com <number>
ERCOT has kicked-off the Single Entry Model Implementation for TSPs
  May 28- SEM Market Kick-off Call
  June 4- Begin weekly ERCOT/TSP market calls for SEM
  June 8- ERCOT deploys test system for TSP testing
  June 23- First training class (3-day class, 6 weeks of classes)
  August 31- SEM Go-Live milestone
In the coming weeks ERCOT will report progress on testing and training to NDSWG, ROS, and TAC
  More details of SEM Go-Live in the Appendix
The processes and approvals leading up to this go-live activity are outlined in the SEM Go-Live Procedure, which were approved by TPTF and TAC in Aug/Sep 2008
  http://nodal.ercot.com/readiness/golive/index.html

## Slide 4: Consider changes to SEM Go-Live Procedure
http://nodal.ercot.com <number>
Two issues brought to TAC last month were basis for redlines to the SEM Go-Live Procedure
Issue #1: Go-Live Procedure calls for ERCOT to post the Network Operations Model on or before 8/31/09
  Confidentiality concerns expressed by TAC in May
    Disclosure of resource RARF data to all MPs
    Nodal protocols would not be in effect
  TAC asked ERCOT to present this issue to ROS and WMS
  Both ROS/WMS had similar concerns:
    Posting Resource/RARF data with many months of Zonal market remaining (too early)
    Recommended careful attention to disclosure of Private Use Network load data at any date
  Motion from WMS to “Move to limit postings to only TSPs”
  Redlines made to procedure to specify posting for TSP (interim solution)

## Slide 5: Consider changes to SEM Go-Live Procedure (continued)
http://nodal.ercot.com <number>
Issue #2 Procedure calls for TPTF/TAC/BOD approval prior to SEM Go-Live
  Redlines made to change TPTF to ROS for approval
TAC could consider motion to amend SEM Go-Live Procedure as modified and posted with TAC materials
  Note that the SEM Go-Live approval will be a squeeze-play in August
    Heads-up to TAC that many SEM Go-Live criteria will not be met until August
    May require email votes or conditional approvals from ROS/TAC/BOD

## Slide 6: Next steps
http://nodal.ercot.com <number>
  Possible TAC vote to change SEM Go-Live Procedure as amended and posted with TAC materials to accommodate changes to model posting and approval from TPTF to ROS stakeholder groups.
  ERCOT will continue to provide SEM updates to TAC and escalate issues through NDSWG/ROS/TAC
  Questions?

## Slide 7
http://nodal.ercot.com <number>
  APPENDIX
  What is SEM Go-Live?
  Market Engagement/Communications
  Training Update
  SEM Go-Live Criteria
  Transition summary during June – August 2009
  Next steps

## Slide 8: SEM Go-Live Overview
http://nodal.ercot.com <number>
Single Entry Model (SEM) Go-Live is the switchover on Aug 31, 2009 for TSP submissions of network operations model change requests
  from “Service Request” submissions via TML
  to “NOMCR” submissions via the NMMS
    System of record for model changes becomes NOMCRs on 8/31//09
    System of record for Network operations Model for reliability and dispatch remains Zonal/Genesys system until Dec 2010
TSP
Current Activity
Submit Modeling
Change via Service Request
ERCOT Uploads
Svc Request
into Zonal
Genesys Model
ERCOT Copies/Converts
Zonal Model “seed”
Into Nodal
NMMS Model
TSP
Aug 31, 2009
Submit Modeling Change via
NOMCR/NMMS Tool
(includes ICCP)
ERCOT Incrementally
Converts NOMCR
Into Svc Req
Uploads into Zonal
Genesys Model
ERCOT uploads
NOMCR
Into Nodal
NMMS Model to
support nodal testing
Data Consistency Checks are run to
ensure model synchronization/fidelity
Periodic checks are run to
ensure model synchronization/fidelity
Full
Copy
Incr.
NOMCR

## Slide 9: Current Network Operations Model Maintenance for TSPs
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
Submits Service Request to Change Model
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
Periodic full copy and conversion of model
(zonal seed used for nodal systems)
TSP
Notes: <number>
<number>

## Slide 10: After 8/31/2009: SEM Go-Live Network Operations Model Maintenance for TSP
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
ERCOT enters NOMCRs into zonal model
ERCOT runs consistency checks to ensure models are aligned and maintained
Submits Model Change Request (NOMCR)
TSP
NMMS Model
System of Record
Nodal Go-Live 12/1/2010
Notes: <number>
<number>

## Slide 11: Network Operations Model Maintenance for Resource & QSE (today and post 8/31/09)
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
ERCOT enters into zonal model
NMMS Model
System of Record
Nodal Go-Live 12/1/2010
Submits RARF
(Resource Asset Reg Form)
via Service Request
Submits ICCP Change
via Service Request
ERCOT process
QSE
RE
Notes: <number>
<number>

## Slide 12: Market Engagement / Communications
http://nodal.ercot.com <number>
The processes and approvals leading up to this activity were outlined in the SEM Go-Live Procedure approved by TPTF and TAC in Aug/Sep 2008
  http://nodal.ercot.com/readiness/golive/index.html
ERCOT has engaged and presented updates to the following groups, and will do so monthly moving forward:
  NDSWG- Jan, Feb, Mar, April
    Market SMEs review artifacts and training agenda
  ROS- Feb, April
    High level reports of schedule, metrics, and criteria status
Metrics-
  MP13 – MP Completes Nodal Operations Training
    Measure of training attendance for MPs
  MP14-B EDS2-Rel4 Trials Participation
    Measure of testing participation- target 95% of aTSPs

## Slide 13: Market Engagement / Communications
http://nodal.ercot.com <number>
Coming into critical window of final Zonal->Nodal model transformation, market training, application roll-out

## Slide 14: Training Update
http://nodal.ercot.com <number>
TSP Testing and Training environments will be the same
Testing system access
  Available June 8 – Aug 10
  NOMCR testing system will be on-line and available to all TSPs
  ERCOT will establish dedicated email and have staff available to support questions (nomcrhelp@ercot.com)
Instructor Led Training to be hosted in Taylor
  Pre-SEM classes June 22 – Aug 3
    Current plans for at least six 3-day sessions
    Planning for 12-18 seats for each class
    Large dedicated training room
  Post-SEM classes Sept 23- Oct 20
    Fewer sessions and smaller classes (tbd)
    Make-up classes, not just-in-time training for all staff after go-live

## Slide 15: SEM Go-Live Criteria
http://nodal.ercot.com <number>
SEM Go-Live Criteria defined in the SEM Go-Live Procedure http://nodal.ercot.com/readiness/golive/index.html
Section 4- The following entry criteria shall be met for SEM Go-Live
  TSPs & ERCOT complete EDS 2 Release 4 activities (next page)
  Nodal network model validated and approved as baseline for SEM Go-Live by ERCOT System Ops and Market Ops Directors
  ERCOT publishes CIM model to be used for SEM Go-Live
  ERCOT sufficiently staffed for maintenance of nodal & zonal systems
  Nodal EMS is capable of consuming NMMS CIM files through the EMS CIM importer for use in the Nodal EMS application suite
  SEM Go-Live readiness approved by TPTF, TAC and ERCOT BOD
    presume ROS approval in place of TPTF
  ERCOT publishes the following documents for TSPs
    ERCOT Network Operations Model validation whitepaper
    ERCOT Network Operations Model validation results
    NMMS Modeling Guidelines / Validation Rules document
    Latest CIM data dictionary and schema

## Slide 16: SEM Go-Live Criteria (cont’d)
http://nodal.ercot.com <number>
  All TSPs complete EDS 2 Release 4 activities
    MPs have enrolled and can access the ERCOT MIS portal
    MPs have been trained on the NOMCR process
    TSPs can electronically submit data changes utilizing the NOMCR user interface and CIM compliant format for data exchange or via the manual MIS NOMCR process
    QSEs can submit data changes utilizing the registration submission and subsequent ERCOT NOMCR process
    MPs can receive NOMCR acknowledgement of submittals, verifications, and confirmation of data posting
  ERCOT completes EDS 2 Release 4 activities
    ERCOT is ready to fully utilize the NOMCR process for all TSP/QSE data change requests
    TSP MPs can successfully submit data changes via the CIM compliant electronic NOMCR process.
    QSE can successfully submit data changes through registration submissions (and updated in the Network Operations Model via the NOMCR process)
    ERCOT has processes in place to use a “single entry point” to maintain both Nodal and Zonal network model databases when MPs submit changes via the NOMCR process
    NMMS is the database of record for the Network Operations Model including the ICCP modeling point database and operatorship / ownership information
    NMMS database is under full change control by ERCOT Network Model Group
    ERCOT discontinues the use of Service Requests for data changes and change control
    ERCOT begins the use of the NOMCR process for data changes and change control

## Slide 17: Transition summary during June-Aug’09
http://nodal.ercot.com <number>
  Currently no limits on submissions (Market Notice sent March 5)
    “… to clarify that there are no restrictions or “freezes” currently in place limiting network model change submissions via the service request process.”
  Transition periods:
    June 1- Aug 30, 2009 (objective to minimize SvcReq during this period)
      No equipment name changes (defer until after SEM Go-Live 8/31/09)
      Submit changes as far in advance as possible
    Aug 15-30, 2009
      Two weeks no submissions, except for emergency changes
    Aug 31, 2009 - Feb 2010 (NOMCRs for any/all network changes)
      Initially the NOMCR timeline will align with zonal timeline
        NOMCRs received and translated to zonal model change
        30-day lead-time, compliant with current zonal database schedule
        Status is tracked and communicated via system emails
      SRs that did not go into zonal production will be converted to NOMCRs for verification and submission by TSPs in Sept
      TSP gradually transitions to NodalProtocols(3.10) 90-day reqts