## Slide 1: Texas Nodal Program Implementation: Program Update
Mike Cleary
Sr. VP and Chief Technology Officer
June 4, 2009
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
4 June 2009
Program Highlights
  Current Timeline
  Risks & Issues
New Organization & Hires
Program Control & Review
ERCOT & Market Readiness
Notes: <number>
<number>

## Slide 3: Timeline
4 June 2009
Technical Advisory Committee
Notes: <number>
<number>

## Slide 4: Risks & Issues to Achieving Nodal’s Major Milestones
Technical Advisory Committee
4 June 2009
Complete Integrated Systems (11-18-09)
  Risk: Resource constraints for Nodal Program
  Issue: Handling CMM delays for Nodal Program
Integrated Market Trials (2-10)
  Risk: Reconciling Protocols, Systems and Market Expectations
Nodal Go-Live (12-1-10)
  Risk: Data Center capacity concerns
  Risk: SEM data integrity provided by Market Participants
Notes: <number>

## Slide 5
EERM Program Team
Enterprise Verification David Luedtke
Chief Technology
Officer
Mike Cleary
Market Systems
Hope Parrish
Reliability Systems Cagle Lowe
Web Presence
Adam Martinez
Resource
Management & Human Capital
Andrew Rinaldi
Systems
Murray Nixon
Communications
Tom Kleckner
Program Control & Review
Betty Day
ERCOT & Market Readiness
Vikki Gates
Market Mgmt System
Independent Mkt Monitor
Congestion Revenue Rights
Commercial Systems
Network Model Mgmt System
Energy Mgmt System
Outage Scheduler
MIS Portal
Current Day Reports
Enterprise Data Warehouse
Enterprise Integration
Data Management
Integration Testing
End-to-End Testing
Market Trials
PMO
Janet Ply
Budget/ Schedules
Vendor/ Contracts
Workflow
Resource Reconciliation
Risk/QA
Process & Procedures
ERCOT Readiness/Trng
MP Readiness
Training/ Metrics
Applications Infrastructure
David Forfia
Operational Readiness
System Cutover
Infrastructure
Cyber Security
4 June 2009
Technical Advisory Committee
Notes: <number>
.

## Slide 6: People: New Hires
Technical Advisory Committee
4 June 2009
Vikki Gates
  12 years experience in energy/utility sector
  ERCOT, MISO, PG&E, Entergy
  Market-rules development (ERCOT, SERC), translating rules into system design specs
David Luedtke
  13 years utility and energy consulting experience
  MISO, ESB National Grid, Southwest Power Pool, ERCOT, Constellation
  Led system-cutover team for MISO ASM and led planning/execution of MISO market trials
Bob Spangler
  20 years experience in regulatory/energy/nuclear sectors
  Luminant Energy, Johnson Controls, US Nuclear Regulatory Commission
  Protocol/design development of Nodal Program; develop ERCOT/MP consensus on protocols/designs
Jeff Fruit
  20 years experience in energy and trading; extensive ISO/RTO experience
  Southwest Power Pool, CAISO, MISO, Henwood Energy Services
  Managed/validated Areva’s delivery schedule; key player in launch of MISO’s $25B market
Harry Nelson
  29 years IT, energy experience
  MISO, Maxcess, ATT, AMS
  MISO PM analyzing, planning, designing infrastructure/integration components for $70M program

## Slide 7: Program Review & Control
A “SWAT Team”
  Traceability: tracing protocols to market expectations
  Internal reviews
  Other issues as they arise
Traceability
  Protocols Requirements
    Identify gaps
    Plan to meet gaps
  Requirements Test Cases
    Prove protocols have been met through test results
    Provides “auditability”
Technical Advisory Committee
4 June 2009

## Slide 8: Program Review & Control
Going Forward …
  Involving business SMEs
  Floyd Trefney/Bob Spangler
  First: Protocol sections 3-9, 16
    Initial focus on systems from external vendors to quickly identify if any gaps exist
  Regular communications with market
    Status reports
Technical Advisory Committee
4 June 2009

## Slide 9
May 7, 2009
Technical Advisory Committee
ERCOT & Market Readiness
It’s inter-related … ERCOT and Market Readiness
Total Readiness Effort laid out in July TAC meeting
Point of Contact: Vikki Gates
    vgates@ercot.com
    512.248.4218
    512.350.4020

## Slide 10
Questions ?