## Market Design
ERCOT
Renewable Technology Working Group (RTWG)
List of Market Design Issues
May 2009
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Revision Mechanism | Status | Other REF No. | Action Date
MD | 1 | Ancillary Services Cost Allocations Applicable to Wind | Develop any ancillary services cost allocations applicable to wind generation resources. | TAC | Near Term |  | The ERCOT Board requested TAC provide more detail related to their recommendation to not do any special Ancillary Services cost allocations applicable to Wind. TAC is no longer working on this issue. COMPLETE?
MD | 3 | Non-Spin Requirements | Determine if additional Non-Spin Service procurements are required to accommodate increased amounts of wind generation in ERCOT. | PERTF | Near Term |  | To be included in MD 4
MD | 4 | New Ancillary Service Products Needed for Reliability | Determine if new ancillary services are needed to reliably integrate the large amounts of wind generation coming into the ERCOT market. | ROS | Long Term |  | Eric Goff had developed a list of questions to be discussed at the Feb. 20 RTWG meeting; Eric will bring a whitepaper in May |  | Circulated prior to Feb meeting
MD | 5 | Benefits of Storage Technologies | Determine benefit and potential applications of storage technologies in the ERCOT market. | RTWG | Long Term |  | Steve Isser will bring white paper to RTWG; |  | Presented at Jan 29 meeting
MD | 7 | Wind Generating Resources Providing Ancillary Services | Determine possible changes in the ERCOT Nodal Protocols to allow Wind Generation Resources to provide ancillary services. | ROS | Undetermined | PRR | Walter Reid will develop list of questions to be presented to RTWG in May. |  | Circulated prior to Jan 29 meeting
MD | 8 | Reactive and Voltage Requirements Applicable to Wind Generators | Review of current ERCOT Protocols to ensure reactive and voltage control requirements are applicable to all generating technologies, including wind generation. | WOTF | Near Term | PRR | Docket 36482 has been abated. ERCOT staff is preparing a draft PRR that should be out in March. | WOTF 1a
MD | 9 | Wind Generation Dispatch in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to dispatch response. | WMS | Near Term | NPRR | Draft PRR will be prepared and distributed for review in April | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 10 | Wind Generation Performance Metrics in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to performance metrics when negative pricing exists. | WMS | Near Term | NPRR | Draft PRR will be prepared and distributed for review in April | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 11 | Wind Generation and Base Point Deviation in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to Base Point deviation. | WMS | Near Term | NPRR | Draft PRR will be prepared and distributed for review in April | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March

## System Ops
ERCOT
Renewable Technology Working Group (RTWG)
List of System Operations Issues
May 2009
Issue Category | System Ops Issue No. | Title | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
SO | 1 | Inventory of Wind Generation Facilities | Develop forms and collect wind turbine data from Wind Generation Resources to improve ERCOT's modeling and operations databases. | WOTF | Near Term | ERCOT Forms | Assigned to WOTF Modeling Subgroup. Currently being reviewed | WOTF 1d
SO | 2 | Nodal Tools to Integrate Wind Generation | Determine tools applicable to the Nodal Protocols to successfully integrate wind generation into the ERCOT markets. | RTWG | Undetermined |  | Reviewed at January 29 RTWG meeting through Floyd Trefny's presentation; next steps pending.
SO | 3 | Wind Generation Response and SCE | Determine proper wind generation response to down balancing instructions from ERCOT and also address SCE issues. | QMWG | Near Term |  | Being worked on currently by QMWG; draft PRR/OGRR to be available in March
SO | 4 | Smart Grid Implications for Renewable Resources | Determine how development of a "smart grid" could benefit and improve integration of renewable resources into the ERCOT grid. | RTWG | Long Term |  | Eric Goff and Steve Isser will develop a white paper
SO | 5 | Operational Studies Related to Wind Generation | Operational studies re: Wind (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Walter Reid to develop a white paper to be presented to RTWG
SO | 6 | Testing Reactive Capability of Wind Generation | Determine the appropriate testing methodology to measure the reactive capability of wind generation. | ERCOT Operations | Near Term | OGRR | ERCOT Operations is drafting OGRR because the current procedure is inadequate
SO | 7 | Wind Generation and High System Frequency | Determine impact of wind generation on high system frequency events and develop possible solutions. | WOTF | Near Term |  | WOTF currently reviewing a whitepaper on governor response; a draft PRR will be developed. | WOTF 5
SO | 8 | Wind Generation and System Inertia | Determine impact of wind generation on system inertia and develop possible solutions. | PDCWG | Long Term |  | Mark Garrett to ask ROS for status update | WOTF 1e
SO | 9 | SCADA Control of Generator Circuit Breakers | Develop guidelines for better control of generator circuit breakers via SCADA. | OGRR TF | Near Term | OGRR | Draft OGRR is being discussed at OGRTF | WOTF 1b
SO | 10 | Voltage Management Practices Applicable to Wind Generation | Develop appropriate voltage management practices for ERCOT and Transmission Service Providers that would apply to wind generation resources. | RPG | Near Term |  | Walter Reid to develop a white paper to be presented to RTWG
SO | 11 | Technology-Specific Procedures and Protocols Changes | Develop renewable technology-specific changes in existing ERCOT Protocols, Operating Guides, Interconnection Agreements and interconnection procedures to recognize unique characteristics of various renewable generation technologies. | ROS | Near Term | PRR, OGRR, ERCOT Procedures and Agreements | ERCOT developing a technology-specific procedure for wind; RTWG is considering technology-specific procedures for other renewable technologies
SO | 14 | Impact of Transmission Outage Planning on Wind Generation | Examine possible ways to improve transmission outage planning to better coordinate with wind generation operations. | RPG | Long Term | PRR 795 | PRR 795 was approved by the Board - Policy issues still open
SO | 15 | Communications between Wind Farms and TSPs | Examine possible improvements in real-time communications between wind farms and transmission service providers (TSPs). | WOTF | Near Term | OGRR | Draft OGRR will be discussed at OGRTF (response time OGRR) | WOTF 2a
SO | 23 | Impact of Advanced Meters on Integration of Renewable Resources | Examine impact of advanced metering capabilities on integration and deployment of renewable resources and demand-side management technologies. | DSWG | Long Term |  | 2009 Goal for WMS; on-going in DSWG
SO | 25 | Generator Governor Response for Wind Generators | : Determine proper generator governor response requirements for wind generators in the Nodal Market design. | WOTF | Short Term |  | Under active discussion at WOTF; a draft PRR will be prepared | WOTF 1e
SO | 26 | Impact of Solar Generation on System Operations | Determine potential impact of new solar generation on ERCOT system operations through appropriate studies of solar ramp rate capabilities, forecasting of solar energy production, voltage and reactive control capabilities. | RTWG | Long Term |  | Steve Isser to develop a white paper to be presented to RTWG in April
SO | 28 | SPS Actuation for N-0 Conditions | Determine possible changes to eliminate actuation of special protection systems (SPS) caused by variable output of wind farms. | CMWG | Near Term |  | John Dumas is planning to prepare an OGRR to address this issue
SO | 29 | Transmission Outage Planning for CREZ | Determine ways to accommodate large amounts of transmission outages associated with the CREZ buildout while still providing adequate transmission service to existing wind farms and maintaining adequate system reliability. | RPG | Near Term |  | Issue has been raised at RPG but little support has been forthcoming; the Red Creek line is being evaluated
SO | 30 | Application of Wind Generation Forecast to PASA | Determine how the ERCOT wind generation output forecast could be used to improve the Projected Assessment of System Adequacy (PASA). | ERCOT Operations | Near Term |  | To be discussed at April RTWG meeting
SO | 31 | Tension Monitors on Transmission Lines | Determine the need (if any) to install tension monitors on certain existing transmission lines that will be affected by construction of CREZ transmission facilities. | RPG | Near Term |  | To be brought up at RPG
SO | 32 | Real-Time Wind Generation Capacity | Determine the value of having a real-time value of available wind generating capacity for use by ERCOT operations. | QMWG | Near Term |  | Draft PRR/OGRR to be developed by QMWG
SO | 33 | Real-Time Wind Turbine Availability | Determine the value of having a real-time indication of the availability of each wind turbine for use by ERCOT operations. | QMWG | Near Term |  | Draft PRR/OGRR to be developed by QMWG

## System Planning
ERCOT
Renewable Technology Working Group (RTWG)
List of System Planning Issues
May 2009
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref. No.
SP | 2 | Wind Turbine Computer Models | Collect and verify accuracy of computer models for each type of wind turbine installed on the ERCOT grid. | ERCOT Planning | Near Term |  | Included in ERCOT's LVRT Study
SP | 3 | Wind Turbine Fault Tolerance | Prepare a study of the fault tolerance of wind turbines installed on the ERCOT grid. | ERCOT Planning | Near Term | OGRR | Included in ERCOT's LVRT Study
SP | 4 | Voltage Transient and Small Signal Stability Study | Update ERCOT voltage transient and small signal stability study and prepare a West Zone to North Zone transfer study. | ERCOT Operations | Near Term |  | Limit study is underway; the design study is still under discussion at RPG
SP | 5 | Impact of Wind Turbines on System Inertia | Determine the potential impact on system reliability of large amounts of wind turbine generating capacity on ERCOT's system inertia requirements. | ERCOT Planning | Long Term |  | Will be undertaken following completion of LVRT study
SP | 6 | Variable Frequency Transformers | Determine potential for variable frequency transformers (VFTs) to solve stability problems caused by the addition of large amounts of remotely-located generation capacity (e.g., wind generation). | RTWG | Long Term |  | Walter Reid/Paul Hassink to develop white paper
SP | 7 | Voltage Control Process | Develop a process to better control voltage in areas with large amounts of wind generation (comment: have I described this issue correctly?) | ERCOT Planning | Long Term |  | Walter Reid to develop a whitepaper
SP | 8 | Low Voltage Ride-Through (LVRT) Study | Prepare a study of the system reliability and associated requirements applicable to all generators for voltage ride-through capability. | ERCOT Planning | Near Term |  | All study results due to ROS no later than June 2010

## WT
ERCOT
Renewable Technology Working Group (RTWG)
List of Workshop/Training Opportunities
May 2009
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Status | Other Ref. No.
WT | 1 | Resource Plan and Schedule Update Process | Determine potential improvements to the Resource Plan and Resource Schedule update process to improve performance and reliability. | RTWG/ERCOT Operations | Undetermined | Included with Workshop III
WT | 2 | Wind Workshop III - Summer 2009 | Develop list of topics and speakers for the ERCOT Wind Workshop III to be held in the summer of 2009. | RTWG/ERCOT Operations | Near Term | ERCOT Operations to develop draft outline
WT | 3 | Wind Turbine Operator Training | Develop list of topics for use in development of a training session for wind turbine generator operators. | RTWG/ERCOT Operations | Long Term | Ask ERCOT training to discuss with RTWG
WT | 4 | Wind in the Nodal Market | Develop presentation for use in the Wind Workshop explaining how wind generation will be treated in the Nodal Market design. | RTWG/ERCOT Operations | Near Term | Include in Wind Workshop III

## COMPLETED
ERCOT
Renewable Technology Working Group (RTWG)
List of All Completed Issues
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
MD | 2 | Ancillary Services Procurement Optimization for 2009 | Develop any ancillary services cost allocations applicable to wind generation resources (see also MD-6). | QMWG | Complete |  | ERCOT Board approved the 2009 Ancillary Services Procurement methodology at the February Board Meeting - COMPLETE
MD | 6 | Ancillary Service Procurement Methodology | Determine impact and possible changes in amounts of ancillary services to be procured to ensure reliability with increasing amounts of wind generation being installed in the ERCOT market. | WOTF | Complete | ERCOT Procedure | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 12 | Wind Generation Resource LSL as a Percentage of HSL | Establish a minimum percentage for the Low Sustained Limit (LSL) of the High Sustained Limit (HSL) for a wind generation resource. | QMWG | Complete | PRR 773 | COMPLETE | WOTF 2a
MD | 13 | Use of State of the Art Wind Forecast | Requires Wind Generation Resources to use of a state-of-the-art wind production forecast (AWS Truewind) in their daily resource plan submittals. | N/A | Complete | PRR 763 | COMPLETE | WOTF 3b
SO | 12 | Low-Voltage-Ride-Through for Wind Generators | Develop low-voltage-ride-through requirements for wind generators. | N/A | Complete | OGRR 208 | COMPLETE
SO | 13 | Performance Metrics for Wind Generation | Develop appropriate operational performance metrics for wind generation. | QMWG | Complete | PRR 793 (Urgent) | PRR793 approved by the ERCOT Board - COMPLETE
SO | 16 | Wind Generation Ramp Limits | Develop appropriate ramp rate limits for wind farms | ROS | Complete | PRR 771, PRR 788 | COMPLETE | WOTF 3a
SO | 17 | Mid-Term and Short-Term Load Forecast Weather Sensitivity | WOTF determined that this was not a determining factor in the Februrary 26, 2008 event. | WOTF | Complete | ERCOT Procedures | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3b
SO | 19 | Improve Competitively Sensitive Constraints (CSC) Process | Evaluate increasing the frequency of ERCOT CSC studies to more accurately determine congestion problems that affect wind generation. | WOTF | Complete | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3f
SO | 20 | Dynamic Transmission Line Ratings | Evaluate cost and benefits of using dynamic transmission line ratings in ERCOT's planning processes to allow more efficient use of transmission lines serving wind farms. | WOTF | Complete | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3g
SO | 21 | Evaluate Emergency Electric Curtailment Plan (EECP) Steps | Determine if the existing EECP steps need to be modified to take into account the increasing amount of variable wind generation in the ERCOT system. | OWG | Complete | PRR 769 NPRR 142 | COMPLETE: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting | WOTF 3h
SO | 24 | Settlement of Advanced Meters in the Nodal Market | Determine appropriate settlement timeline to accommodate use of advanced meters in the Nodal Market design. | AMIT | Complete |  | Go-live date is November 2009; all provisioned advanced meters will be settled on a 15-minute basis - COMPLETE
SO | 27 | Manual Curtailment of Wind Generation to Resolve Local Congestion | Determine if changes can be made in the existing zonal systems to allow for automating curtailment of wind to resolve local congestion problems. | CMWG | Complete |  | COMPLETE: ERCOT Operations discussed this issue extensively at February CMWG; no reasonable, timely or cost-effective solution is available in the existing zonal market, issue is resolved by the Nodal market design.
SP | 1 | Verify Wind Turbine Technical Data | Create and maintain an inventory of installed wind turbine characteristics. | ERCOT Operations | Complete | ERCOT Survey | COMPLETE: ERCOT to report on status at January 30 WOTF meeting