|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Reliability and Operations Subcommittee for May 2009 |
|  | Report Highlights |  |
| Item |  |  |
| 1. | ERCOT is currently tracking 242 active generation interconnection requests totaling almost 97,000 MW. This includes over 39,000 MW of wind generation. |  |
| 2. | Regional Planning is currently reviewing proposed transmission improvements with a total cost of $948.3 Million Transmission Projects approved in 2009 total $ 105 Million All projects (in engineering, routing, licensing and construction) totals approximately $4.1 Billion Transmission Projects energized in 2008 total about $453 million |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	3

1.5	Generation Projects Undergoing Full Interconnection Studies	5

1.6	Wind Generation	6

2.	Regional Planning Group Project Reviews	7

3.	Other Notable Activities	8

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Beginning Commercial Operations - none for May 2009

## The total installed wind capacity remains 8,135 MW, of which 7,477 (92%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements

## Penascal Wind Farm II & III (06INR0022) - 404 MW Wind in Kenedy County

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 242 active generation interconnection or change requests |
| As of May 31, 2009 | North | South | West | Total |
| Security Screening Study | 3 | 6 | 7 | 16 |
| SSS Completed | 2 | 12 | 25 | 39 |
| Full Interconnect Study | 28 | 34 | 81 | 143 |
| FIS Completed | 5 | 5 | 4 | 14 |
| Interconnect Agreement Completed | 8 | 11 | 11 | 28 |
| Capacity under Interconnection Agreements | 5,342 | 2,550 | 2,003 | 9,895 |
| Capacity for Grid, MW | 23,105 | 32,950 | 40,645 | 96,700 |
| Wind Capacity, MW | 1,687 | 7,355 | 29,982 | 39,024 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC | - | - | 4,241 | 21,708 |
| Gas-CT | - | - | 527 | 1,677 |
| Total Gas | 1,725 | 16,892 | 4,768 | 23,385 |
| Nuclear | 0 | 3,200 | 9,186 | 12,386 |
| Coal | 0 | 3,995 | 3,550 | 7,545 |
| Wind | 10,555 | 31,159 | 7,688 | 49,402 |
| Solar | 1,268 | 369 | 0 | 1,637 |
| Biomass | 0 | 50 | 145 | 195 |
| Other | 950 | 1,200 | 0 | 2,150 |
| Grand Total | 14,498 | 56,865 | 25,337 | 96,700 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of May 31, 2009 |
| --- |
| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 | Wind | 465 |  |
| 10INR0025 | Mont Belvieu | IA | Chambers | South | May-09 | Gas-CT | 0 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Jun-09 | Wind | 500 |  |
| 09INR0039 | Nueces Bay 7 Repowering | IA | Nueces | South | Jul-09 | Gas-CC | 327 |  |
| 09INR0079 | Pearsall Expansion | IA | Frio | South | Aug-09 | Gas-CT | 200 |  |
| 09INR0072 | Dansby3 | PL | Brazos | North | Aug-09 | Gas-CT | 48 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Sep-09 | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Sep-09 | Wind | 400 |  |
| 09INR0028 | V H Braunig 6 | IA | Bexar | South | Oct-09 | Gas-CT | 185 |  |
| 09INR0015 | Comanche Peak 1&2 Upgrade | PL | Somervell | North | Oct-09 | Nuclear | 86 |  |
| 08INR0012a | Papalote Creek Wind Farm | IA | San Patricio | South | Oct-09 | Wind | 180 |  |
| 11INR0015 | Panther Creek 3 | IA | Sterling | West | Nov-09 | Wind | 200 |  |
| 09INR0038 | Barney Davis 2 Repowering | IA | Nueces | South | Nov-09 | Gas-CC | 360 |  |
| 09INR0006a | Oak Grove SES 1 | IA | Robertson | North | Nov-09 | Coal | 855 |  |
| 09INR0047 | Loraine Windpark | IA | Mitchell | West | Dec-09 | Wind | 251 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-09 | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-09 | Wind | 194 |  |
| 10INR0026 | Langford Wind Power | IA | Tom Green | West | Dec-09 | Wind | 150 |  |
| 11INR0014 | TECO Central Plant | IA | Harris | South | Feb-10 | Gas-CC | 50 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Mar-10 | Wind | 350 |  |
| 09INR0006b | Oak Grove SES 2 | IA | Robertson | North | May-10 | Coal | 855 |  |
| 09INR0002 | J K Spruce 2 | IA | Bexar | South | Jun-10 | Coal | 750 |  |
| 09INR0045 | Sand Hill Peakers | IA | Travis | South | Jul-10 | Gas-CT | 94 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-10 | Wind | 150 | Date |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 | Wind | 400 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-10 | Wind | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 | Wind | 400 |  |
| 06INR0022c | Penascal Wind Farm 2 | IA | Kenedy | South | Dec-10 | Wind | 202 | New IA |
| 07INR0036 | Coyote Run Windfarm | IA | Borden | West | Mar-11 | Wind | 225 |  |
| 10INR0020 | Panda Temple Power | PL | Bell | North | May-11 | Gas-CC | 1,092 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 | Gas-CC | 620 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-11 | Wind | 120 |  |
| 09INR0060 | Stephens Wind Farm | PL | Borden | West | Nov-11 | Wind | 141 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-11 | Wind | 120 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 06INR0022b | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-11 | Wind | 202 | New IA |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 | Coal | 165 |  |
| 09INR0026a | Sterling Energy Center | PL | Sterling | West | Jun-12 | Wind | 200 |  |
| 09INR0026 | Sterling Energy Center | IA | Sterling | West | Jun-12 | Wind | 300 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1,001 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Jun-12 | Coal | 925 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 | Wind | 400 |  |
| 08INR0040 | Lenorah Project | IA | Martin | West | Sep-12 | Wind | 251 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 | Gas-CC | 1,792 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-13 | Wind | 100 |  |
| 04INR0011b | Mesquite Wind Phase 4 | IA | Shackelford | West | Jun-13 | Wind | 136 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 | Nuclear | 3,200 |  |
| 11INR0011 | Victoria City Nuclear | PL | Victoria | South | Jan-15 | Nuclear | 3,200 |  |
| 06INR0029 | Jackson Mountain | XX | Nolan | West | Jan-10 | Wind | 90 | Cancelled |
|  |  |  |  |  |  |  | 25,337 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0044 | Concho | 200 | TBD | Wind |  | 08INR0049 | Clay | 50 | TBD | Wind |
| 09INR0064 | Borden | 41 | TBD | Wind |  | 08INR0042 | Coke | 200 | TBD | Wind |
| 08INR0041 | Coke | 200 | TBD | Wind |  | 09INR0059 | Freestone | 20 | TBD | Coal |
| 09INR0025 | Concho | 180 | Jun-09 | Wind |  | 08INR0005 | Wise | 400 | Jun-09 | Gas |
| 10INR0027 | Nueces | 35 | Oct-09 | Wind |  | 09INR0075 | Kinney | 248 | Oct-09 | Wind |
| 09INR0055 | McCulloch | 299 | Oct-09 | Wind |  | 09INR0041 | Mitchell | 300 | Oct-09 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-09 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-09 | Wind |
| 09INR0048 | Jack | 150 | Oct-09 | Wind |  | 08INR0054 | Comanche | 401 | Oct-09 | Wind |
| 09INR0073 | Scurry | 200 | Nov-09 | Wind |  | 08INR0031 | Childress | 100 | Nov-09 | Wind |
| 11INR0013 | Mills | 150 | Dec-09 | Wind |  | 11INR0012 | Duval | 400 | Dec-09 | Wind |
| 09INR0082 | Webb | 300 | Dec-09 | Wind |  | 09INR0077 | Reagan | 500 | Dec-09 | Wind |
| 09INR0065 | Webb | 150 | Dec-09 | Wind |  | 09INR0061 | Kent | 258 | Dec-09 | Wind |
| 09INR0058 | Howard | 250 | Dec-09 | Wind |  | 09INR0054 | Stonewall | 148.5 | Dec-09 | Wind |
| 09INR0051 | Borden | 249 | Dec-09 | Wind |  | 08INR0056 | Nolan | 149 | Dec-09 | Wind |
| 08INR0039 | Hamilton | 90 | Dec-09 | Wind |  | 08INR0023 | Floyd | 100 | Dec-09 | Wind |
| 08INR0022 | Floyd | 100 | Dec-09 | Wind |  | 09INR0029 | Calhoun | 263 | Dec-09 | Coal |
| 07INR0008 | Howard | 35 | Dec-09 | Wind |  | 11INR0036a | Matagorda | 200 | Jan-10 | Wind |
| 11INR0033a | Cameron | 200 | Jan-10 | Wind |  | 10INR0048 | Hardeman | 1000 | Jan-10 | Wind |
| 10INR0047 | Kendall | 1000 | Jan-10 | Wind |  | 10INR0024 | Briscoe | 3000 | Jan-10 | Wind |
| 10INR0011 | Johnson | 275 | Jan-10 | Gas |  | 09INR0062 | Brown | 140 | Mar-10 | Wind |
| 10INR0046 | Jim Hogg | 264 | Apr-10 | Wind |  | 10INR0045 | Webb | 734 | Apr-10 | Wind |
| 10INR0079 | Nolan | 60 | May-10 | Wind |  | 10INR0054 | Palo Pinto | 36 | May-10 | Wind |
| 10INR0023 | Haskell | 386 | May-10 | Wind |  | 10INR0016 | Childress | 150 | May-10 | Wind |
| 09INR0070 | Reagan | 42 | May-10 | Wind |  | 09INR0069 | Reagan | 36 | May-10 | Wind |
| 09INR0035 | Concho | 750 | May-10 | Wind |  | 09INR0018 | Concho | 249 | May-10 | Wind |
| 07INR0032 | Tom Green | 249 | May-10 | Wind |  | 10INR0017 | Chambers | 685 | May-10 | Gas |
| 10INR0069 | Rusk | 818 | May-10 | Coal |  | 10INR0035 | Harris | 416 | Jun-10 | Gas |
| 10INR0029 | Hood | 810 | Jun-10 | Gas |  | 09INR0081 | Rusk | 818 | Jun-10 | Coal |
| 10INR0057 | Taylor | 200 | Jul-10 | Wind |  | 10INR0052a | Knox | 21 | Jul-10 | Wind |
| 10INR0013 | Upton | 400 | Jul-10 | Wind |  | 10INR0012 | Nacogdoches | 300 | Jul-10 | Gas |
| 10INR0038 | Glasscock | 350 | Aug-10 | Wind |  | 10INR0071 | Matagorda | 88 | Sep-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 09INR0074 | Motley | 70 | Oct-10 | Wind |  | 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |
| 10INR0070 | Hunt | 50 | Nov-10 | Gas |  | 10INR0039 | Dickens | 200 | Nov-10 | Wind |
| 10INR0080 | Presidio | 144 | Dec-10 | Solar |  | 10INR0077 | Callahan | 101 | Dec-10 | Wind |
| 10INR0060 | Willacy | 400.5 | Dec-10 | Wind |  | 10INR0059 | Zapata | 250.7 | Dec-10 | Wind |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 10INR0033 | Armstrong | 420 | Dec-10 | Wind |
| 10INR0032 | Navarro | 800 | Dec-10 | Gas |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 09INR0031 | Ector | 275 | Dec-10 | Gas |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 07INR0026 | Baylor | 400 | Dec-10 | Wind |  | 07INR0017 | Erath | 210 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 11INR0036b | Matagorda | 200 | Jan-11 | Wind |  | 11INR0033b | Cameron | 200 | Jan-11 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 08INR0014 | Webb | 183 | Mar-11 | Wind |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 11INR0046 | Brazoria | 300 | May-11 | Gas |  | 11INR0037 | Smith | 55 | May-11 | Biomass |
| 11INR0028 | Grimes | 1280 | May-11 | Gas |  | 10INR0009 | Castro | 200 | May-11 | Wind |
| 11INR0057 | Cameron | 144 | Jun-11 | Wind |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 11INR0009 | Navarro | 1200 | Jun-11 | Gas |  | 09INR0050 | Fannin | 1200 | Jun-11 | Gas |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 06INR0041 | Newton | 1160 | Jul-11 | Gas |  | 11INR0040 | freestone | 749 | Aug-11 | Gas |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0008a | Roberts | 1000 | Sep-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 09INR0016 | Yoakum | 680 | Nov-11 | Gas |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 06INR0022d | Kenedy | 200 | Dec-11 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 10INR0022 | Harris | 3500 | Jun-12 | Gas |
| 12INR0002 | Briscoe | 750 | Jul-12 | Wind |  | 12INR0016 | Nueces | 1200 | Nov-12 | Other |
| 08INR0019c | Gray | 250 | Nov-12 | Wind |  | 08INR0019b | Gray | 250 | Nov-12 | Wind |
| 08INR0019a | Gray | 250 | Nov-12 | Wind |  | 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0018 | Gray | 600 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1100 | Dec-12 | Wind |
| 11INR0023 | King | 400 | Dec-12 | Wind |  | 06INR0022f | Kenedy | 200 | Dec-12 | Wind |
| 12INR0009 | Nueces | 875 | May-13 | Gas |  | 13INR0006 | Gray | 750 | Oct-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 06INR0022e | Kenedy | 200 | Dec-13 | Wind |
| 14INR0002 | Goliad | 756 | Feb-14 | Coal |  | 14INR0003 | Nolan | 850 | Jun-14 | Coal |
| 14INR0005 | Matagorda | 1200 | Jul-14 | Coal |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 15INR0003 | Matagorda | 3200 | Jan-15 | Nuclear |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year					County Location of Installed Capacity and Interconnection Requests

# Regional Planning Group Project Reviews

# American Electric Power Service Corporation submitted a project to construct 2 new 138 kV substations, rebuild a 138 kV circuit, build  2 new 138 kV circuits, and install a new 138/69 kV autotransformer in the Abilene/San Angelo area.  The estimated cost of this project is $105.9 M.  The review of this project is complete and an ERCOT Recommendation Letter is in process.

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

# Oncor submitted a project to add several 345 kV circuits to support the addition of Comanche Peak units 3 and 4 in 2015 at an estimated cost of $ 133 M.    These upgrades include a new 345 kV double circuit line with one circuit in place from Comanche to Whitney, a new 345 kV line from Comanche to Johnson Switch, a new circuit on existing structures from Johnson Switch to Everman, a new 345 kV double circuit with one circuit in place from Comanche to DeCordova, and a new 345 kV line on existing structures from Comanche to Parker Switch.  This project is in ERCOT Independent Review and will be studied when the 2009 Five-Year Transmission Plan is complete.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review and will be studied as part of the 2009 Five-Year Transmission Plan.

- Austin Energy submitted a project to relocate the Decker to Techridge circuit to new ROW so that the existing structures can be utilized for the new Gilleland to Techridge circuit.  The estimated completion date of this project is November 2010 and estimated cost is $ 4.3 M.   This project is in ERCOT Independent Review.

- The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to construct a new 6.2 mile transmission line from Highway 123 to Cushman substation.  The estimated completion date of this project is June 2014 and estimated cost is $ 11.6 M.   This project is in ERCOT Independent Review.

- The Lower Colorado River Authority Transmission Services Company (LCRA TSC) submitted a project to construct a new 7.8 mile transmission line between the existing GPI and Parkway substations.  The estimated completion date of this project is June 2013 and estimated cost is $ 12.9 M.   This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to expand the Zenith substation, add one 800 MVA autotransformer, connect Zenith to existing circuits near the Gertie substation and upgrade/reconfigure nearby 138 kV circuits.  The estimated completion date of this project is summer 2012 and estimated cost is $ 26.6 M.   This project is in ERCOT Independent Review.

# American Electric Power Service Corporation submitted a project to construct several improvements in the Corpus Christi area.  The estimated completion date of this project is June 2012 and estimated cost is $ 214 M.   This project is in ERCOT Independent Review.

# Other Notable Activities

All postings referred to below can be found at http://planning.ercot.com/login/login unless otherwise indicated.

- The reliability phase of the 2009 Five-Year Transmission Plan utilizing the latest SSWG base cases is underway.  Projects to eliminate unserved energy have been identified and sent to Transmission Owners.  Most of the Transmission owners have replied with their concurrence or set of alternate projects.  This phase will continue with G-1 analysis.

- RMR exit strategy development is underway for the Permian Basin RMR unit.

- ERCOT has contracted with PB Americas, Inc. to perform the Voltage Ride-Through (VRT) Study.  A kick-off meeting with PB and ERCOT staff has been held.  The project will proceed in three phases.  Phase I is a simulation of the VRT capabilities of the system with existing wind farm models.  Phase II will consist of model improvement.  Both of these phases are scheduled for completion by the End of 2009.  Phase III involves simulating the VRT capabilities of the system with the revised models and investigation of any required changes.

- Began co-ordination with Steady-State Working Group to create Data Set A cases.

- Completed analysis to propose SAPS to Menard 138 kV line as a CRE for the W – N CSC.

- ERCOT TPIT report for 2009 2nd quarter was posted on June 1, 2009