## Slide 1: May 2009 RO Projects Financial Overview Retail Market Subcommittee June 10, 2009 Hope Parrish Market Operations Division Projects Organization

## Slide 2: Agenda
Overview of project status on RO 2009 PPL
Current 2009 Financials
Approve 2010 RO PPL

## Slide 3: 2009 Projects

## Slide 4: Projects in Execution
Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Revised Budget Range
RO | PUCT 34610 | Advanced Metering -Interim Solution for Settlement | 80027_01 | Execution | 0 - Previously Approved | $1M - 2M
RO |  | TIBCO Siebel Integration | 80040_01 | Execution | 0-Previously Approved | $250k-$500k
RO |  | Paperfree and NAESB Transition to ISM formerly (EDW EAI Transition Phase 1 (including PaperFree & NAESB)) | 50061_01 | Execution | 0 - Previously Approved | $250k-$500k
PR80040_01 – Migrated to production on May 16, 2009

## Slide 5: Projects in Planning
Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Revised Budget Range
RO |  | Data Research and Reporting (formerly ETS Transition to EDW) | 50088_01 | Planning | 0 - Previously Approved | $1M-$2M
RO |  | Retail Application Upgrades | 80031_01 | Planning | 2 - High | $1M-2M
Notes: <number>

## Slide 6: Projects in On Hold or Not Started
Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Revised Budget Range | 2009 Running Range
RO |  | Advance Metering Long Term Settlement Solution | 90007_01 | Not started | 1 - Critical | $ - | $3M-$4M
RO |  | MarkeTrak Phase 3 | 80030_01 | On Hold | 2 - High | $ - | $3M-$4M
RO | PUCT 34610 | Advanced Metering - Retail Market Interface | 90011_01 | Not started | 2 - High | $100k-$250k | $3M-$4M

## Slide 7: Projects Closing, Closed or Cancelled
PR80028_01 – Gated to Closing Phase May 26, 2009
Prog Area | Source Doc | Project | Project No. | Current Status | 2009 Priority | 2009 Revised Budget Range
RO/MO | HS3693 PUCT 34890 | Small Renewables/Distributed Generation - RMWG | 80028_01 | Closing | 0 - Previously Approved | <$25K
RO | SCR749 | MarkeTrak Enhancements (Workflow & Reporting) | 70007_01 | Closing | 0 - Previously Approved | <$100k
RO | SCR748 | Website Enhancements for ERCOT Outages PhII | 70006_02 | Closed | 0 - Previously Approved | <$50k
RO |  | Paperfree and NAESB Transition to ISM formerly (EDW EAI Transition Phase 1 (including PaperFree & NAESB)) | 50061_02 | Cancelled | 2 - High | $100k-$250k

## Slide 8: Financial Overview as of 06/01/2009
RO PPL Budget Activity | Amount | Notes/comments
Approved RO Capability Line Budget Funding | $3.616M | Current approved RO funding allocation Designates where the capability line falls
Current Forecast Spend of projects above the Capability Line | ~$3.594M | Based on current expectations and run rates for active and not started projects above the capability line
Budget Variance | ~$22k | Budget Variance is difference between RO Capability Line Budget Funding and Current Forecast Spend of projects above the Capability Line.

## Slide 9
2010 PPL Prioritization

## Slide 10: 2010 PPL Prioritization – RMS Goals
WebEx with RMS – Apr 30 2-3pm (Complete)
Submit all 2010 Project Initiatives to hparrish@ercot.com – May 4 (Complete)
Process Kick off at RMS – May 13 (Complete)
ERCOT Draft Project Charters, CBA and review – May 08 (Complete)
ERCOT Draft TCE for projects – May 15 (Complete)
ALL - Review and finalize Draft Charter, CBA, and TCE week of May 29 (Complete)
Approve 2010 PPL

## Slide 11: Questions / Contact
Hope Parrish
Market Operations Divisional Projects Organization
ERCOT
(512) 248-6522
hparrish@ercot.com
Notes: <number>