## Market Design
ERCOT
Renewable Technology Working Group (RTWG)
List of Market Design Issues
April 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other REF No. | Action Date
MD | 1 | Ancillary Services Cost Allocations applicable to Wind | TAC | Near Term |  | The ERCOT Board requested TAC provide more detail related to their recommendation to not do any special Ancillary Services cost allocations applicable to Wind. TAC is no longer working on this issue. COMPLETE?
MD | 3 | Non-Spin requirements | PERTF | Near Term |  | To be included in MD 4
MD | 4 | Consideration of new ancillary service products in order to support reliability needs | ROS | Long Term |  | Eric Goff had developed a list of questions to be discussed at the Feb. 20 RTWG meeting; Eric will bring a whitepaper in May |  | Circulated prior to Feb meeting
MD | 5 | Storage technologies benefits (e.g., flywheels) to the integration of wind and provision of necessary ancillary services (regulation, responsive reserves) | RTWG | Long Term |  | Steve Isser will bring white paper to RTWG; |  | Presented at Jan 29 meeting
MD | 7 | Investigate whether any Nodal Protocol changes are necessary to allow wind resources to provide ancillary services | ROS | Undetermined | PRR | Walter Reid will develop list of questions to be presented to RTWG in May. |  | Circulated prior to Jan 29 meeting
MD | 8 | Review of current Protocol to ensure requirements are applicable to all technologies re: reactive and voltage requirements | WOTF | Near Term | PRR | Docket 36482 has been abated. ERCOT staff is preparing a draft PRR that should be out in March. | WOTF 1a
MD | 9 | Review Nodal Protocols for proper treatment of wind generation re: dispatch response | WMS | Near Term | NPRR | Draft PRR will be prepared and distributed for review in April | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 10 | Review nodal protocols for proper treatment of wind generation re: performance metrics with negative pricing | WMS | Near Term | NPRR | Draft PRR will be prepared and distributed for review in April | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 11 | Review nodal protocols for proper treatment of wind generation re: base point deviaton charges as applicable to wind generation | WMS | Near Term | NPRR | Draft PRR will be prepared and distributed for review in April | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March

## System Ops
ERCOT
Renewable Technology Working Group (RTWG)
List of System Operations Issues
April 2009
Issue Category | System Ops Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
SO | 1 | Update forms used by ERCOT to gather generator data so that WGRs can provide accurate information | WOTF | Near Term | ERCOT Forms | Assigned to WOTF Modeling Subgroup. Currently being reviewed | WOTF 1d
SO | 2 | Identifying nodal tools to more effectively integrate wind into the grid | RTWG | Undetermined |  | Reviewed at January 29 RTWG meeting through Floyd Trefny's presentation; next steps pending.
SO | 3 | Response to down balancing instructions (QMWG); SCE issues, clarity on expected following instructions, requirements | QMWG | Near Term |  | Being worked on currently by QMWG; draft PRR/OGRR to be available in March
SO | 4 | Smart grid implications on market design and integration of renewable resources | RTWG | Long Term |  | Eric Goff and Steve Isser will develop a white paper
SO | 5 | Operational studies re: Wind (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Walter Reid to develop a white paper to be presented to RTWG
SO | 6 | Qualification testing of reactive capability for wind generation | ERCOT Operations | Near Term | OGRR | ERCOT Operations is drafting OGRR because the current procedure is inadequate
SO | 7 | High frequency: Develop alternate solutions | WOTF | Near Term |  | WOTF currently reviewing a whitepaper on governor response; a draft PRR will be developed. | WOTF 5
SO | 8 | System intertia capability of wind generators | PDCWG | Long Term |  | Mark Garrett to ask ROS for status update | WOTF 1e
SO | 9 | Better defined SCADA control of generation breakers | OGRR TF | Near Term | OGRR | Draft OGRR is being discussed at OGRTF | WOTF 1b
SO | 10 | ERCOT/TSP/Generator voltage management practices | RPG | Near Term |  | Walter Reid to develop a white paper to be presented to RTWG
SO | 11 | Protocols, Operating Guides, Interconnection Procedure and the Interconnection Agreement need to be updated to make requirements less ambiguous and more generic to include all types of generation | ROS | Near Term | PRR, OGRR, ERCOT Procedures and Agreements | ERCOT developing a technology-specific procedure for wind; RTWG is considering technology-specific procedures for other renewable technologies
SO | 14 | What can we do to identify upcoming transmission outages and what can we do to minimize outage times and impact to wind power production? | RPG | Long Term | PRR 795 | PRR 795 was approved by the Board - Policy issues still open
SO | 15 | 24/7 communication must be available for TSP to reach wind generators. | WOTF | Near Term | OGRR | Draft OGRR will be discussed at OGRTF (response time OGRR) | WOTF 2a
SO | 23 | Integrating advanced meters and other demand response into the existing and Nodal Ancillary Service markets | DSWG | Long Term |  | 2009 Goal for WMS; on-going in DSWG
SO | 25 | Governor Generator Response of wind generators | WOTF | Undetermined |  | Under active discussion at WOTF; a draft PRR will be prepared | WOTF 1e
SO | 26 | Operational studies: Solar (ramp rate, low load situations, forecasting) | RTWG | Long Term |  | Steve Isser to develop a white paper to be presented to RTWG in April
SO | 28 | Resources tripping due to Base Case (N-0) SPS | CMWG | Near Term |  | John Dumas is planning to prepare an OGRR to address this issue
SO | 29 | Transmission outage planning related to CREZ line construction outages | RPG | Near Term |  | Issue has been raised at RPG but little support has been forthcoming; the Red Creek line is being evaluated
SO | 30 | Use of wind generation output forecast for the purposes of the Projected Assessment of System Adequacy (PASA) | ERCOT Operations | Near Term |  | To be discussed at April RTWG meeting |  | HD contact ERCOT
SO | 31 | Investigate need for tension monitors on selected lines during construction of CREZ lines | RPG | Near Term |  | To be brought up at RPG
SO | 32 | Real-time signal of estimate of wind generation capability | QMWG | Near Term |  | Draft PRR/OGRR to be developed by QMWG
SO | 33 | Real-time signal of wind turbine availability | QMWG | Near Term |  | Draft PRR/OGRR to be developed by QMWG

## System Planning
ERCOT
Renewable Technology Working Group (RTWG)
List of System Planning Issues
April 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref. No.
SP | 2 | Verify computer models for wind generation | ERCOT Planning | Near Term |  | Included in ERCOT's LVRT Study
SP | 3 | Fault Tolerance Studies (OGRR208) | ERCOT Planning | Near Term | OGRR | Included in ERCOT's LVRT Study
SP | 4 | Updated Voltage Transient and Small Signal Stability Study (West to North Transfer Study) | ERCOT Operations | Near Term |  | Limit study is underway; the design study is still under discussion at RPG
SP | 5 | Inertia Study | ERCOT Planning | Long Term |  | Will be undertaken following completion of LVRT study
SP | 6 | Use of VFTs to solve stability problems | RTWG | Long Term |  | Walter Reid/Paul Hassink to develop white paper
SP | 7 | Voltage Swing Management (Voltage Control Process) | ERCOT Planning | Long Term |  | Walter Reid to develop a whitepaper
SP | 8 | Low Voltage Ride Through Study | ERCOT Planning | Near Term |  | All study results due to ROS no later than June 2010

## WT
ERCOT
Renewable Technology Working Group (RTWG)
List of Workshop/Training Opportunities
April 2009
Issue Category | Issue No. | Description | Assigned to: | Priority | Status | Other Ref. No.
WT | 1 | WGR QSE Resource Plan and Energy Schedule Update Process | RTWG/ERCOT Operations | Undetermined | Included with Workshop III
WT | 2 | ERCOT Wind Workshop III - Spring 2009 | RTWG/ERCOT Operations | Near Term | ERCOT Operations to develop draft outline
WT | 3 | WGR Operator Training | RTWG/ERCOT Operations | Long Term | Ask ERCOT training to discuss with RTWG
WT | 4 | Wind in the Nodal Market | RTWG/ERCOT Operations | Near Term | Include in Wind Workshop III

## COMPLETED
ERCOT
Renewable Technology Working Group (RTWG)
List of All Completed Issues
Issue Category | Issue No. | Description | Assigned to: | Priority | Revision Mechanism | Status | Other Ref No.
MD | 2 | Ancillary Services Procurement Optimization for 2009 | QMWG | Complete |  | ERCOT Board approved the 2009 Ancillary Services Procurement methodology at the February Board Meeting - COMPLETE
MD | 6 | Ancillary Service procurement methodology (Increase RGS, RRS, NSRS during high risk periods) | WOTF | Complete | ERCOT Procedure | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 12 | WGR LSL as % of HSL | QMWG | Complete | PRR 773 | COMPLETE | WOTF 2a
MD | 13 | Mandate use of AWST 80% forecast in wind Resource Plans | N/A | Complete | PRR 763 | COMPLETE | WOTF 3b
SO | 12 | Low Voltage Ride-Through (LVRT) for WGRs | N/A | Complete | OGRR 208 | COMPLETE
SO | 13 | Performance metrics for wind | QMWG | Complete | PRR 793 (Urgent) | PRR793 approved by the ERCOT Board - COMPLETE
SO | 16 | Wind generation ramp rate limitations | ROS | Complete | PRR 771, PRR 788 | COMPLETE | WOTF 3a
SO | 17 | Mid Term and Short Term Load Forecast weather sensitivity | WOTF | Complete | ERCOT Procedures | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3b
SO | 19 | Run multiple CSC limit studies | WOTF | Complete | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3f
SO | 20 | Dynamic line ratings | WOTF | Complete | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3g
SO | 21 | Reexamine EECP Steps | OWG | Complete | PRR 769 NPRR 142 | COMPLETE: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting | WOTF 3h
SO | 24 | Advanced meter settlement; incuding, impact of plug-in hybrid vehicles on storage and use of renewable resources. | AMIT | Complete |  | Go-live date is November 2009; all provisioned advanced meters will be settled on a 15-minute basis - COMPLETE
SO | 27 | ERCOT Operations is currently analyzing and deploying all wind generation local curtailment manually - what, if any, problems is this causing? | CMWG | Complete |  | COMPLETE: ERCOT Operations discussed this issue extensively at February CMWG; no reasonable, timely or cost-effective solution is available in the existing zonal market, issue is resolved by the Nodal market design.
SP | 1 | Verify technical data (installed technology) | ERCOT Operations | Complete | ERCOT Survey | COMPLETE: ERCOT to report on status at January 30 WOTF meeting