## 2009
No. | PWG 2009 Goals | Target Date | % Complete
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2009-04-30 | 100%
5 | Review Proxy Day Method | 2009-07-30 | 0%
11 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16, 2007) | 2009-06-30 | 0%
4 | Review Weather Sensitivity Correlation | 2009-07-31 | 0%
1 | Review 2008 UFE Analysis (April 30, true-up in Aug or Sept) | 2009-09-23 | 50%
3 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2009-12-09 | 0%
6 | Evaluate Hurricane Ike affect on settlement for possible improvements | 2009-12-09 | 0%
8 | Review profile models using Round 2 load research data, review if having more weather stations adds accuracy, and review if the weighting of weather stations is appropriate. | 2009-12-09 | 0%
9 | Improve Business Profile ID assignment process | 2009-12-09 | 0%
10 | Reevaluate distribution loss methodology due to advanced metering. | 2009-12-09 | 0%
12 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2009-12-09 | 0%
13 | Demand Response LPG or PRR language changes as needed | 2009-12-09 | 0%
2 | 2009 Annual Validation. | 2009-12-15 | 0%
14 | Evaluate language changes for Annual Validation Process due to AMS | 2009-12-16 | 0%
NEW