## Market Design
ERCOT
Renewable Technology Working Group (RTWG)
List of Market Design Issues
June 2009
Issue Category | Issue No. | Title | Description | Current Group | Priority | Wholesale/Retail | Impact | Area Affected | Solution Implemented by | Revision Mechanism | Status | Other REF No. | RTWG Last Action/Next Step
MD | 1 | Ancillary Services Cost Allocations Applicable to Wind | Develop any ancillary services cost allocations applicable to wind generation resources. | TAC | Near Term | Wholesale | Medium | Open Access | Market Participants | PRR/NPRR | Open issue that will be addressed on a case-specific basis.
MD | 3 | Non-Spin Requirements | Determine if additional Non-Spin Service procurements are required to accommodate increased amounts of wind generation in ERCOT. | WMS | Near Term | Wholesale | High | Reliability | ERCOT | Other | Complete
MD | 4 | New Ancillary Service Products Needed for Reliability | Determine if new ancillary services are needed to reliably integrate the large amounts of wind generation coming into the ERCOT market. | ROS | Long Term | Wholesale | Medium | Reliability | ERCOT | PRR/NPRR | Dependent on results of SO-5
MD | 5 | Benefits of Storage Technologies | Determine benefit and potential applications of storage technologies in the ERCOT market. | RTWG | Long Term | Wholesale | Low | Reliability | Market Participants | Other | Steve Isser will bring white paper to RTWG;
MD | 7 | Wind Generating Resources Providing Ancillary Services | Determine possible changes in the ERCOT Nodal Protocols to allow Wind Generation Resources to provide ancillary services. | QMWG | Long-Term | Wholesale | Medium | Reliability | Market Participants | NPRR | List of issues has been circulated; Walter Reid will be developing a NPRR to address market facilitation issues |  | Circulated prior to Jan 29 meeting
MD | 8 | Reactive and Voltage Requirements Applicable to Wind Generators | Review of current ERCOT Protocols to ensure reactive and voltage control requirements are applicable to all generating technologies, including wind generation. | WOTF | Near Term | Wholesale | Low | Reliability | ERCOT | PRR | In Docket 36482, a motion has been made to dismiss. Wnd generators have until June 30 to respond to the motion to dismiss. | WOTF 1a
MD | 9 | Wind Generation Dispatch in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to dispatch response. | QMWG | Near Term | Wholesale | Medium | Open Access | Market Participants | NPRR | Under discussion at QMWG; a draft NPRR will be available for discussion by the QMWG in June. | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 10 | Wind Generation Performance Metrics in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to performance metrics when negative pricing exists. | QMWG | Near Term | Wholesale | Medium | Reliability | ERCOT | NPRR | Under discussion at QMWG; a draft NPRR will be available for discussion by the QMWG in June. | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 11 | Wind Generation and Base Point Deviation in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to Base Point deviation. | QMWG | Near Term | Wholesale | Medium | Reliability | ERCOT | NPRR | Under discussion at QMWG; a draft NPRR will be available for discussion by the QMWG in June. | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March

## System Ops
ERCOT
Renewable Technology Working Group (RTWG)
List of System Operations Issues
June 2009
Issue Category | System Ops Issue No. | Title | Description | Current Group | Priority | Impact | Area Affected | Solution Implemented by | Revision Mechanism | Status | Other Ref No.
SO | 1 | Inventory of Wind Generation Facilities | Develop forms and collect wind turbine data from Wind Generation Resources to improve ERCOT's modeling and operations databases. | ERCOT/Consultant | Near Term | Low | Open Access | ERCOT | Other | ERCOT Planning has hired a consultant to do specific studies including database grooming. ERCOT will develop a consolidated data-gathering process.
SO | 2 | Nodal Tools to Integrate Wind Generation | Determine tools applicable to the Nodal Protocols to successfully integrate wind generation into the ERCOT markets. | RTWG | Undetermined | Medium | Open Access | Market Participants | NPRR | COMPL:ETE (pending completion of Nodal market trials) - open issues are addressed in other specific issues. Review and discussion of the Nodal Protocols indicates that wind is addressed adequately.
SO | 3 | Wind Generation Response and SCE | Determine proper wind generation response to down balancing instructions from ERCOT and also address SCE issues. | QMWG | Near Term | Low | Reliability | Market Participants | PRR | PRR 812 has been approved by PRS and is up for review by TAC. The PRR was revised to reduce its impact on ERCOT resources working on the Nodal market design.
SO | 4 | Smart Grid Implications for Renewable Resources | Determine how development of a "smart grid" could benefit and improve integration of renewable resources into the ERCOT grid. | RTWG | Long Term | Low | Reliability | Market Participants | Other | Eric Goff and Steve Isser will develop a white paper
SO | 5 | Operational Studies Related to Wind Generation | Operational studies re: Wind (ramp rate, low load situations, forecasting) to identify if new ancillary services are needed. | RTWG | Long Term | Medium | Reliability | ERCOT | NPRR | A white paper has been developed and will be discussed RTWG in July
SO | 6 | Testing Reactive Capability of Wind Generation | Determine the appropriate testing methodology to measure the reactive capability of wind generation. | ERCOT Operations | Near Term | Medium | Reliability | ERCOT | OGRR | See MD-8
SO | 7 | Wind Generation and High System Frequency | Determine impact of wind generation on high system frequency events and develop possible solutions. | WOTF | Near Term | Medium | Reliability | Market Participants | PRR/NPRR | WOTF a draft PRR which will be provided to ROS in July. | WOTF 5
SO | 8 | Wind Generation and System Inertia | Determine impact of wind generation on system inertia and develop possible solutions. | PDCWG | Complete | Medium | Reliability | Market Participants | Other | COMPLETE: PDCWG report to ROS in October 2008. Further discussion of this issue is being done under SP-5 | WOTF 1e
SO | 9 | SCADA Control of Generator Circuit Breakers | Develop guidelines for better control of generator circuit breakers via SCADA. | OGRR TF | Near Term | Low | Reliability | Market Participants | OGRR | OGRR 226 is under review at OWG | WOTF 1b
SO | 10 | Voltage Management Practices Applicable to Wind Generation | Develop appropriate voltage management practices for ERCOT and Transmission Service Providers that would apply to wind generation resources. | ERCOT | Near Term | High | Reliability | ERCOT/TSPs | NPRR | ERCOT has issued an RFP for a reactive study of West Texas.
SO | 11 | Technology-Specific Procedures and Protocols Changes | Develop renewable technology-specific changes in existing ERCOT Protocols, Operating Guides, Interconnection Agreements and interconnection procedures to recognize unique characteristics of various renewable generation technologies. | ROS | Near Term | Low | Open Access | Market Participants | Other | COMPLETE - This issue is covered by other individual issues in System Operations, Market Design and System Planning
SO | 14 | Impact of Transmission Outage Planning on Wind Generation | Examine possible ways to improve transmission outage planning to better coordinate with wind generation operations. | RPG | Long Term | High | Open Access | ERCOT/TSPs | PRR 795 | PRR 795 was approved by the Board - Policy issues still open
SO | 15 | Communications between Wind Farms and TSPs | Examine possible improvements in real-time communications between wind farms and transmission service providers (TSPs). | WOTF | Near Term | Medium | Open Access | Market Participants | OGRR | OGRR 226 is under review at OWG | WOTF 2a
SO | 23 | Impact of Advanced Meters on Integration of Renewable Resources | Examine impact of advanced metering capabilities on integration and deployment of renewable resources and demand-side management technologies. | DSWG | Long Term | Low | Customer Choice | Market Participants | PRR/NPRR | 2009 Goal for WMS; on-going in DSWG
SO | 25 | Generator Governor Response for Wind Generators | : Determine proper generator governor response requirements for wind generators in the Nodal Market design. | WOTF | Short Term | Medium | Reliability | Market Participants | NPRR | See SO-7 | WOTF 1e
SO | 26 | Impact of Solar Generation on System Operations | Determine potential impact of new solar generation on ERCOT system operations through appropriate studies of solar ramp rate capabilities, forecasting of solar energy production, voltage and reactive control capabilities. | RTWG | Long Term | Medium | Reliability | Market Participants | NPRR | Steve Isser to develop a white paper to be presented to RTWG
SO | 28 | SPS Actuation for N-0 Conditions | Determine possible changes to eliminate actuation of special protection systems (SPS) caused by variable output of wind farms. | CMWG | Near Term | Medium | Open Access | ERCOT | OGRR
SO | 29 | Transmission Outage Planning for CREZ | Determine ways to accommodate large amounts of transmission outages associated with the CREZ buildout while still providing adequate transmission service to existing wind farms and maintaining adequate system reliability. | RPG | Near Term | High | Open Access | ERCOT | Other | The RTWG will bring this issue up at the July TAC.
SO | 30 | Application of Wind Generation Forecast to PASA | Determine how the ERCOT wind generation output forecast could be used to improve the Projected Assessment of System Adequacy (PASA). | ERCOT Operations | Near Term | Medium | Reliability | ERCOT | Other
SO | 31 | Tension Monitors on Transmission Lines | Determine the need (if any) to install tension monitors on certain existing transmission lines that will be affected by construction of CREZ transmission facilities. | RPG | Near Term | Low | Reliability | Market Participants | Other | At the last RPG meeting, ERCOT indicated that they would consider dynamic line ratings.
SO | 32 | Real-Time Wind Generation Capacity | Determine the value of having a real-time value of available wind generating capacity for use by ERCOT operations. | QMWG | Near Term | Medium | Reliability | ERCOT | PRR | Draft PRR/OGRR to be developed by QMWG
SO | 33 | Real-Time Wind Turbine Availability | Determine the value of having a real-time indication of the availability of each wind turbine for use by ERCOT operations. | QMWG | Near Term | Medium | Reliability | ERCOT | PRR | Draft PRR/OGRR to be developed by QMWG
SO | 34 | SCED Line Ratings | Increase the frequency of SCED's consumpiton of dynamic line ratings to better model current system conditons. | ROS | Long Term | High |  | ERCOT | Other | To be raised at the July ROS meeting

## System Planning
ERCOT
Renewable Technology Working Group (RTWG)
List of System Planning Issues
June 2009
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Impact | Area Affected | Solution Implemented by | Revision Mechanism | Status | Other Ref. No.
SP | 2 | Wind Turbine Computer Models | Collect and verify accuracy of computer models for each type of wind turbine installed on the ERCOT grid. | ERCOT Planning | Near Term | Low | Open Access | ERCOT | Other | Included in ERCOT's LVRT Study
SP | 3 | Wind Turbine Fault Tolerance | Prepare a study of the fault tolerance of wind turbines installed on the ERCOT grid. | ERCOT Planning | Near Term | Medium | Reliability | ERCOT | OGRR | Included in ERCOT's LVRT Study
SP | 4 | Voltage Transient and Small Signal Stability Study | Update ERCOT voltage transient and small signal stability study and prepare a West Zone to North Zone transfer study. | ERCOT Operations | Near Term | Medium | Reliability | ERCOT | Other | Limited study is underway; the design study is still under discussion at RPG
SP | 5 | Impact of Wind Turbines on System Inertia | Determine the potential impact on system reliability of large amounts of wind turbine generating capacity on ERCOT's system inertia requirements. | ERCOT Planning | Long Term | Medium | Reliability | ERCOT | Other | Will be undertaken following completion of LVRT study
SP | 6 | Variable Frequency Transformers | Determine potential for variable frequency transformers (VFTs) to solve stability problems caused by the addition of large amounts of remotely-located generation capacity (e.g., wind generation). | RTWG | Long Term | Low | Reliability | Market Participants | Other | Walter Reid/Paul Hassink to develop white paper
SP | 7 | Voltage Control Process | Develop a process to better control voltage in areas with large amounts of wind generation. | ERCOT Planning | Long Term | Medium | Reliability | ERCOT | OGRR/NOGRR | ERCOT has issued an RFP for a reactive study of West Texas.
SP | 8 | Low Voltage Ride-Through (LVRT) Study | Prepare a study of the system reliability and associated requirements applicable to all generators for voltage ride-through capability. | ERCOT Planning | Near Term | High | Reliability | ERCOT | Other | All study results due to ROS no later than June 2010

## WT
ERCOT
Renewable Technology Working Group (RTWG)
List of Workshop/Training Opportunities
June 2009
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Impact | Area Affected | Solution Implemented by | Status | Revision Mechanism | Other Ref. No.
WT | 1 | Resource Plan and Schedule Update Process | Determine potential improvements to the Resource Plan and Resource Schedule update process to improve performance and reliability. | RTWG/ERCOT Operations | Undetermined | Low | Reliability | Market Participants | Potential topic for future Wind Workshop | Other
WT | 2 | Wind Workshop III - Summer 2009 | Develop list of topics and speakers for the ERCOT Wind Workshop III to be held in the summer of 2009. | RTWG/ERCOT Operations | Near Term | Low | Open Access | Market Participants | Workshop held on June 26, 2009 | Other
WT | 3 | Wind Turbine Operator Training | Develop list of topics for use in development of a training session for wind turbine generator operators. | ROS | Long Term | Low | Reliability | Market Participants | Ask ROS to consider adding wind-specific training to the ERCOT Operatior training class | Other
WT | 4 | Wind in the Nodal Market | Develop presentation for use in the Wind Workshop explaining how wind generation will be treated in the Nodal Market design. | RTWG/ERCOT Operations | Near Term | Low | Open Access | Market Participants | Complete; ERCOT On-Line Training Course for Wind | Other

## COMPLETED
ERCOT
Renewable Technology Working Group (RTWG)
List of All Completed Issues
Issue Category | Issue No. | Title | Description | Assigned to: | Priority | Impact | Area Affected | Solution Implemented by | Revision Mechanism | Status | Other Ref No.
MD | 2 | Ancillary Services Procurement Optimization for 2009 | Develop any ancillary services cost allocations applicable to wind generation resources (see also MD-6). | QMWG | Complete | Medium | Open Access | ERCOT |  | ERCOT Board approved the 2009 Ancillary Services Procurement methodology at the February Board Meeting - COMPLETE
MD | 6 | Ancillary Service Procurement Methodology | Determine impact and possible changes in amounts of ancillary services to be procured to ensure reliability with increasing amounts of wind generation being installed in the ERCOT market. | WOTF | Complete | Medium | Reliability | ERCOT | ERCOT Procedure | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 12 | Wind Generation Resource LSL as a Percentage of HSL | Establish a minimum percentage for the Low Sustained Limit (LSL) of the High Sustained Limit (HSL) for a wind generation resource. | QMWG | Complete | Medium | Reliability | Market Participants | PRR 773 | COMPLETE | WOTF 2a
MD | 13 | Use of State of the Art Wind Forecast | Requires Wind Generation Resources to use of a state-of-the-art wind production forecast (AWS Truewind) in their daily resource plan submittals. | N/A | Complete | Medium | Reliability | Market Participants | PRR 763 | COMPLETE | WOTF 3b
SO | 8 | Wind Generation and System Inertia | Determine impact of wind generation on system inertia and develop possible solutions. | PDCWG | Complete | Low | Reliability | ERCOT |  | COMPLETE: PDCWG report to ROS in October 2008 | WOTF 1e
SO | 12 | Low-Voltage-Ride-Through for Wind Generators | Develop low-voltage-ride-through requirements for wind generators. | N/A | Complete | Medium | Reliability | ERCOT | OGRR 208 | COMPLETE
SO | 13 | Performance Metrics for Wind Generation | Develop appropriate operational performance metrics for wind generation. | QMWG | Complete | Medium | Reliability | Market Participants | PRR 793 (Urgent) | PRR793 approved by the ERCOT Board - COMPLETE
SO | 16 | Wind Generation Ramp Limits | Develop appropriate ramp rate limits for wind farms | ROS | Complete | Medium | Reliability | Market Participants | PRR 771, PRR 788 | COMPLETE | WOTF 3a
SO | 17 | Mid-Term and Short-Term Load Forecast Weather Sensitivity | WOTF determined that this was not a determining factor in the Februrary 26, 2008 event. | WOTF | Complete | Low | Reliability | Market Participants | ERCOT Procedures | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3b
SO | 19 | Improve Competitively Sensitive Constraints (CSC) Process | Evaluate increasing the frequency of ERCOT CSC studies to more accurately determine congestion problems that affect wind generation. | WOTF | Complete | Medium | Open Access | ERCOT | N/A | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3f
SO | 20 | Dynamic Transmission Line Ratings | Evaluate cost and benefits of using dynamic transmission line ratings in ERCOT's planning processes to allow more efficient use of transmission lines serving wind farms. | WOTF | Complete | Low | Open Access | Market Participants | N/A | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3g
SO | 21 | Evaluate Emergency Electric Curtailment Plan (EECP) Steps | Determine if the existing EECP steps need to be modified to take into account the increasing amount of variable wind generation in the ERCOT system. | OWG | Complete | Low | Reliability | ERCOT | PRR 769 NPRR 142 | COMPLETE: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting | WOTF 3h
SO | 24 | Settlement of Advanced Meters in the Nodal Market | Determine appropriate settlement timeline to accommodate use of advanced meters in the Nodal Market design. | AMIT | Complete | Medium | Customer Choice | Market Participants |  | Go-live date is November 2009; all provisioned advanced meters will be settled on a 15-minute basis - COMPLETE
SO | 27 | Manual Curtailment of Wind Generation to Resolve Local Congestion | Determine if changes can be made in the existing zonal systems to allow for automating curtailment of wind to resolve local congestion problems. | CMWG | Complete | High | Reliability | ERCOT |  | COMPLETE: ERCOT Operations discussed this issue extensively at February CMWG; no reasonable, timely or cost-effective solution is available in the existing zonal market, issue is resolved by the Nodal market design.
SP | 1 | Verify Wind Turbine Technical Data | Create and maintain an inventory of installed wind turbine characteristics. | ERCOT Operations | Complete | Medium | Open Access | ERCOT | ERCOT Survey | COMPLETE: ERCOT to report on status at January 30 WOTF meeting

## Menus
Priority
| Near-Term | Within a year
| Long-Term | Year out or longer
Undetermined
Est. Impact
| High | Has a major cost/benefit to MP; major resource requrement for ERCOT to implement; a major impact when implemented
Medium
Low
Area Affected | Delete column | Already covered in our division of issues (Mkt, Operations, etc.)
Reliability
| Open Access | Market Design Wholesale Tab
| Customer Choice | Market Design Retail Tab
Implementer
ERCOT
ERCOT/TSPs
Market Participants
Both
To be determined
Revision Mechanism
PRR
NPRR
PRR/NPRR
OGRR
NOGRR
OGRR/NOGRR
Other