## Slide 1: Nodal Program Update
Mike Cleary
Sr. VP and Chief Technology Officer
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
9 July 2009
Current Timeline
Recent Achievements
Systems Update
Integrated Testing Update
Program Control & Review
Risks & Issues
Notes: <number>
<number>

## Slide 3: Nodal Timeline
9 July 2009
Technical Advisory Committee
Notes: <number>
<number>

## Slide 4: CMM/NMMS Milestone Slips
Technical Advisory Committee
9 July 2009
CMM
  Excessive defects found in custom components delivered in July
  CMM 4.1 custom components required for end-to-end testing will be delivered on-time
    Key functionality: Credit monitoring (8 custom components)
  ERCOT will complete CMM 4.2 custom components in house and deliver by February 2010
    Key functionality: Internal reports, report management
  CMM 4.3’s components rolled into 4.1 and 4.2
NMMS 7
  One week delay exiting FAT due to testing-resource constraints (due June 23, delivered June 30)
Notes: <number>
<number>

## Slide 5: Significant Accomplishments
9 July 2009
Technical Advisory Committee
All Vendor Software Deliveries Complete
  MMS 5 delivered to iTest July 7 (3 days ahead of schedule)
  EMS 6 delivered to iTest July 1
  NMMS 7 exited FAT June 30
SEM Go-Live on Track for August 31
Vendor Contract Re-Negotiations
  5 targeted vendor contracts re-negotiated
  Results:
    Lower rates
    More ERCOT control and oversight
    Cleaned up unfavorable language in contractual documents
Notes: <number>
<number>

## Slide 6: Market Systems Update
Technical Advisory Committee
9 July 2009
Project | Sub-Project | Status | Open Critical Defects June 12/July 2 |  |  | 
MMS |  | On schedule MMS 5 final release; currently in FAT and scheduled to exit Aug. 21 MMS 5 Patch 1 preliminary drop to iTest July 7 (scheduled July 10) 14 interfaces to test by Sept. 1; test planning underway Market Manager UI to exit FAT July 16 | MMS5 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s | 0 3 85 | 1 3 79 |  
CRR |  | On schedule CRR 1.9 final release; currently in FAT and scheduled to exit Aug. 31 3 of 9 interfaces in iTest, 2 in FAT, 4 in execution phase | CRR 1.9 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s | 0 1 3 | 0 0 2 |  
COMS | CMM | Behind schedule CMM 4.1 in FAT; on schedule to exit July 31 Two CMM 4.2 components scheduled to exit FAT by July 31; remaining components combined with CMM 4.3 and to exit FAT February 2010 (internal functions only) 4 of 5 interfaces currently in iTest Outstanding release: CMM 4.2 | CMM 4.1 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s | 0 151 46 | 0 84 21 |  
 | S&B | FAT testing complete; 7 of 8 interfaces currently in iTest Targeting refactoring completion by September 2009 | Sev 1s Sev 2s Sev 3s | 0 3 20 | 0 0 2 |  
 | CSI | FAT testing complete Targeting refactoring completion by August 2009 | Sev 1s Sev 2s Sev 3s | 0 0 29 | 0 0 35 | 
 | REG | Nearing completion All 3 interfaces currently in iTest; 96% of testing complete | Sev 1s Sev 2s Sev 3s | 0 0 1 | 0 0 0 | 

## Slide 7: Reliability Systems Update
Technical Advisory Committee
9 July 2009
Project | Status | Open Critical Defects June 12/July 2 |  |  | 
NMMS | On schedule NMMS 7 final release; exited FAT June 30 All 3 interfaces have exited FAT and are currently in iTest | NMMS 7 |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 0 0 83 | 0 0 48 | 
EMS | On schedule EMS 6 Patch 3 deployed to iTest July 1 All 13 interfaces’ test plans now complete SPR Patch 3 completed FAT June 30 | SPR Patch 3 |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 0 1 83 | 0 0 86 |  
OS | On schedule Common test plan for 12 of 13 interfaces complete 2 defect patches planned for OS UI | OS 2.1.4 |  |  | 
 |  | Sev 1s Sev 2s Sev 3s * | 0 0 3 | 0 1 71 |  
 |  | * excluding ROO defects |  |  | 

## Slide 8: Market Verification Update
Technical Advisory Committee
9 July 2009
Project | Status | Open Critical Defects June 12/July 2 |  |  | 
Interface/Adapter Testing | Data management strategy undergoing review and approval System-to-system testing of connectors in progress using Common Data Set MMS 5 available for I/A testing Level 1/Level 2 testing running behind, but working on efficiency gains in automation areas, early Level 3 testing and other adjustments | FAT Defects |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 1 26 375 | 3 129 496 |   
 |  | iTest Defects |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 1 84 52 | 2 87 127 |   
End-to-End Testing | Early E2E testing started with CRR auction settlement Additional E2E testing planned in July (7 functional strings in total) Full E2E to start in late September |  |  |  | 
Market Trials | Detailed plan to be rolled out at August TAC meeting SEM Go-Live training for TSPs began June 23 Market Trials submission testing begins in October 2009 |  |  |  | 
Market Readiness | In detailed planning phase |  |  |  | 
ERCOT Readiness | In detailed planning phase |  |  |  | 
Operational Readiness | Schedule is being finalized NMMS performance testing under way System cutover validation and implementation under way |  |  |  | 

## Slide 9: Integrated Testing Update
Technical Advisory Committee
9 July 2009
Connectors to be Tested: 82 |  |  | 
 | Definition | In Progress | Completed
Level 1 | Connector installed; one record transferred through connector (“smoke test”) | 2 | 68
Level 2 | Connector tested using a common data set with multiple records | 11 | 9
Level 3 | System-to-system functional test; connector tested with system-generated data | 7 | 0
Target Completion:
Sept. 22, 2009 (Levels 1-2)
Nov. 13, 2009 (Level 3)
Status: On Schedule

## Slide 10: Program Review & Control
Traceability
  Protocols Requirements
Prioritization of the effort into tiers
Tier 1 (Significant/high volume of changes): 3, 4, 5, 6, 7, 8, 9, 16, 17
Tier 2 (Moderate): 10, 11, 12, 13, 20, 22
Tier 3 (Low impact): 1, 2, 14, 15, 18, 19, 21, 23, 24
    Identify alignment issues
    First-level analysis: Bob Spangler, Floyd Trefny
    Meet with business owners for validation
    Provide information to ERCOT Readiness Team for reporting
      7: ERCOT to review late July
      3, 4, 5, 6: ERCOT to review Sept./Oct.
      8, 9, 16, 17: ERCOT to review Oct./Nov.
Technical Advisory Committee
9 July 2009

## Slide 11: Risks & Issues to Achieving Nodal’s Major Milestones
Technical Advisory Committee
9 July 2009
Complete Integrated Systems (2-12-10)
  Issue: Resource constraints for program
  Issue: Handling CMM delays for program
Market Trials (2-12-10)
  Risk: Reconciling protocols, systems and market expectations
Nodal Go-Live (12-1-10)
  Risk: Data Center capacity concerns
  Risk: Integrity of network model data from market participants
Notes: <number>

## Slide 12
Questions ?