## Slide 1: Single Entry Model (SEM) Go-Live Update
http://nodal.ercot.com <number>
ROS Update
July 16, 2009

## Slide 2: SEM Go-Live
http://nodal.ercot.com <number>
Summary of current SEM Activities
ERCOT and Market Criteria Status for Go-Live Aug 31, 2009
Appendix
  What is SEM Go-Live?
  Market Engagement/Communications
  Training Update
  Transition summary during June – August 2009
  Next steps

## Slide 3: Summary of current SEM Activities
http://nodal.ercot.com <number>
Market/TSP engagement calendar for Single Entry Model Implementation
  May 28- SEM Market Kick-off Call
  June 4- Began weekly ERCOT/TSP market calls for SEM
  June 8- ERCOT deployed test system for TSP testing on schedule
  June 23- Training commenced on schedule 6-weeks of 3-day classes
  We are here - July stakeholder meetings
  August 31- SEM Go-Live milestone
ERCOT activity highlights
  Supporting market testing/training/questions/weekly-calls
  Converting final copy of 6/1/2009 of zonal operations model into nodal model
  Adding nodal data sets (such as RARF/Resource data) into the nodal model
  Confirming consumption of model into NMMS/EMSNodal/MMS test systems
  Nodal integration testing aligned to use post-SEM Go-Live model
Stakeholder communications
  ERCOT has reported detailed progress on testing and training to market on SEM Weekly calls, NDSWG/ROS, NIT, and TAC

## Slide 4: SEM Go-Live Market Engagement Dashboard
http://nodal.ercot.com <number>

## Slide 5: SEM Go-Live Criteria
http://nodal.ercot.com <number>
SEM Go-Live Criteria defined in the SEM Go-Live Procedure http://nodal.ercot.com/readiness/golive/index.html
Section 4- The following entry criteria shall be met for SEM Go-Live
  All TSPs & ERCOT complete EDS 2 Release 4 activities (ie training and testing)
  Nodal network model validated and approved as baseline for SEM Go-Live by ERCOT System Ops and Market Ops Directors
  ERCOT publishes CIM model to be used for SEM Go-Live
  ERCOT sufficiently staffed for maintenance of nodal & zonal systems
  Nodal EMS is capable of consuming NMMS CIM files through the EMS CIM importer for use in the Nodal EMS application suite
  ERCOT publishes the following documents for TSPs
    ERCOT Network Operations Model validation whitepaper
    ERCOT Network Operations Model validation results
    NMMS Modeling Guidelines / Validation Rules document
  Latest CIM data dictionary and schema
  SEM Go-Live readiness approved by TAC and ERCOT BOD
    Zonal protocol req’t 21.12.3 for TAC/Board “certification that all Market Readiness Criteria have been met”
    Issue market notices 30 days and 10 days prior to SEM Go-Live

## Slide 6: SEM Go-Live Criteria Dashboard
http://nodal.ercot.com <number>

## Slide 7: SEM Go-Live Criteria
http://nodal.ercot.com <number>

## Slide 8: SEM Go-Live Criteria
http://nodal.ercot.com <number>

## Slide 9: SEM Go-Live Criteria
http://nodal.ercot.com <number>

## Slide 10: SEM Go-Live Criteria and Approval
http://nodal.ercot.com <number>
Summary of remaining Stakeholder meeting dates for SEM discussion/approval of Go-Live
  July
    Next week- NDSWG - July 14 & ROS - July 16
    BOD - July 21
  August
    30-day “Conditional upon Board Approval” Market Notice - Aug 1
    TAC - Aug 6
    ROS - Aug 13
    NDSWG - Aug 18
    ERCOT publishes results and sign-off from Directors – Aug 20 -> Aug17
    BOD - Aug 18
    10-day Market Notice - Aug 21
    SEM Go-Live - Aug 31

## Slide 11
http://nodal.ercot.com <number>
  APPENDIX
  What is SEM Go-Live?
  Training Update
  Transition summary during June – August 2009

## Slide 12: SEM Go-Live Overview
http://nodal.ercot.com <number>
Single Entry Model (SEM) Go-Live is the switchover on Aug 31, 2009 for TSP submissions of network operations model change requests
  from “Service Request” submissions via TML
  to “NOMCR” submissions via the NMMS
    System of record for model changes becomes NOMCRs on 8/31//09
    System of record for Network operations Model for reliability and dispatch remains Zonal/Genesys system until Dec 2010
TSP
Current Activity
Submit Modeling
Change via Service Request
ERCOT Uploads
Svc Request
into Zonal
Genesys Model
ERCOT Copies/Converts
Zonal Model “seed”
Into Nodal
NMMS Model
TSP
Aug 31, 2009
Submit Modeling Change via
NOMCR/NMMS Tool
(includes ICCP)
ERCOT Incrementally
Converts NOMCR
Into Svc Req
Uploads into Zonal
Genesys Model
ERCOT uploads
NOMCR
Into Nodal
NMMS Model to
support nodal testing
Data Consistency Checks are run to
ensure model synchronization/fidelity
Periodic checks are run to
ensure model synchronization/fidelity
Full
Copy
Incr.
NOMCR

## Slide 13: Current Network Operations Model Maintenance for TSPs
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
Submits Service Request to Change Model
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
Periodic full copy and conversion of model
(zonal seed used for nodal systems)
TSP
Notes: <number>
<number>

## Slide 14: After 8/31/2009: SEM Go-Live Network Operations Model Maintenance for TSP
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
ERCOT enters NOMCRs into zonal model
ERCOT runs consistency checks to ensure models are aligned and maintained
Submits Model Change Request (NOMCR)
TSP
NMMS Model
System of Record
Nodal Go-Live 12/1/2010
Notes: <number>
<number>

## Slide 15: Network Operations Model Maintenance for Resource & QSE (today and post 8/31/09)
<number>
ERCOT Zonal EMMS Model
(system of record through 12/1/2010)
ERCOT Nodal NMMS Model
(nodal testing model- CIM file for EMS/MMS/etc)
ERCOT enters into zonal model
NMMS Model
System of Record
Nodal Go-Live 12/1/2010
Submits RARF
(Resource Asset Reg Form)
via Service Request
Submits ICCP Change
via Service Request
ERCOT process
QSE
RE
Notes: <number>
<number>

## Slide 16: Training Update
http://nodal.ercot.com <number>
TSP Testing and Training environments will be the same
Testing system access
  Available June 8 – Aug 10
  NOMCR testing system will be on-line and available to all TSPs
  ERCOT will establish dedicated email and have staff available to support questions (nomcrhelp@ercot.com)
Instructor Led Training to be hosted in Taylor
  Pre-SEM classes June 22 – Aug 3
    Current plans for at least six 3-day sessions
    Planning for 12-18 seats for each class
    Large dedicated training room
  Post-SEM classes Sept 23- Oct 20
    Fewer sessions and smaller classes (tbd)
    Make-up classes, not just-in-time training for all staff after go-live

## Slide 17: Transition summary during June-Aug’09
http://nodal.ercot.com <number>
  Currently no limits on submissions (Market Notice sent March 5)
    “… to clarify that there are no restrictions or “freezes” currently in place limiting network model change submissions via the service request process.”
  Transition periods:
    June 1- Aug 30, 2009 (objective to minimize SvcReq during this period)
      No equipment name changes (defer until after SEM Go-Live 8/31/09)
      Submit changes as far in advance as possible
    Aug 15-30, 2009
      Two weeks no submissions, except for emergency changes
    Aug 31, 2009 - Feb 2010 (NOMCRs for any/all network changes)
      Initially the NOMCR timeline will align with zonal timeline
        NOMCRs received and translated to zonal model change
        30-day lead-time, compliant with current zonal database schedule
        Status is tracked and communicated via system emails
      SRs that did not go into zonal production will be converted to NOMCRs for verification and submission by TSPs in Sept
      TSP gradually transitions to NodalProtocols(3.10) 90-day reqts