## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
July 23, 2009

## Slide 2: PMO Update - Agenda
  2010 Project Prioritization
    Seeking PRS approval of projects planned for 2010
  Recent Project Implementations
    June 2009

## Slide 3: Revised 2010 Project Prioritization Schedule
April 2009
  CARTs develop draft 2010 project lists
    Request and incorporate input from the market
    5 year project forecast referenced and updated
May 2009
  Initial review at Market Subcommittee meetings
    MO - COPS (May 12)
    RO - RMS (May 13)
    SO - ROS, WMS (May 14 / May 20)
June 2009
  Approval by market subcommittees
    MO - COPS (June 9)
    RO - RMS (June 10)
    SO - ROS, WMS (June 11 / June 17)
July 2009
  Approval by PRS
    CO, IO, MO, RO, SO (July 23)
August 2009
  Approval by TAC (August 6)
  Available for F&A and Board review (August 18)

## Slide 4: 2010 Project Priority List / Funding Level Review
2010 Project Prioritization – Introductory Comments
  Nodal delivery is the focus of the organization next year
  Zonal projects are limited to:
    Critical projects
    Completion of projects already executing
    Records management project
  On May 1, 2010, production and testing environments will be locked down to reduce risk during the months preceding Nodal implementation
  Resource constraints between other efforts and Nodal must be limited as much as possible
  No “Capability” line projected in 2010 due to multiple constraints

## Slide 5: 2010 Project Priority List / Funding Level Review
2010 Project Budgets and Project Counts by Program Area
Program Area | Budget Request | Projects Started in 2008/2009 | New 2010 Projects
CO | $ 1,150,000 | 3 | 2
IO | $ 1,450,000 | 0 | 3
MO | $ 1,500,000 | 1 | 0
RO | $ 1,850,000 | 3 | 0
SO | $ 150,000 | 2 | 0
Subtotal | $ 6,100,000 | 9 | 5
Met Center (CO) | $ 31,900,000 | 1 | 0
Data Center Refresh (IO) | $ 8,000,000 | 0 | 6
Minor Cap (CO) | $ 750,000 | 0 | 1
Grand Total | $ 46,250,000 | 10 | 12

## Slide 6: 2010 Project Priority List / Funding Level Review
Program Area | 2010 Budget Request | 2009 F | 2008 A | 2007 A | 2006 A
CO | $ 1,150 | $ 1,721 | $ 4,092 | $ 5,409 | $ 3,612
IO | $ 1,450 | $ 2,809 | $ 4,609 | $ 6,701 | $ 7,261
MO | $ 1,500 | $ 778 | $ 1,194 | $ 1,008 | $ 2,281
RO | $ 1,850 | $ 3,992 | $ 2,622 | $ 3,257 | $ 5,648
SO | $ 150 | $ 987 | $ 922 | $ 2,855 | $ 5,074
Subtotal | $ 6,100 | $ 10,287 | $ 13,439 | $ 19,230 | $ 23,876
Met Center | $ 31,900 | $ 20,000 | $ 1,113 | $ 0 | $ 0
DC Refresh | $ 7,500 | $ 6,152 | $ 0 | $ 0 | $ 0
Minor Cap | $ 750 | $ 893 | $ 1,334 | $ 1,895 | $ 1,308
Nodal Interdependent | $ 0 | $ 0 | $ 6,715 | $ 21,745 | $ 9,281
Total | $ 46,250 | $ 37,332 | $ 22,601 | $ 42,870 | $ 34,465
Previous Year Forecast (F) / Actuals (A) (in thousands)

## Slide 7: 2010 Project Priority List / Funding Level Review
2010 Project Prioritization Notes by Program Area
  CO ($ 1,150,000)
    3 carryover projects, a critical security project, and a document mgmt project
  IO ($ 1,450,000)
    3 critical infrastructure projects
  MO ($ 1,500,000)
    Continuation of Information Lifecycle Management project
  RO ($ 1,850,000)
    2 PUCT projects and Data Research & Reporting project
  SO ($ 150,000)
    Carryover funding for two projects that might cross into 2010
  Met Center (managed by CO) ($31,900,000)
    Large, multi-year project to replace the Met Center
      Approved by Board of Directors in Feb. 2008
  Data Center Refresh (IO) ($ 7,500,000)
    Telecom and Network Gear funding for Data Center Refresh project
    Initial Planning funds for additional 2011 Data Center Refresh efforts

## Slide 8: PMO Update - YTD 2009 Project Implementations
January 2009
  RO PR-70007_01 MarkeTrak Enhancements (SCR749)
  CO PR-80003_01 Employee Performance Management
  CO PR-80038_01 ACL Audit Exchange
  CO PR-80036_01 ERCOT / TRE Accounting Structure
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0217/20090217_FA_Meeting_Materials.pdf (p. 83)
February 2009
  CO PR-60058_01 Microsoft Project Server Upgrade
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0317/20090317_FA_Meeting_Materials.pdf (p. 44)
March 2009
  CO PR-70046_01 SEM Enhancement
  IO PR-80026_01 Enterprise Visibility
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0422/20090422_FA_Meeting_Materials.pdf (p. 69)

## Slide 9: PMO Update - YTD 2009 Project Implementations
April 2009
  None
May 2009
  CO PR-80016_01 Security Configuration Management
  RO PR-80040_01 TIBCO Siebel Integration Enhancements
http://www.ercot.com/content/meetings/finance_audit/keydocs/2009/0616/20090616_FA_Meeting_Materials.pdf (p. 25)
June 2009
  IO PR-80044_01 Tape Hardware Backup Replacement
  SO PR-90022_01 Zonal AWS Wind Gen Forecast for QSEs
    SCR754 / PRR763