## Master
Change Control Number | Requested Priority | Transaction Type | Description | Trans Set(s) | Requestor | Company | Guide or SET Change? | Disposition by Texas Standard Electronic Transactions
2007-705 | Y | 867_03 | Correct improper use of element separator in some elements of REF~5I segment in example. Modified in discussions on 2/5 to include MEA and QTY segments Texas SET determined this is a guide clean-up to be done after Texas SET 3.0 and this change control will be revised to include any other segments that need to be corrected. | 867_03 | Tammy Beaver | EP Solutions | Guide | Approved 5/22/08 change control
2007-706 | N | 814_24 | Remove the EM Communicaton Number Qualifier from the 814_24 | 814_24 | Catherine Meiners | ERCOT | TX SET Change | Approved 3/28/07 change control
2007-707 | N | 814_11 | Remove Drop to AREP process references from the 814_11 Implementation Guide since the 814_10 transaction and Drop to AREP functionality is no longer valid in the market, Per PUCT Subst. R. §25.482 Project 33025. | 814_11 | Susan Munson | ERCOT | Guide | Approved 4/25/07 change control
2007-709 | N | 867_03Final, 867_04 | REF~TN needs to specify that special characters are not allowed. Clarification of the gray box | 867_03Final, 867_04 | Catherine Meiners | ERCOT | Guide | Approved 5/22/08 change control
2007-710 | N | 814_14 | Add “Not Used when NM109=NONE” to the REF~NH segment. | 814_14 | Kyle Patrick | Reliant Energy | Guide | Approved 5/22/08 change control
2007-711 | N | 814_28 | Add clarification to the summary section of the 814_28 Implementation Guide | 814-28 | Catherine Meiners | ERCOT | Guide | Approved 5/22/08 change control
2007-713 | N | 814_16 | Revise inconsistent language in the gray box on REF~PH | 814_16 | Kyle Patrick | Reliant Energy | Guide | Approved 5/22/08 change control
2007-714 | N | 867_03 | Ts and Cs Requirement 3: Modified the 810_02 to send the BIG08~05’ Replace code on every corrected 810_02. The Implementation guide gray box contradicts that and needs to be modified on the BPT01. | 867_03 | Kyle Patrick | Reliant Energy | Guide | Approved 5/22/08 change control
2007-715 | N | 814_25 | Clarification to the graybox information on 814_25 to clarify that NFI is an ERCOT only reject reason. | 814_25 | Cary Reed | AEP | Guide | Approved 5/22/08 change control
2008-716 | N | 810_02 | Update gray box to reflect true validation process of the BIG05 | 810_02 | Suzette Sondag |  | Guide | Tabled 5/22/08 change control
2008-717 | N | 650_02 | V3.0 added duplicate YNQ segment. Instead of duplicate segment, update YNQ segment to communicate either the meter test results or if the service at the premise was left on or off. | 650_02 | Suzette Sondag |  | Guide | Approved 5/22/08 change control
2008-718 | N | 814_24 | Change to ERCOT logic to use receipt of an 814_04 on a Move In in order to determine if the Move Out should be cancelled. | 814_24 | Kathy Scott | Centerpoint | TX SET Change | Approved 5/22/08 change control
2008-719 | N | 814_11 | SNP should be added as a valid reject code to the 814_11 | 814_11 | Kathryn Thurman | ERCOT | Guide | Approved 5/22/08 change control
2008-720 | N | 814_29 | Add A78 as a valid reject code on the 814_29 | 814_29 | Kathryn Thurman | ERCOT | TX SET Change | Approved 5/22/08 change control
2008-721 | N | 814_03 814_14 | Update gray box that ERCOT will not use customer information in the transactions during a Mass Transition event. | 814_03, 814_14 | Rob Bevill | Green Mountain | Guide | Approved 5/22/08 change control
2008-722 | N | 650_04 | IG currently requires Originating Tran ID and Estimated Restoration Date whenever purpose code = “79”. It is actually only required when purpose code = 79 AND Suspension/Reactivation code = RC001. Causing false rejection of a 650_04 Reactivate after disconnect for denial of access when Originating Transaction ID and Estimated Restoration Date is not also included. And correct gray box for the MTX segment. | 650_04 | Kathy Scott | Centerpoint | TX SET Change | Tabled 5/22/08 change control
2008-723 | N | 810_03 | Add SAC04 codes to the Muni/Coop 810_03 (DAB001, DAB002, and CCA001) | 810_03 | Dave Lowder | Nueces | TX SET Change | Tabled 5/22/08 change control
2008-724 | N | 814_08 | clarify that the TS code should only be used when cancelling a Mass Transition Drop and should not be used for any other purpose | 814_08 | Rob Bevill | Green Mountain | Guide | Approved 5/22/08 change control
2008-725 | N | 867_03 867_02 | Update the Implementation Guide for the 867_03 and 867_02 to show that the REF~JH~I will be used for kWh Generation values only and to state that if there are multiple REF~JH~I loops in the 867_03, that ERCOT will only read and use the first one in the transaction that is encountered. | 867_03, 867_02 | Kathryn Thurman | ERCOT | Guide
2008-726 | N | 810_02 | Revised PUCT Subs. rule 25.181 allows for the breakout of the Energy Efficiency Cost Recovery Factor (EECRF) from TDSPs base rates. With this change any rate case pending or filed by a TDSP after December 31, 2007 would be affected, therefore a new SAC 04 code will be needed to uniquely identify the Energy Efficiency Cost Recovery Factor (EECRF) applied as a line item on the 810_02 invoice sent by the TDSP to the CR. | 810_02 | Kathy Scott | Centerpoint | TX SET Change
2009-727 | N | 814_25 | TX Set Transaction Guide should specify the reject reason “RNE” (Request Not Eligible) for ERCOT use only. | 814_25 | Kathryn Thurman | ERCOT | Guide