## Slide 1: Nodal Program Update
Mike Cleary
Sr. VP and Chief Technology Officer
Notes: <number>

## Slide 2: Agenda
Technical Advisory Committee
6 August 2009
Current Timeline
Recent Achievements
Integrated Testing Update
Risks & Issues
Notes: <number>
<number>

## Slide 3: Nodal Timeline
6 August 2009
Technical Advisory Committee
Notes: <number>
<number>

## Slide 4: CMM Milestone Slip
Technical Advisory Committee
CMM 4.1
  5 of 8 CMM 4.1 components have exited FAT
    2 components’ FAT exit pushed back to Aug. 14
      External Reports
      Custom Calculation Management
    Vendor re-work will push Twelve Trailing Month to Aug. 31
  Good progress made working through excessive defects found in custom components delivered in July
  CMM Phase II work has begun concurrently
  CMM focus on testing, defect remediation for components required for End-to-End Testing
  No impact to End-to-End schedule
6 August 2009
Notes: <number>
<number>

## Slide 5: Significant Accomplishments
6 August 2009
Technical Advisory Committee
Integration Testing Update
  All major systems have consumed, executed against common data set
  All major systems have started Integration Testing
  CRR auction has been executed twice in integrated environment and results processed by settlement and market systems.
  Market Web Services, Outage Scheduler are undergoing integrated testing with common data set (“string tests”)
  Systems Update
  CRR 1.9 exited FAT July 28 (originally scheduled Aug. 31)
  2 CMM 4.1 components finished testing one week ahead of schedule
SEM Go-Live SWAT Team
Notes: <number>
<number>

## Slide 6: Integration Testing Overview
Connector
Control Table
Action Table
Transaction Table
App. Data Table
Source
Control Table
Action Table
Transaction Table
App. Data Table
Sink
Level 1: Connector Team ensures the connector between source and sink system passes a smoke test; results are verified to be correct.
Level 2: Owner Team (generally the Sink Team) demonstrates ability to transfer data correctly across the connector. Data used must be one of: native CCDS, system-generated data based on CCDS, or data from the Data Management team based on a special request. No hand-crafted data is to be used.
Level 3: Owner team (generally the Sink Team) ensures data generated by source system (may be based on the CCDS (or other generated data)) is transferred correctly across the connector to the sink system and demonstrates valid system functionality through running the sink application.
6 August 2009
Technical Advisory Committee

## Slide 7: Integration Testing Update
Technical Advisory Committee
6 August 2009
Connector Scorecard (78 Total) |  |  |  |  | 
 | Definition | Completed | In Progress | Deferred | Started
Level 1 | Connector installed; one record transferred through connector (“smoke test”) | 62 (79% complete) | 4 | 0 | 12
Level 2 | Connector tested using a common data set with multiple records | 28 (36% complete) | 24 | 5 | 21
Level 3 | System-to-system functional test; connector tested with system-generated data | 7 (9% complete) | 20 | 1 | 50
Target Completion
  Levels 1 & 2  September 22, 2009
  Level 3  November 13, 2009

## Slide 8: String Test Summary Table
String Name | High-Level System Flow | Objectives | Status
CRR Auction (Iteration A) | CRR -> S&B -> CRR -> S&B & MMS | Conduct CRR Auction Produce CRR Auction invoices Reflect CRR Ownership/Disseminate CRR Ownership | Complete
CRR Auction (Iteration B) | CRR -> S&B -> CRR -> S&B & MMS | Conduct CRR Auction Produce CRR Auction Invoices Post Invoices to MIS Create CRR Ownership in CRR system | Started
CRR Auction (Iteration C) | TBD | TBD | Not Started
CRR Auction (Iteration D) | TBD | TBD | Not Started
Outage Scheduler | EWS -> OS -> EMS -> OS -> MMS | Web Services Submission to Outage Scheduler Outage Evaluation study Forced Outage Detection Study results consumed into OS Usage of Outage data for Day Ahead by MMS (without running DAM) | Started
Web Services Oct Market Connectivity R2.1 | EWS -> MMS | Submission of specified transactions through EWS and the Market Manager Interfaces Asynchronous validation notifications Will NOT initially run SCED or DAM Will NOT initially produce reports | Started
Technical Advisory Committee
6 August 2009

## Slide 9: String Test Summary Table
String Name | High-Level System Flow | Objectives | Status
DAM (Iteration A) | CRR -> MMS & S&B S&B -> MMS -> S&B | Complete base string process execution based on common data set across CRR/MMS/S&B using DSV July 15th data Data (Verifiable Cost, RMR contract, and Load Ratio Share) transfer from S&B to MMS Data (CRR ownership, MCFRI allocation) transfer from CRR to MMS MMS perform AS obligation calculation and publication MMS perform SFT and MCFRI DA allocation MMS perform CRR offer derating MMS perform DAM DAM solution transfer from MMS to S&B | In Planning: Scheduled to start first week of Aug
DAM (Iteration B) | TBD | TBD | Not Started
DAM (Iteration C) | TBD | TBD | Not Started
DAM (Iteration D) | TBD | TBD | Not Started
RUC | TBD | TBD | Not Started
SCED/RTM | TBD | TBD | Not Started
SASM | TBD | TBD | Not Started
Technical Advisory Committee
6 August 2009

## Slide 10: Risks & Issues to Achieving Nodal’s Major Milestones
Technical Advisory Committee
6 August 2009
Complete Integrated Systems (2-12-10)
  Issue: Resource constraints for Nodal Program
  Issue: Handling CMM delays for program
Market Trials (2-12-10)
  Risk: Reconciling protocols, systems and market expectations
Nodal Go-Live (12-1-10)
  Risk: Data Center capacity concerns
  Risk: Integrity of network model data from market participants
Notes: <number>

## Slide 11
Questions ?

## Slide 12
Appendix
Notes: <number>

## Slide 13: Market Systems Update
Technical Advisory Committee
Project | Sub-Project | Status | Open Critical Defects July 17/July 30 |  |  | 
MMS |  | On schedule MMS 5 final release; currently in FAT and scheduled to exit Aug. 21 MMS 5 Patch A (interface defects) installation scheduled July 31 14 interfaces to test by Sept. 1; testing now underway Market Manager UI to exit FAT July 31; weekly defect cycles planned to address remaining defects in iTest | MMS5 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s | 1 3 81 | 1 3 76 | 
CRR |  | On schedule CRR 1.9 final release; exited FAT July 28 (1 month early) All 9 interfaces in iTest; 4 in execution phase, 5 completed | CRR 1.9 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s | 0 0 0 | 0 0 0 | 
COMS | CMM | Behind schedule CMM 4.1 in FAT at 90% completion; targeted to exit July 31 Two CMM 4.1 components exited FAT July 24 (2 weeks early); three more to exit FAT July 31, two more Aug. 14 Remaining components combined with CMM Phase II to exit FAT February 2010 (internal functions only) 4 of 5 interfaces currently in iTest Outstanding release: CMM Phase II (4.2) | CMM 4.1 |  |  | 
 |  |  | Sev 1s Sev 2s Sev 3s | 1 80 49 | 1 42 50 |  
 | S&B | FAT testing complete; all interfaces currently in iTest Targeting refactoring completion by September 2009 | Sev 1s Sev 2s Sev 3s | 0 0 2 | 0 0 2 | 
 | CSI | FAT testing complete Targeting refactoring completion by August 2009 | Sev 1s Sev 2s Sev 3s | 0 0 16 | 0 0 1 | 
 | REG | Interface/Adapter Level 1 and Level 2 completed Team is currently working on I/A Level 3 testing | Sev 1s Sev 2s Sev 3s | 0 0 0 | 0 0 0 | 
6 August 2009

## Slide 14: Reliability Systems Update
Technical Advisory Committee
Project | Status | Open Critical Defects July 17/July 30 |  |  | 
NMMS | On schedule NMMS 7 final release; exited FAT June 30, installed in iTest on July 14 All 3 interfaces have exited FAT and are currently in iTest (2 complete) | NMMS 7 |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 0 0 49 | 1 0 50 |  
EMS | On schedule EMS 6 Patch 3 deployed to iTest July 1 All 13 interfaces’ test plans now complete; Level 1 & 2 testing has been completed on more than half EMS 6 Patch 4 has started testing in FAT | SPR Patch 3 |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 0 0 105 | 0 0 102 | 
OS | On schedule Common test plan for 12 of 13 interfaces complete 2 defect patches planned for OS UI | OS 2.1.4 |  |  | 
 |  | Sev 1s Sev 2s Sev 3s * | 0 4 74 | 0 8 73 |  
 |  | * excluding ROO defects |  |  | 
6 August 2009

## Slide 15: Market Verification Update
Technical Advisory Committee
Project | Status | Open Critical Defects July 17/July 30 |  |  | 
Interface/Adapter Testing | Completed MMS 5 smoke test in Nodal-iTest; started integration effort Completed EMS load of Common Data Set and started integration with downstream systems Created a new baseline for the Connector list (78 connectors being tracked) | FAT Defects |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 2 107 433 | 3 97 421 |   
 |  | iTest Defects |  |  | 
 |  | Sev 1s Sev 2s Sev 3s | 2 92 89 | 1 67 73 |   
End-to-End Testing | Phase 1 of End-to-End Testing underway; first phase focuses on running E2E functions “string” in the integrated environment with a common dataset: String 1: CRR completed auction String 2: Outage Scheduler String 3: Market Web Services String 4: Day-Ahead Market String 5: Reliability Unit Commitment String 6: Real-Time Market /SCED String 7: Secondary AS Market |  |  |  | 
Market Trials | Preparing 30-day Market Notice for SEM Go-Live Market Trials submission testing begins October |  |  |  | 
Market Readiness | Targeting 35 MP outreach site visits Identified key resources to execute program |  |  |  | 
ERCOT Readiness | Identified 20 departments affected by nodal process; completing detailed transition plans 255 employees yet to complete nodal training (remainder in compliance) |  |  |  | 
Operational Readiness | System cutover validation and implementation under way NMMS performance testing under way |  |  |  | 
6 August 2009