## Guidelines
Rules for Submission of Large Volume of Transactions
Block out all maintenance and release windows
Block out ERCOT holidays
Block out Tuesday or Wednesday, if possible.
Rate of Submission:
During the week
Prior to 5 PM
Submit transactions at a rate of once an hour
In bundles that are no more than 33,000 transactions at a time
OR
After 5 PM
No restrictions as to rate or number of transactions
On weekends
No restrictions as to rate or number of transactions

## Draft Timeline
| November |  |  |  | December |  |  |  | January
|  | Max # | Oncor | Remaining |  | Max # | Oncor | Remaining |  | Max # | Oncor | Remaining
Tues | 3 |  |  |  | 1 |  | 30286
Wed | 4 |  |  |  | 2 | 60000 | 30286 | 29714
Thurs | 5 |  |  |  | 3 | 60000 | 30286 | 29714
Fri | 6 |  |  |  | 4 | 60000 | 30286 | 29714 | 1 | New Year's Weekend
Sat | 7 |  |  |  | 5 | 100000 |  | 100000 | 2
Sun | 8 |  |  |  | 6 |  |  |  | 3
Mon | 9 |  |  |  | 7 | 60000 | 24286 | 35714 | 4 | 60000 | 5500 | 54500
Tues | 10 |  |  |  | 8 |  | 30286 |  | 5 |  | 5500
Wed | 11 |  |  |  | 9 | 60000 | 30286 | 29714 | 6 | 60000 | 5500 | 54500
Thurs | 12 |  |  |  | 10 | 60000 | 27286 | 32714 | 7 | 60000 | 5500 | 54500
Fri | 13 |  |  |  | 11 | 60000 | 30286 | 29714 | 8 | 60000 | 5500 | 54500
Sat | 14 | PR80027 Go Live |  |  | 12 | December Retail Release |  |  | 9 | 100000 |  | 100000
Sun | 15 |  |  |  | 13 |  |  |  | 10
Mon | 16 | 60000 | 24286 | 35714 | 14 | 60000 | 30286 | 29714 | 11 | 60000 | 4500 | 55500
Tues | 17 |  | 24286 |  | 15 |  | 30286 |  | 12 |  | 4500
Wed | 18 | 60000 | 24286 | 35714 | 16 | 60000 | 30286 | 29714 | 13 | 60000 | 4500 | 55500
Thurs | 19 | 60000 | 24286 | 35714 | 17 | 60000 | 5500 | 54500 | 14 | 60000 | 4500 | 55500
Fri | 20 | 60000 | 24286 | 35714 | 18 | 60000 | 5500 | 54500 | 15 | 60000 | 4500 | 55500
Sat | 21 | 100000 |  | 100000 | 19 | 100000 |  | 100000 | 16 | 100000 |  | 100000
Sun | 22 |  |  |  | 20 |  |  |  | 17
Mon | 23 | 60000 | 24286 | 35714 | 21 | 60000 | 5500 | 54500 | 18 | 60000 | 4500 | 55500
Tues | 24 |  | 24286 |  | 22 |  | 5500 |  | 19 |  | 4500
Wed | 25 | 60000 | 24286 | 35714 | 23 | 60000 | 5500 | 54500 | 20 | 60000 | 4500 | 55500
Thurs | 26 | Thanksgiving Weekend |  |  | 24 | Christmas Weekend |  |  | 21 | 60000 | 4500 | 55500
Fri | 27 |  |  |  | 25 |  |  |  | 22 | 60000 | 4500 | 55500
Sat | 28 |  |  |  | 26 |  |  |  | 23 | January Retail Release
Sun | 29 |  |  |  | 27 |  |  |  | 24
Mon | 30 | 60000 | 24286 | 35714 | 28 |  | 5500 |  | 25 | 60000 | 4500 | 55500
Tues |  |  |  |  | 29 |  | 5500 |  | 26 |  | 4500
Wed |  |  |  |  | 30 | 60000 | 5500 | 54500 | 27 | 60000 | 4500 | 55500
Thurs |  |  |  |  | 31 | 60000 | 5500 | 54500 | 28 | 60000 | 4500 | 55500